# NPA 306/639 RELIEF PLANNING COMMITTEE - TIF REPORT

**Date Submitted:** 12 December 2018

**WORKING GROUP:** NPA 306/639 Relief Planning Committee (Ad Hoc)

**REPORT #:** NPA 306/639 TIF Report 1

**File ID:** 306\_639RE01A.docx

**REPORT TITLE**: Relief Planning Committee (RPC) Recommendation for NPA 306/639 Relief (Planning Document and Relief Implementation Plan)

**OUTCOME:** Consensus

**RELATED TASK(s) #:** None

**BACKGROUND:**

The Canadian Numbering Administrator (CNA) initiated Relief Planning based on the results of the January 2018 General Numbering Resource Utilization Forecast (G‑NRUF), which indicated NPA 306/639 would exhaust in June 2022.

On 1 March 2018, the CNA advised the Canadian Radio‑television and Telecommunications Commission (CRTC) staff that NPA 306/639 had entered the relief planning window.

The most recent R-NRUF conducted by the CNA for NPA 306/639 in May 2018 indicated a Projected Exhaust Date for NPA 306/639 of September 2022.

On 11 July 2018, the CRTC issued Telecom Notice of Consultation CRTC 2018‑236*, Establishment of a CISC ad hoc committee for relief planning for area codes 306 and 639 in Saskatchewan*, by which it established the CISC ad hoc Relief Planning Committee (RPC) for NPA 306/639.

In this TIF Report, the NPA 306/639 Relief Planning Committee is submitting a Planning Document which includes the following recommendations:

1. The Relief Method should be a Distributed Overlay of a new NPA Code on NPA 306/639;
2. The Relief NPA Code for NPA 306/639 should be NPA 474, in accordance with Telecom Decision CRTC 2017-38;
3. The Relief Date should be 2 October 2021 in order to provide Carriers and customers with advanced notification and sufficient lead-time to implement relief in NPA 306/639; and
4. The proposed schedule in Section 9 of the Planning Document should be used for NPA 306/639 relief (based on the current Projected Exhaust Date (PED) of September 2022).

In addition, the NPA 306/639 Relief Planning Committee is also submitting a Relief Implementation Plan (RIP).

The attached RIP was prepared in accordance with the above recommendations. The RIP establishes a public framework and timeframe for implementing NPA relief for the province of Saskatchewan. The RIP also addresses the activities, deliverables, and issues impacting more than one individual TSP. It does not cover activities internal to each TSP. This RIP does not cover areas for which there is already an established process for coordination between TSPs to establish service (e.g., interconnection agreements between Carriers).

The NPA 306/639 Relief Planning Committee hereby submits the attached NPA 306/639 Planning Document and the Relief Implementation Plan for CISC and Commission approval.

**RECOMMENDATIONS:**

The NPA 306/639 Relief Planning Committee recommends that the Commission approve the attached Planning Document and Relief Implementation Plan for NPA 306/639.

**ATTACHMENTS:**



NPA 306/639 Planning Document



NPA 306/639 Relief Implementation Plan