**CRTC INTERCONNECTION STEERING COMMITTEE**

**TIF REPORT**

**Date Submitted:             DD MMMM YYYY**

**WORKING GROUP: NPA 343/613 RPC**

**REPORT #:      2                                                            File ID: 343-613RE02A**

**REPORT TITLE**: Revisions to the NPA 343/613 relief implementation schedule

**OUTCOME: CONSENSUS**

**RELATED TASK(s) #:**

**BACKGROUND:**

On 12 March 2021, the NPA 343/613 Relief Planning Committee approved TIF Report 343-613RE01A and submitted it to the CISC for consideration.

On 17 May 2021 it was approved by the CISC and sent to the CRTC.

On 10 November 2021, the CRTC issued Telecom Decision CRTC 2021-372 which approved the recommendations in 343-613RE01A including a Relief Date of 26 March 2022.

**FACTORS:**

The relief implementation schedule in the TIF Report had an expected Telecom Decision date of 23 July 2021 and several of the activities in the relief schedule were based on that date. Since the Decision was issued 3 months later than expected for an NPA that is already in a Jeopardy Condition, several of the deadlines for listed activities have been missed.

To meet the CRTC-approved Relief Date of 26 March 2022, the RPC must revise the relief implementation schedule.

**ALTERNATIVES:**

n/a

**ANALYSIS:**

To meet the CRTC-approved Relief Date, which is necessary due to the pending exhaust and Jeopardy Condition in NPA 343/613, the RPC should revise the schedule without resubmitting it for CRTC approval as the key items in the Decision (Relief Date, new NPA and Relief Method) will be kept.

**CONCLUSIONS:**

The RPC has revised the relief schedule for NPA 343/613 to meet the CRTC-approved Relief Date of 26 March 2022. This schedule will replace the one previously included in the Relief Implementation Plan.

**RECOMMENDATIONS:**

The RPC is submitting this report to the CISC for information purposes only to maintain the CRTC-approved Relief Date (26 March 2022).

**ATTACHMENTS:**



Revised Relief Implementation Plan



Revised Relief Implementation Schedule