CRTC INTERCONNECTION STEERING COMMITTEE

CONTRIBUTION FORM:

Working Group:       CSCN                     Date of Submission: 15 January 2026

Contribution #: 312B

TIF #:      125                                                         File ID:

Task Title:  TBP Rollout Schedule

Related to Task(s) ID:  117, 118

Contributor:

Name:		Joey-Lynn Abdulkader and Marie-Christine Hudon

Company:	Bell Canada

Address:

Tel:

Fax:

E-mail:

Distribution to:	CSCN

Subject:  Proposed Rollout Scheule for Thousand-Block Pooling (“TBP”)

Proposal for Phased Implementation of Thousand-Block Pooling (TBP) in Canada

Background and Commission Direction

On 28 November 2025, the Canadian Radio-television and Telecommunications Commission (CRTC) issued Telecom Decision CRTC 2025-321, “Modification of deadline for thousand-block pooling.” At paragraph 37 of the Decision, the Commission made several key requests and directives as follows:

a) requests the CSCN to develop a schedule for the phased-in implementation of TBP, by exchange, taking into account CO code demand and TSP readiness, and file it for information with the Commission no later than 30 March 2026, with:

i. the first exchange transitioning to TBP no later than 28 July 2026; and

ii. the final exchange transitioning to TBP no later than 28 July 2027

b) directs all LECs and wireless carriers to actively participate in developing the exchange implementation timeline under the leadership of the CSCN, either individually or through consolidated groups with shared representation, and complete the implementation of TBP as detailed in the CSCN schedule; and

c) expects that all LECs and wireless carriers will continue to actively work towards TBP readiness as guided by the CSCN’s TBP checklist, as applicable.

### Rollout Approach

In accordance with the Decision, we have developed a phased rollout schedule commencing with a trial in Markam on 28 July 2026 and concluding with the final exchange on 28 July 2027. As indicated in the carriers’ submission dated 24 July 2025, the carriers proposed an exchange-based rollout that aligns with the phased approach successfully employed in the United States (U.S.). Consistent with the U.S. approach, which prioritized deployment in the Top 100 MSAs, we recommend an initial rollout encompassing the top 110 Canadian exchanges with highest demand for numbering resources according to the criteria detailed below.

Selection Criteria and Phase-Gate Conditions

Exchanges chosen for the first year of the rollout are those with at least 12 NPA-NXXs ordered between 2015 and 2025, according to data from the Canadian Numbering Administrator (CNA) in contribution CNCO313A. This criterion ensures TBP is deployed where it will be most effective and aligns with the U.S. approach, which prioritises larger, high-demand exchanges during the initial deployment year.

Markham Trial

TBP will initially launch in the Markham, Ontario exchange on 28 July 2026 (see contribution CNCO292D.docx for details). The successful launch and evaluation of TBP in Markham will serve as a foundation for expanding TBP to additional exchanges, in phases, based on carrier readiness. The list of exchanges included in the proposed phased rollout plan are provided in the table below.

Note: exchanges involving entities with an ITPA presence are excluded until 28 July 2027. This exclusion is based on the list of ITPA members included in the ITPA Part 1 application submitted on 27 June 2025.

#### Phased Rollout Timeline

- Phase 1A (2026-09-29): Launch exchanges within the two most populous provinces in the two largest Incumbent Local Exchange Carrier (ILEC) territories.

- Phase 1B (2026-12-01): Continue rollout in the same regions.

- Phase 2 (2027-02-23): Launch exchanges in Alberta and Quebec.

- Phase 3 (2027-05-24): Launch exchanges in the Atlantic provinces, Manitoba, Saskatchewan, Yukon, and the Northwest Territories.

- Phase 4 (2027-07-28): Include exchanges with an Independent Telecommunications Providers Association (ITPA) presence, i.e., those excluded from prior phases.

Phased Deployment Schedule for TBP Across Canadian Exchanges

| Phase | Date | Exchange | Province |
| --- | --- | --- | --- |
| Launch | 2026-07-28 | MARKHAM | ON |
| 1A | 2026-09-29 | 100 MILE HOUSE | BC |
|  |  | ABBOTSFORD | BC |
|  |  | AJAX-PICKERING | ON |
|  |  | ALDERGROVE | BC |
|  |  | ALLISTON | ON |
|  |  | AURORA | ON |
|  |  | BARRIE | ON |
|  |  | BELLEVILLE | ON |
|  |  | BRAMPTON | ON |
|  |  | BROCKVILLE | ON |
|  |  | CHATHAM | ON |
|  |  | CHILLIWACK | BC |
|  |  | CLAREMONT | ON |
|  |  | COLLINGWOOD | ON |
|  |  | COOKSVILLE | ON |
|  |  | CRANBROOK | BC |
|  |  | HUNTSVILLE | ON |
|  |  | KANATA-STITTSVILLE | ON |
|  |  | KELOWNA | BC |
|  |  | LEAMINGTON | ON |
|  |  | MAPLE | ON |
|  |  | MILTON | ON |
|  |  | NANAIMO | BC |
|  |  | NEWMARKET | ON |
|  |  | NEW WESTMINSTER | BC |
|  |  | NIAGRA FALLS | ON |
|  |  | NORTH VANCOUVER | BC |
|  |  | OAKVILLE | ON |
|  |  | OSHAWA | ON |
|  |  | PETERBOROUGH | ON |
|  |  | PRINCE GEORGE | BC |
|  |  | RICHMOND | BC |
|  |  | RICHMOND HILL | ON |
|  |  | SAULT STE. MARIE | ON |
|  |  | SOUTH KAMLOOPS | BC |
|  |  | ST. CATHARINES-THOROLD | ON |
|  |  | STREETSVILLE | ON |
|  |  | SUDBURY | ON |
|  |  | THORNHILL | ON |
|  |  | THUNDER BAY | ON |
|  |  | VICTORIA | BC |
|  |  | WEST VANCOUVER | BC |
|  |  | WINDSOR | ON |
| 1B | 2026-12-01 | OTTAWA-HULL | ON |
|  |  | TORONTO | ON |
|  |  | VANCOUVER | BC |
| 2 | 2027-02-23 | ALMA | QC |
|  |  | BANFF | AB |
|  |  | CALGARY | AB |
|  |  | CHICOUTIMI | QC |
|  |  | EDMONTON | AB |
|  |  | FORT MCMURRAY | AB |
|  |  | FOX CREEK | AB |
|  |  | GATINEAU | QC |
|  |  | GRANDE PRAIRIE | AB |
|  |  | HIGH RIVER | AB |
|  |  | LETHBRIDGE | AB |
|  |  | MANIWAKI | QC |
|  |  | MEDICINE HAT | AB |
|  |  | OTTWA-HULL | QC |
|  |  | PEACE RIVER | AB |
|  |  | POINTE-CLAIRE | QC |
|  |  | QUEBEC | QC |
|  |  | RED DEER | AB |
|  |  | STE-GENEVIEVE | QC |
|  |  | ST-JEROME | QC |
|  |  | VALLEYFIELD | QC |
| 3 | 2027-05-24 | AMHERST | NS |
|  |  | BATHURST | NB |
|  |  | CHARLOTTETOWN | PE |
|  |  | FREDERICTON | NB |
|  |  | HALIFAX | NS |
|  |  | MIRAMICHI | NB |
|  |  | MONCTON | NB |
|  |  | MOOSE JAW | SK |
|  |  | OAKBANK | MB |
|  |  | PORTAGE LA PRAIRIE | MB |
|  |  | REGINA | SK |
|  |  | SAINT JOHN'S | NF |
|  |  | SAINT-JOHN | NB |
|  |  | SASKATOON | SK |
|  |  | SYDNEY | NS |
|  |  | TRURO | NS |
|  |  | WHITEHORSE | YT |
|  |  | WINDSOR | NS |
|  |  | WINNIPEG | MB |
|  |  | YELLOWKNIFE | NT |
| 4 | 2027-07-28 | BRANTFORD | ON |
|  |  | BURLINGTON | ON |
|  |  | CORNWALL | ON |
|  |  | DRUMMONDVILLE | PQ |
|  |  | ESSEX | ON |
|  |  | GRANBY | QC |
|  |  | GUELPH | ON |
|  |  | HAMILTON | ON |
|  |  | JOLIETTE | PQ |
|  |  | KINGSTON | ON |
|  |  | KITCHENER-WATERLOO | ON |
|  |  | LINDSAY | ON |
|  |  | LISTOWEL | ON |
|  |  | LONDON | ON |
|  |  | MONTREAL | QC |
|  |  | SARNIA | ON |
|  |  | SHERBROOKE | QC |
|  |  | SOREL | QC |
|  |  | ST-HYACINTHE | QC |
|  |  | TROIS-RIVIERES | QC |
|  |  | VICTORIAVILLE | QC |
|  |  | WOODSTOCK | ON |

Phase-gate for subsequent launches.

Progression to subsequent TBP rollout phases is contingent on the successful completion of the preceding phase, determined by the following criteria:

- Carrier attestations to readiness are complete, and all carriers are able to conduct testing for the affected exchanges.

- No major routing issues or adverse customer impacts are reported for a period of two months following the launch of TBP in an exchange.

- No evidence of dual assignment or issues with portability requests is observed for a period of two months.

Future Deployment

Future deployment in additional exchanges beyond the rollout schedule should follow the proposals and recommendations of the CNA, as the CNA manages the Numbering Resource Utilization Forecast (NRUF) at the exchange level and is best positioned to identify where TBP is warranted. However, as outlined in contribution CNCO237A, the establishment of an Exchange Area Number Pool in any location requires a thousands-block implementation plan submitted by the CSCN and approved by the Commission.

Conclusion

We submit that initiating TBP deployment in the Markham exchange is the most pragmatic, least disruptive, and technically robust approach to begin TBP implementation in Canada. Subsequent phased rollouts (as per the schedule) will follow based on the lessons learned and data gathered from this initial deployment. This proposal is designed to:

- Balance industry readiness by allowing larger carriers to advance while affording additional implementation time for smaller TSPs.

- Enable comprehensive carrier testing and identification of potential errors or misrouting.

- Produce actionable data for the CSCN and the Commission to inform and enhance future rollout phases.

- Support number conservation objectives effectively.

Carriers Intervention, Part 1 application by the independent telecommunications providers associations to delay the implementation of thousands-block pooling for small telecommunications service providers, 24 July 2025.