CRTC INTERCONNECTION STEERING COMMITTEE

CONTRIBUTION FORM:

Working Group:       CSCN                     Date of Submission: 18 February 2026

Contribution #: CNCO312F

TIF #:      125                                                         File ID: CNCO312F

Task Title:  TBP Rollout Schedule

Related to Task(s) ID:  117, 118

Contributor:

Name:		CNA

Company:	CNA

Address:

Tel:

Fax:

E-mail:

Distribution to:	CSCN

Subject:  Proposed Rollout Scheule for Thousand-Block Pooling (“TBP”)

Proposal for Phased Implementation of Thousand-Block Pooling (TBP) in Canada

Background and Commission Direction

On 28 November 2025, the Canadian Radio-television and Telecommunications Commission (CRTC) issued Telecom Decision CRTC 2025-321, “Modification of deadline for thousand-block pooling.” At paragraph 37 of the Decision, the Commission made several key requests and directives as follows:

a) requests the CSCN to develop a schedule for the phased-in implementation of TBP, by exchange, taking into account CO code demand and TSP readiness, and file it for information with the Commission no later than 30 March 2026, with:

i. the first exchange transitioning to TBP no later than 28 July 2026; and

ii. the final exchange transitioning to TBP no later than 28 July 2027

b) directs all LECs and wireless carriers to actively participate in developing the exchange implementation timeline under the leadership of the CSCN, either individually or through consolidated groups with shared representation, and complete the implementation of TBP as detailed in the CSCN schedule; and

c) expects that all LECs and wireless carriers will continue to actively work towards TBP readiness as guided by the CSCN’s TBP checklist, as applicable.

### Rollout Approach

In accordance with the Decision, we have developed a phased rollout schedule commencing with a trial in Markam on 28 July 2026 and concluding with the final exchange on 28 July 2027. As indicated in the carriers’ submission dated 24 July 2025, the carriers proposed an exchange-based rollout that aligns with the phased approach successfully employed in the United States (U.S.). Consistent with the U.S. approach, which prioritized deployment in the Top 100 MSAs, we recommend an initial rollout encompassing the top 110 Canadian exchanges with highest demand for numbering resources according to the criteria detailed below.

Selection Criteria and Phase-Gate Conditions

Exchanges chosen for the first year of the rollout are those with at least 12 NPA-NXXs ordered between 2015 and 2025, according to data from the Canadian Numbering Administrator (CNA) in contribution CNCO313A. This criterion ensures TBP is deployed where it will be most effective and aligns with the U.S. approach, which prioritises larger, high-demand exchanges during the initial deployment year.

To provide further context for the scope and rationale of the rollout, we note that Canada has 2,996 exchanges. The proposed rollout schedule includes 110 exchanges, selected based on demonstrated demand for numbering resources and phased in accordance with the timelines set out in this contribution. This targeted approach focuses industry effort where TBP will deliver measurable benefits; implementing TBP across all exchanges at this timemany of which show little to no demand-would not be a prudent use of resources and would impose costs on legacy systems for which no commensurate benefit would be realized. As demand matures in additional exchanges such that TBP would realize tangible benefits, those exchanges can be added to the TBP program and opened consistent with the implementation milestones and phase-gate criteria set out herein. The industry will bring forward a follow-up application seeking Commission approval for exchanges not included in the initial rollout schedule, in advance of the date by which all exchanges are expected to be TBP-ready under Telecom Decision CRTC 2025-321.

Launch Trial

TBP will initially launch in 3 Exchange Areas (Markham, ON, Brampton, ON and Victoria, BC) on 28 July 2026 (see contribution CNCO292D.docx for details). The successful launch and evaluation of TBP in these Exchange Areas will serve as a foundation for expanding TBP to additional exchanges, in phases, based on carrier readiness. The list of exchanges included in the proposed phased rollout plan are provided in the table below.

Regardless of which Exchange Areas are launching in this initial phase, all Carriers operating in Canada must be performing LNP dips on a TBP ready query database by the Launch Date of July 28, 2026. This may entail changing LNP dip provider.

Any Carrier that has not successfully completed testing of TBP in a production environment will have the following restrictions imposed in TBP-ready Exchanges until such time as they have successfully completed testing:

- The Carrier will be ineligible to receive any CO Codes or Blocks in any exchange open for TBP.

- The Carrier must agree not to return or donate any Blocks from existing CO Code inventories.

Note: exchanges involving entities with an ITPA presence are excluded until 28 July 2027. This exclusion is based on the list of ITPA members included in the ITPA Part 1 application submitted on 27 June 2025.

#### Phased Rollout Timeline

- Phase 1A (2026-09-29): Launch exchanges within the two most populous provinces in the two largest Incumbent Local Exchange Carrier (ILEC) territories.

- Phase 1B (2026-12-01): Continue rollout in the same regions.

- Phase 2 (2027-02-23): Launch exchanges in Alberta and Quebec.

- Phase 3 (2027-05-24): Launch exchanges in the Atlantic provinces, Manitoba, Saskatchewan, Yukon, and the Northwest Territories.

- Phase 4 (2027-07-28): Include exchanges with an Independent Telecommunications Providers Association (ITPA) presence, i.e., those excluded from prior phases.

Phased Deployment Schedule for TBP Across Canadian Exchanges

| Phase Order | Phase Name | Date | Exchange Area (CNAS) | Rate Center (BIRRDS) | Province (Canada Post) |
| --- | --- | --- | --- | --- | --- |
| 1 | 1-LaunchTrial | 2026-07-28 | Brampton | BRAMPTON | ON |
| 1 | 1-LaunchTrial |  | Markham | MARKHAM | ON |
| 1 | 1-LaunchTrial |  | Victoria | VICTORIA | BC |
| 2 | 1A | 2026-12-01 | 100 Mile House | 100 MILE HOUSE | BC |
| 2 | 1A |  | Abbotsford | ABBOTSFORD | BC |
| 2 | 1A |  | Ajax-Pickering | AJAX-PICKERING | ON |
| 2 | 1A |  | Aldergrove | ALDERGROVE | BC |
| 2 | 1A |  | Alliston | ALLISTON | ON |
| 2 | 1A |  | Aurora | AURORA | ON |
| 2 | 1A |  | Barrie | BARRIE | ON |
| 2 | 1A |  | Brockville | BROCKVILLE | ON |
| 2 | 1A |  | Chilliwack | CHILLIWACK | BC |
| 2 | 1A |  | Claremont | CLAREMONT | ON |
| 2 | 1A |  | Collingwood | COLLINGWOOD | ON |
| 2 | 1A |  | Cooksville | COOKSVILLE | ON |
| 2 | 1A |  | Cranbrook | CRANBROOK | BC |
| 2 | 1A |  | Huntsville | HUNTSVILLE | ON |
| 2 | 1A |  | Kanata-Stittsville | KANATA STITTSVILLE | ON |
| 2 | 1A |  | Kelowna | KELOWNA | BC |
| 2 | 1A |  | Leamington | LEAMINGTON | ON |
| 2 | 1A |  | Maple | MAPLE | ON |
| 2 | 1A |  | Milton | MILTON | ON |
| 2 | 1A |  | Nanaimo | NANAIMO | BC |
| 2 | 1A |  | New Westminster | NEW WESTMINSTER | BC |
| 2 | 1A |  | Newmarket | NEWMARKET | ON |
| 2 | 1A |  | Niagara Falls | NIAGARA FALLS | ON |
| 2 | 1A |  | North Vancouver | NORTH VANCOUVER | BC |
| 2 | 1A |  | Oakville | OAKVILLE | ON |
| 2 | 1A |  | Oshawa | OSHAWA | ON |
| 2 | 1A |  | Prince George | PRINCE GEORGE | BC |
| 2 | 1A |  | Richmond | RICHMOND | BC |
| 2 | 1A |  | Richmond Hill | RICHMOND HILL | ON |
| 2 | 1A |  | Sault Ste. Marie | SAULT SAINTE MARIE | ON |
| 2 | 1A |  | South Kamloops | SOUTH KAMLOOPS | BC |
| 2 | 1A |  | St. Catharines-Thorold | SAINT CATHARINES THOROLD | ON |
| 2 | 1A |  | Streetsville | STREETSVILLE | ON |
| 2 | 1A |  | Sudbury | SUDBURY | ON |
| 2 | 1A |  | Thornhill | THORNHILL | ON |
| 2 | 1A |  | West Vancouver | WEST VANCOUVER | BC |
| 3 | 1B | 2027-01-12 | Ottawa-Hull | OTTAWA-HULL | ON |
| 3 | 1B |  | Toronto | TORONTO | ON |
| 3 | 1B |  | Vancouver | VANCOUVER | BC |
| 4 | 2 | 2027-02-23 | Alma | ALMA | QC |
| 4 | 2 |  | Banff | BANFF | AB |
| 4 | 2 |  | Calgary | CALGARY | AB |
| 4 | 2 |  | Chicoutimi | CHICOUTIMI | QC |
| 4 | 2 |  | Edmonton | EDMONTON | AB |
| 4 | 2 |  | Fort McMurray | FORT MCMURRAY | AB |
| 4 | 2 |  | Fox Creek | FOX CREEK | AB |
| 4 | 2 |  | Gatineau | GATINEAU | QC |
| 4 | 2 |  | Grande Prairie | GRANDE PRAIRIE | AB |
| 4 | 2 |  | High River | HIGH RIVER | AB |
| 4 | 2 |  | Lethbridge | LETHBRIDGE | AB |
| 4 | 2 |  | Maniwaki | MANIWAKI | QC |
| 4 | 2 |  | Medicine Hat | MEDICINE HAT | AB |
| 4 | 2 |  | Ottawa-Hull | OTTAWA-HULL | QC |
| 4 | 2 |  | Peace River | PEACE RIVER | AB |
| 4 | 2 |  | Pointe-Claire | POINTE-CLAIRE | QC |
| 4 | 2 |  | Quebec | QUEBEC | QC |
| 4 | 2 |  | Red Deer | RED DEER | AB |
| 4 | 2 |  | St-Jerome | SAINT-JEROME | QC |
| 4 | 2 |  | Ste-Genevieve | SAINTE-GENEVIEVE | QC |
| 4 | 2 |  | Valleyfield | VALLEYFIELD | QC |
| 5 | 3 | 2027-05-25 | Amherst | AMHERST | NS |
| 5 | 3 |  | Bathurst | BATHURST | NB |
| 5 | 3 |  | Charlottetown | CHARLOTTETOWN | PE |
| 5 | 3 |  | Fredericton | FREDERICTON | NB |
| 5 | 3 |  | Halifax | HALIFAX | NS |
| 5 | 3 |  | Miramichi | MIRAMICHI | NB |
| 5 | 3 |  | Moncton | MONCTON | NB |
| 5 | 3 |  | Moose Jaw | MOOSE JAW | SK |
| 5 | 3 |  | Oakbank | OAKBANK | MB |
| 5 | 3 |  | Portage La Prairie | PORTAGE LA PRAIRIE | MB |
| 5 | 3 |  | Regina | REGINA | SK |
| 5 | 3 |  | Saint John | SAINT JOHN | NB |
| 5 | 3 |  | Saskatoon | SASKATOON | SK |
| 5 | 3 |  | St. John's | SAINT JOHNS | NL |
| 5 | 3 |  | Sydney | SYDNEY | NS |
| 5 | 3 |  | Truro | TRURO | NS |
| 5 | 3 |  | Whitehorse | WHITEHORSE | YT |
| 5 | 3 |  | Windsor | WINDSOR | NS |
| 5 | 3 |  | Winnipeg | WINNIPEG | MB |
| 5 | 3 |  | Yellowknife | YELLOWKNIFE | NT |
| 6 | 4 | 2027-07-28 | Belleville | BELLEVILLE | ON |
| 6 | 4 |  | Brantford | BRANTFORD | ON |
| 6 | 4 |  | Burlington | BURLINGTON | ON |
| 6 | 4 |  | Chatham | CHATHAM | ON |
| 6 | 4 |  | Cornwall | CORNWALL | ON |
| 6 | 4 |  | Drummondville | DRUMMONDVILLE | QC |
| 6 | 4 |  | Essex | ESSEX | ON |
| 6 | 4 |  | Granby | GRANBY | QC |
| 6 | 4 |  | Guelph | GUELPH | ON |
| 6 | 4 |  | Hamilton | HAMILTON | ON |
| 6 | 4 |  | Joliette | JOLIETTE | QC |
| 6 | 4 |  | Kingston | KINGSTON | ON |
| 6 | 4 |  | Kitchener-Waterloo | KITCHENER-WATERLOO | ON |
| 6 | 4 |  | Lindsay | LINDSAY | ON |
| 6 | 4 |  | Listowel | LISTOWEL | ON |
| 6 | 4 |  | London | LONDON | ON |
| 6 | 4 |  | Montreal | MONTREAL | QC |
| 6 | 4 |  | Peterborough | PETERBOROUGH | ON |
| 6 | 4 |  | Sarnia | SARNIA | ON |
| 6 | 4 |  | Sherbrooke | SHERBROOKE | QC |
| 6 | 4 |  | Sorel | SOREL | QC |
| 6 | 4 |  | St-Hyacinthe | SAINT-HYACINTHE | QC |
| 6 | 4 |  | Thunder Bay | THUNDER BAY | ON |
| 6 | 4 |  | Trois-Rivieres | TROIS-RIVIERES | QC |
| 6 | 4 |  | Victoriaville | VICTORIAVILLE | QC |
| 6 | 4 |  | Windsor | WINDSOR | ON |
| 6 | 4 |  | Woodstock | WOODSTOCK | ON |

Phase-gate for subsequent launches.

Progression to subsequent TBP rollout phases is contingent on the successful completion of the preceding phase, determined by the following criteria:

- Carrier attestations to TBP readiness are complete, and all carriers were able to successfully conduct production-level testing.

- No major routing issues or adverse customer impacts are reported for a period of two months following the launch of TBP in an exchange.

- No material evidence of a marked increase in dual assignment or issues with portability requests is observed.

Future Deployment

Future deployment in additional exchanges beyond the rollout schedule should follow proposals and recommendations by the CSCN based on data provided by the CNA.

Conclusion

We submit that initiating TBP deployment in the Markham exchange is the most pragmatic, least disruptive, and technically robust approach to begin TBP implementation in Canada. Subsequent phased rollouts (as per the schedule) will follow based on the lessons learned and data gathered from this initial deployment. This proposal is designed to:

- Balance industry readiness by allowing larger carriers to advance while affording additional implementation time for smaller TSPs.

- Enable comprehensive carrier testing and identification of potential errors or misrouting.

- Produce actionable data for the CSCN and the Commission to inform and enhance future rollout phases.

- Support number conservation objectives effectively.

Carriers Intervention, Part 1 application by the independent telecommunications providers associations to delay the implementation of thousands-block pooling for small telecommunications service providers, 24 July 2025.

Pre-launch activities for any Exchange or group of Exchanges shall be as set out in CNCO237B to be amended and clarified.