## Sheet1
| launch date | -90 days | -30 days
Launch Trial | 2026-07-28 | 2026-04-29 | 2026-05-29
1a | 2026-12-01 | 2026-09-02 | 2026-10-02
1b | 2027-01-12 | 2026-10-14 | 2026-11-13
2 | 2027-02-23 | 2026-11-25 | 2026-12-25
3 | 2027-05-25 | 2027-02-24 | 2027-03-26
4 | 2027-07-28 | 2027-04-29 | 2027-05-29

## Coversheet
CRTC INTERCONNECTION STEERING COMMITTEE
CONTRIBUTION FORM:
Working Group: |  | CSCN | Date of Submission: |  | 2026-05-27
Contribution #: |  | 326A
TIF #: | 125 |  | File ID: | CNCO326A
Task Title: |  | TBP Controlled Production Rollout
Related to Task(s) ID:
Contributor:
Name: |  | David Comrie
Company: |  | CNA
Address:
Tel:
Fax:
E-mail:
Distribution to: |  | CSCN
Subject:
Task schedule for TBP implementation for all phases
(See next tab)

## All Phases
Phase Order | Phase Name | Description | Date
1 | Phase 1-Launch Trial | Launch Trial kickoff meeting | 2026-03-24 | Tuesday
1 | Phase 1-Launch Trial | Deadline for Affirmation forms | 2026-04-23 | Thursday
1 | Phase 1-Launch Trial | Notice of Intent to Donate Blocks | 2026-05-21 | Thursday
1 | Phase 1-Launch Trial | Date for Donation Submission for Initial Pool (Part 1A submission) | 2026-06-04 | Thursday
1 | Phase 1-Launch Trial | 3-Exchange Area Launch trial. | 2026-07-28 | Tuesday
2 | Phase 1A | Phase kickoff meeting | 2026-09-02 | Wednesday
2 | Phase 1A | Deadline for Affirmation forms | 2026-10-02 | Friday
2 | Phase 1A | Notice of Intent to Donate Blocks | 2026-09-24 | Thursday
2 | Phase 1A | Date for Donation Submission for Initial Pool (Part 1A submission) | 2026-10-08 | Thursday
2 | Phase 1A | Launch Exchange Areas within the two most populous provinces in the two largest Incumbent Local Exchange Carrier (ILEC) territories. | 2026-12-01 | Tuesday
3 | Phase 1B | Phase kickoff meeting | 2026-10-14 | Wednesday
3 | Phase 1B | Deadline for Affirmation forms | 2026-11-13 | Friday
3 | Phase 1B | Notice of Intent to Donate Blocks | 2026-11-05 | Thursday
3 | Phase 1B | Date for Donation Submission for Initial Pool (Part 1A submission) | 2026-11-19 | Thursday
3 | Phase 1B | Continue rollout in the same regions. | 2027-01-12 | Tuesday
4 | Phase 2 | Phase kickoff meeting | 2026-11-25 | Wednesday
4 | Phase 2 | Deadline for Affirmation forms | 2026-12-25 | Friday
4 | Phase 2 | Notice of Intent to Donate Blocks | 2026-12-17 | Thursday
4 | Phase 2 | Date for Donation Submission for Initial Pool (Part 1A submission) | 2026-12-31 | Thursday
4 | Phase 2 | Launch Exchange Areas in Alberta and Quebec. | 2027-02-23 | Tuesday
5 | Phase 3 | Phase kickoff meeting | 2027-02-24 | Wednesday
5 | Phase 3 | Deadline for Affirmation forms | 2027-03-26 | Friday
5 | Phase 3 | Notice of Intent to Donate Blocks | 2027-03-18 | Thursday
5 | Phase 3 | Date for Donation Submission for Initial Pool (Part 1A submission) | 2027-04-01 | Thursday
5 | Phase 3 | Launch Exchange Areas in the Atlantic provinces, Manitoba, Saskatchewan, Yukon, and the Northwest Territories. | 2027-05-25 | Tuesday
6 | Phase 4 | Phase kickoff meeting | 2027-04-29 | Thursday
6 | Phase 4 | Deadline for Affirmation forms | 2027-05-29 | Saturday
6 | Phase 4 | Notice of Intent to Donate Blocks | 2027-05-21 | Friday
6 | Phase 4 | Date for Donation Submission for Initial Pool (Part 1A submission) | 2027-06-04 | Friday
6 | Phase 4 | Include Exchange Areas with an Independent Telecommunications Providers Association (ITPA) presence, i.e., those excluded from prior phases. | 2027-07-28 | Wednesday
Formulas:
Date = [Date, row below]-14
Date = [Date, row below]-40-14

## Chronological Phase Dates
Phase Order | Phase Name | Description | Date
1 | Phase 1-Launch Trial | Launch Trial kickoff meeting | 2026-03-24
1 | Phase 1-Launch Trial | Deadline for Affirmation forms | 2026-04-23
1 | Phase 1-Launch Trial | Notice of Intent to Donate Blocks | 2026-05-21
1 | Phase 1-Launch Trial | Date for Donation Submission for Initial Pool (Part 1A submission) | 2026-06-04
1 | Phase 1-Launch Trial | 3-Exchange Area Launch trial. | 2026-07-28
2 | Phase 1A | Phase kickoff meeting | 2026-09-02
2 | Phase 1A | Notice of Intent to Donate Blocks | 2026-09-24
2 | Phase 1A | Deadline for Affirmation forms | 2026-10-02
2 | Phase 1A | Date for Donation Submission for Initial Pool (Part 1A submission) | 2026-10-08
3 | Phase 1B | Phase kickoff meeting | 2026-10-14
3 | Phase 1B | Notice of Intent to Donate Blocks | 2026-11-05
3 | Phase 1B | Deadline for Affirmation forms | 2026-11-13
3 | Phase 1B | Date for Donation Submission for Initial Pool (Part 1A submission) | 2026-11-19
4 | Phase 2 | Phase kickoff meeting | 2026-11-25
2 | Phase 1A | Launch Exchange Areas within the two most populous provinces in the two largest Incumbent Local Exchange Carrier (ILEC) territories. | 2026-12-01
4 | Phase 2 | Notice of Intent to Donate Blocks | 2026-12-17
4 | Phase 2 | Deadline for Affirmation forms | 2026-12-25
4 | Phase 2 | Date for Donation Submission for Initial Pool (Part 1A submission) | 2026-12-31
3 | Phase 1B | Continue rollout in the same regions. | 2027-01-12
4 | Phase 2 | Launch Exchange Areas in Alberta and Quebec. | 2027-02-23
5 | Phase 3 | Phase kickoff meeting | 2027-02-24
5 | Phase 3 | Notice of Intent to Donate Blocks | 2027-03-18
5 | Phase 3 | Deadline for Affirmation forms | 2027-03-26
5 | Phase 3 | Date for Donation Submission for Initial Pool (Part 1A submission) | 2027-04-01
6 | Phase 4 | Phase kickoff meeting | 2027-04-29
6 | Phase 4 | Notice of Intent to Donate Blocks | 2027-05-21
5 | Phase 3 | Launch Exchange Areas in the Atlantic provinces, Manitoba, Saskatchewan, Yukon, and the Northwest Territories. | 2027-05-25
6 | Phase 4 | Deadline for Affirmation forms | 2027-05-29
6 | Phase 4 | Date for Donation Submission for Initial Pool (Part 1A submission) | 2027-06-04
6 | Phase 4 | Include Exchange Areas with an Independent Telecommunications Providers Association (ITPA) presence, i.e., those excluded from prior phases. | 2027-07-28