CRTC INTERCONNECTION STEERING COMMITTEE

TIF REPORT

Date Submitted:		30 June 2026

WORKING GROUP:	CSCN

REPORT #:			163A		File ID:  CNRE163A

REPORT TITLE:		Status Report #10, Thousand-Block Pooling, Canadian Implementation

OUTCOME: ONGOING

RELATED TASK(s) #: 118, 119, 120, 125

BACKGROUND:

On 5 February 2024, the CRTC issued Telecom Regulatory Policy CRTC 2024-26 - Implementing thousand-block pooling.

Paragraph 31 of the Policy directs the CRTC Interconnection Steering Committee (CISC) to:

- facilitate and monitor the implementation of TBP and assist in resolving any challenges;

- file quarterly progress reports on 30 March, 30 June, 30 September, and 30 December until TBP is operational; and

- as part of its first quarterly progress report, advise the Commission as to whether the segregation of numbers between wireless and wireline technology must be retained or whether this requirement can be eliminated as a further way to preserve numbers.

Accordingly, the CSCN, as a CISC working group, has taken on the task of providing the quarterly reports.

RECOMMENDATIONS:

CSCN TIF 117 working group respectfully submits this Status Report #10 pursuant to the Commission’s direction.

ATTACHMENTS:  Status Report #10

CRTC Interconnection Steering Committee

Canadian Steering Committee on Numbering

Per para. #31 of CRTC 2024-26

Thousand-Block Pooling TIF 117

Status Report #10 – CNRE163A

Version 1.0

30 June 2026

Contents

Background	1

TIF Work Breakdown	1

Production Thousands-Block Pooling end-to-end testing	1

Thousand Block Pooling Task List	3

Carrier Checklist for Thousands Block Pooling	3

TIF 117 - TBP Implementation Monitoring	3

TIF 118 - Update CSCN-Administered Guidelines for Thousands-Block Pooling	4

TIF 119 - Report of inclusion of unused numbers from previously assigned CO Codes in pool	7

TIF 120 - Report on LIR expansion or Exchange Area consolidation opportunities	8

TIF 125 - TBP Controlled Production Rollout	8

TIF 126 - Update the Canadian TBCOCAG and Appendix A (Audits)	9

Appendix A: Thousand Block Pooling Task List	9

Appendix B: Carrier Checklist for Thousands Block Pooling	9

# Background

On 5 February 2024, the CRTC issued Telecom Regulatory Policy CRTC 2024-26 - Implementing thousand-block pooling.

Paragraph 31 of the Policy directs the CRTC Interconnection Steering Committee (CISC) to:

- facilitate and monitor the implementation of TBP and assist in resolving any challenges;

- file quarterly progress reports on 30 March, 30 June, 30 September, and 30 December until TBP is operational; and

- as part of its first quarterly progress report, advise the Commission as to whether the segregation of numbers between wireless and wireline technology must be retained or whether this requirement can be eliminated as a further way to preserve numbers.

  - This advice was provided in the 30 March 2024 quarterly report

Accordingly, the CSCN, as a CISC working group, has taken on, via TIF 117, the task of providing the quarterly reports.

# TIF Work Breakdown

CSCN has formed the following TIFs for industry participants to define the guidelines and procedures for TBP:

TIF 117 - TBP Implementation Monitoring

TIF 118 - Update CSCN-Administered Guidelines for Thousands-Block Pooling

TIF 119 - Report of inclusion of unused numbers from previously assigned CO Codes in pool

TIF 120 - Report on LIR expansion or Exchange Area consolidation opportunities

TIF 125 - TBP Controlled Production Rollout

TIF 126 - Update the Canadian TBCOCAG and Appendix A (Audits)

# Production Thousands-Block Pooling end-to-end testing

A collaborative group of CSCN Industry participants has established and is progressing through many end-to-end testing activities related to the launch of TBP in Canada.

As of the date of this report 10 June 2026:

- Production NPAC has been enabled for TBP (May 18, 2025).

- All LSMS and SOA vendors used by Canadian carriers for number porting and routing have passed certification testing. (June 20, 2025)
Note: With the industry desire to receive TN range notifications from the NPAC, additional testing is required by LSMS and SOA vendors if carriers wish to enable TN range notifications.

An additional database was identified but has been since passed certification as of early September.

- 26 test pooled CO Codes have been assigned by the CNA so far. The following table shows the planned and assigned codes. Codes missing the OCN and Date Assigned are currently only planned. (2026-05-29)

| # | Exchange Area | NPA | NXX | OCN | Company | Date Assigned |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Vancouver | 257 | 945 | 8086 | TELUS | 2025-04-04 |
| 2 | Vancouver | 257 | 946 | 497E | Rogers | 2025-04-08 |
| 3 | Halifax | 782 | 945 | 329A | Bell | 2025-04-03 |
| 4 | Halifax | 782 | 946 | 4878 | Eastlink | 2025-04-10 |
| 5 | Toronto | 942 | 945 | 8051 | Bell | 2025-04-08 |
| 6 | Toronto | 942 | 946 | 8821 | Rogers | 2025-04-09 |
| 7 | Montreal | 263 | 945 | 328F | Videotron | 2025-04-02 |
| 8 | Montreal | 263 | 946 | 8050 | Bell | 2025-04-09 |
| 9 | Regina | 474 | 945 | 9868 | SaskTel | 2025-04-08 |
| 10 | Regina | 474 | 946 | 2782 | TELUS | 2025-04-04 |
| 11 | Rimouski | 367 | 945 | 8083 | TELUS | 2025-04-04 |
| 12 | Rimouski | 367 | 946 | 984C | Bell | 2025-04-09 |
| 13 | Ste-Victoire | 354 | 945 | 818D | CoopTEL | 2025-04-22 |
| 14 | Ste-Victoire | 354 | 946 | 843D | Sogetel | 2025-06-26 |
| 15 | Thunder Bay | 807 | 945 | 8303 | TELUS Mobility | 2025-08-13 |
| 16 | Thunder Bay | 807 | 946 | 8094 | Thunder Bay Telephone | 2025-08-18 |
| 17 | Brandon | 584 | 945 | 120F | Westman Communications | 2025-08-28 |
| 18 | Brandon | 584 | 946 | 8088 | Bell MTS | 2025-09-12 |
| 19 | London | 382 | 945 | 2776 | MNSI | 2025-09-29 |
| 20 | London | 382 | 946 | 8226 | Execulink Telecom Inc. | 2025-10-03 |
| 21 | Terrace | 257 | 947 | 2933 | BELL West | 2025-09-29 |
| 22 | Terrace | 257 | 948 | 705F | City West | 2025-10-09 |
| 23 | Yellowknife | 867 | 945 | 8092 | Northwestel | 2025-10-01 |
| 24 | Yellowknife | 867 | 946 | 940G | Ssi | 2025-10-01 |
| 25 | Stratford | 382 | 947 | 004G | Quadro | 2026-01-30 |
| 26 | Stratford | 382 | 948 | 400E | Mornington | 2026-02-02 |
| 27 | Kingston | 753 | 945 |  | Iristel |  |
| 28 | Kingston | 753 | 946 |  | WTC |  |

- The following table shows the number of Thousands Blocks applications processed by the CNA, broken down by category. The categories are:

  - Assigned - where a Block was successfully assigned),

  - Recovered - where a Block was donated back and made available to other TSPs to test and

  - Updated - where an application was processed to update a Block’s information, an application was denied (for various reasons) or it was cancelled by the applicant.

(2026-05-29)

| Category | Number of Applications Processed |
| --- | --- |
| Assigned | 88 |
| Recovered | 26 |
| Updated | 17 |

Up-to-date status assignments are available on the CNA website at: https://cnac.ca/co_codes/co_block_status.htm

- Special NRUF was requested to capture utilization information prior to launch of TBP. The most recent S-NRUF results were reviewed and approved by CRTC staff and they were published on 25 March 2026.

- Carriers are in the process of updating their LSMS and SOA profiles to support TBP.

- Directions to carriers for updating their LSMS profiles, SOA profiles and CO Code level filters are available from CLNPC, a copy of which is posted on the CSCN Drafts page.

- Carrier checklist for TBP readiness has been approved by CSCN and sent to CNAC for use (20 June 2025). The CNAC TBP Coordinator has sent out requests for TSPs to complete the checklist online.

- CNA interface to production NPAC is operational. 79 Part 1B forms and 27 Part 5 forms have been generated by the CNA for NPAC. (2026-03-16)

# Thousand Block Pooling Task List

A collaborative group of TIF 117 participants have been maintaining the task list noting progress to date for the overall industry implementation of TBP in the form of several updated contributions. Details of contributions since the last TIF 117 report are noted in the TIF 117 commentary below.

During discussion at CSCN 135 on 9 June 2026, it was decided that the Thousand Block Pooling Task List is no longer necessary and will not be attached in future reports.

TBP activity is managed with the implementation documents available here: https://cnac.ca/co_codes/TBP/TBP_Implementation.htm

# Carrier Checklist for Thousands Block Pooling

A collaborative group of TIF 117 participants have created a checklist to monitor the progress to date.

A report was submitted by CNAC to the CRTC.

# TIF 117 - TBP Implementation Monitoring

This TIF met during CSCN 132 on 10 & 11 June 2025 and on 20 June 2025. Quarterly reports will be submitted on or before 30 March, 30 June, 30 September, and 30 December until TBP is operational.

| Contribution Name | Submitter | Date Posted |
| --- | --- | --- |
| CNCO262E - Bell/Sasktel/COMsolve contribution - TIF 117 - Thousand Block Pooling Task List | Bell/Sasktel/COMsolve | 2025-02-07 |
| CNCO262F - Bell contribution - TIF 117 - Thousand Block Pooling Task List | Bell/Sasktel/COMsolve | 2025-02-19 |
| CNCO284A - CLNPC/Teksavvy/Eastlink/CTA/Transunion contribution - TIF 117 - Clarification and suggested edits for TBP Task List | CLNPC/Teksavvy/ Eastlink/CTA/Transunion | 2025-03-06 |
| CNCO285A - CSCN contribution - TIF 117 - Draft March 2025 TBP monitoring report | CSCN | 2025-03-17 |
| CNCO262G - CSCN contribution - TIF 117 - TBP Task List | CSCN | 2025-03-17 |
| CNCO262H - CSCN contribution - TIF 117 - TBP Task List | CSCN | 2025-03-21 |
| CNCO288A - COMsolve/CTA/Bell contribution - TIF 117 - Carrier Checklist for Thousands Block Pooling | CSCN | 2025-06-03 |
| CNCO288B - CSCN contribution - TIF 117 - Carrier Checklist for Thousands Block Pooling | CSCN | 2025-06-13 |
| CNCO289A - CSCN contribution - TIF 117 - Draft quarterly TBP implementation report #6 | CSCN | 2025-06-13 |
| CNCO262I - Bell contribution - TIF 117 - Thousands-Block Pooling Task List | Bell | 2025-10-02 |
| CNCO297A - CNA contribution - TIF 117 - Draft quarterly TBP implementation report #7 | CNA | 2025-09-12 |
| CNCO310A - CNA contribution - TIF 117 - Draft quarterly TBP implementation report #8 | CNA | 2025-12-03 |
| CNCO321A - CNA contribution - TIF 117 - Draft quarterly TBP implementation report #9 | CNA | 2026-03-03 |
| CNCO321B - CSCN Contribution - TIF 117 - TBP monitoring Mar 2026 | CSCN | 2026-03-17 |
| CNCO327A – CNA contribution – TIF 117 - Draft quarterly TBP implementation report #10 | CNA | 2026-06-02 |

# TIF 118 - Update CSCN-Administered Guidelines for Thousands-Block Pooling

TIF 118 was worked on extensively during the CSCN 134 Face to Face meetings on 10 & 11 February 2026.

A letter was sent to the Commission from the CSCN requesting either expedited approval or advanced interim approval of the proposed TBCOCAG to allow the CNA to process Block donations prior to any implementation dates.

The following contributions have been received under TIF 118:

| Contribution Name | Submitter | Date Posted |
| --- | --- | --- |
| CNTF118A - TIF 118 (Proposed) - Update CSCN-Administered Guidelines for Thousands-Block Pooling | CSCN | 2024-03-14 |
| CNCO234A - COMsolve contribution - TIF 118 - Flow chart of when to request a new CO Code in a pooled area | COMsolve | 2024-04-12 |
| CNCO235A - COMsolve contribution - TIF 118 - TBP Guideline Definitions | COMsolve | 2024-04-15 |
| CNCO237A - COMsolve contribution - TIF 119 - TBP implementation plan & milestones | COMsolve | 2024-04-23 |
| CNCO238A - KRob Solutions contribution - TIF 118 - Thousands Block Pooling Utilization Exceptions | KRob Solutions | 2024-04-25 |
| CNCO236B - COMsolve contribution - TIF 118 - TBP Block Return Checklist | COMsolve | 2024-04-30 |
| CNCO240A - COMsolve contribution - TIF 118 - TBP Paragraph 51 questions | COMsolve | 2024-05-02 |
| CNCO238B - KRob Solutions contribution - TIF 118 - Thousands Block Pooling Return Exceptions | COMsolve | 2024-05-02 |
| CNCO236C - CSCN contribution - TIF 118 - TBP Block Return Checklist | CSCN | 2024-05-03 |
| CNCO241A - COMsolve contribution - TIF 118 - Semi-annual forecasting requirements | COMsolve | 2024-05-07 |
| CNCO242A - COMsolve contribution - TIF 118 - LSMS and SCP Functionality in a TBP Environment | COMsolve | 2024-05-07 |
| CNCO244A - CNA contribution - TIF 118 - NECA company codes | CNA | 2024-05-13 |
| CNCO248A - COMsolve contribution - TIF 118 - Draft paragraph 51 report | COMsolve | 2024-05-15 |
| CNCO249A - Rogers/Bell/KRob Solutions contribution - TIF 118 - Recommendations on timeline and utilization for ordering numbering resources | Rogers/Bell/KRob Solutions | 2024-05-28 |
| CNCO248B - Rogers\Bell\KRob Solutions contribution - TIF 118 - Draft paragraph 51 report | Rogers/Bell/KRob Solutions | 2024-06-06 |
| CNCO252A - Cogeco contribution - TIF 118 - Sequential Numbering Assignment | Cogeco | 2024-06-10 |
| CNCO248C - CSCN contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26 | CSCN | 2024-06-12 |
| CNCO248D - TELUS contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26 | TELUS | 2024-06-17 |
| CNCO248E - Bell contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26 | Bell | 2024-06-17 |
| CNCO248F - CSCN contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26 | CSCN | 2024-06-18 |
| CNCO248G - CSCN contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26 | CSCN | 2024-06-20 |
| CNCO252B - Cogeco contribution - TIF 118 - Sequential Numbering Assignment | Cogeco | 2024-06-21 |
| CNCO248H - CSCN contribution - TIF 118 - Draft report (NO MARKUP) for paragraph 51 from Telecom Regulatory Policy 2024-26 | CSCN | 2024-06-21 |
| CNCO248I - CSCN contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26 | CSCN | 2024-06-25 |
| CNCO258A - Bell Canada contribution - TIF 118 - Revisions to Recommendation 5 of Draft CNRE144A | Bell | 2024-07-09 |
| CNCO258B - CNA contribution - TIF 118 - Revisions to Recommendation 5 of Draft CNRE144A | CNA | 2024-07-09 |
| CNCO261A - COMsolve contribution - TIF 118 - Block Assignment Process | COMsolve | 2024-08-15 |
| CNCO262C - Bell contribution - TIF 118 - Thousand Block Pooling Task List | Bell | 2024-09-12 |
| CNCO262D - CSCN contribution - TIF 118 - Thousand Block Pooling Task List | CSCN | 2024-09-16 |
| CNCO261B - COMsolve contribution - TIF 118 - Block Assignment Process | COMsolve | 2024-09-19 |
| CNCO278B - CSCN contribution - TIF 118 - Proposed Part 1A form | CSCN | 2024-12-17 |
| CNCO280A - COMsolve contribution - TIF 118 - Proposed Part 1B for use in Canada for 1K block assignments | COMsolve | 2025-01-22 |
| CNCO281A - Rogers contribution - TIF 118 - TBP Critical Path Items | Rogers | 2025-02-06 |
| CNCO282A - Bell Canada contribution - TIF 118 - Thousand Block Pooling (TBP) Bell Canada Assumptions | Bell Canada | 2025-02-07 |
| CNCO283A - COMsolve contribution - TIF 118 - CNA Order Flow Diagram | COMsolve | 2025-02-10 |
| CNCO278C - CSCN contribution - TIF 118 - Proposed Part 1A form | CSCN | 2025-02-14 |
| CNCO298A - TIF 118 CDT contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix F | TIF 118 CDT | 2025-09-23 |
| CNCO298B - CSCN contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix F | CSCN | 2025-10-20 |
| CNCO299A - TIF 118 CDT contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix C | TIF 118 CDT | 2025-09-23 |
| CNCO299B - CSCN contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix C | CSCN | 2025-10-21 |
| CNCO299C - CSCN contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix C | CSCN | 2025-10-24 |
| CNCO302B - CNA contribution - TIF 118 - TBP updates to Appendix B of the CO Code Guideline | CNA | 2025-10-20 |
| CNCO303A - COMsolve contribution - TIF 118 - Updated Appendix E for Thousands-Block Pooling | COMsolve | 2025-10-02 |
| CNCO303B - CSCN contribution - TIF 118 - Updated Appendix E for Thousands-Block Pooling | CSCN | 2025-10-20 |
| CNCO304A - COMsolve/CNA contribution - TIF 118 - Proposed Canadian TBCOCAG | CNA/COMsolve | 2025-10-20 |
| CNCO305A - CNA contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP | CNA | 2025-10-22 |
| CNCO305B - CSCN contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP | CSCN | 2025-10-24 |
| CNCO305C - KRob Solutions contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP | Krob Solutions | 2025-10-29 |
| CNCO305D - CNA contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP | CNA | 2025-10-29 |
| CNCO305E - CSCN contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP | CSCN | 2025-10-31 |
| CNCO308A - COMsolve contribution - TIF 118 - Discussion of TBCOCAG Section 4.2.3 | COMsolve | 2025-11-03 |
| CNCO311A - CSCN contribution - TIF 118 - Coversheet for TIF Report CNRE158A - Proposed Initial Canadian TBCOCAG – Version 1.0 (posted 2025-12-11) | CSCN | 2025-12-11 |
| CNCO304C - CSCN contribution - TIF 118 - Proposed Canadian TBCOCAG(posted 2025-12-11) | CSCN | 2025-12-11 |
| CNCO302C - CSCN contribution - TIF 118 - TBP updates to Appendix B of the CO Code Guideline(posted 2025-12-11) | CSCN | 2025-12-11 |
| CNCO303C - CSCN contribution - TIF 118 - Updated Appendix E for Thousands-Block Pooling(posted 2025-12-11) | CSCN | 2025-12-11 |
| CNCO298C - CSCN contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix F(posted 2025-12-11) | CSCN | 2025-12-11 |
| CNCO305F - CSCN contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP(posted 2025-12-11) | CSCN | 2025-12-11 |
| CNCO315A - CNA contribution - TIF 118 - Draft Part 1A for a Pooled CO Code or Block request | CNA | 2026-02-03 |
| CNCO316A - CNA contribution - TIF 118 - Draft Part 1B for a Pooled CO Code or Block request | CNA | 2026-02-03 |
| CNCO315B - CSCN contribution - TIF 118 - Draft Part 1A for a Pooled CO Code or Block request | CSCN | 2026-02-12 |
| CNCO316B - CSCN contribution - TIF 118 - Draft Part 1B for a Pooled CO Code or Block request | CSCN | 2026-02-12 |
| CNCO316C - CNA contribution - TIF 118 - Draft Part 1B for a Pooled CO Code or Block request | CNA | 2026-02-24 |

# TIF 119 - Report of inclusion of unused numbers from previously assigned CO Codes in pool

Consensus Report CNRE145A was sent to CISC on August 6th, 2024.

During CSCN 130, it was noted that there was no additional work required for TIF 119. Agreement was reached during the meeting to close TIF 119.

In Telecom Decision CRTC 2024-239, the Commission stated that with respect to the report on inclusion of unused numbers from previous assignments, they were open to the CSCN filing an extension request for a report if needed.

During the CSCN 131 meeting, participants discussed the possibility of revisiting donations of unused blocks from previously assigned codes after Thousand Block Pooling was implemented on October 6, 2025. The CSCN reached an agreement to change the status of TIF 119 to suspended and would re-open the TIF to address previously assigned codes once the Thousand Block Pooling implementation was completed.

# TIF 120 - Report on LIR expansion or Exchange Area consolidation opportunities

There were no meetings for TIF 120 since the last TIF117 report submitted 30 December 2024.

At CSCN 135, the CSCN reached an agreement to Defer/Suspend TIF 120 until some time after the implementation of TBP.

There have been 4 contributions for TIF 120:

| Contribution Description | Date posted |
| --- | --- |
| CNCO264A - TELUS contribution - TIF 120 - Proposed criteria for Exchange Area consolidation | 2024-08-24 |
| CNCO264B – Bell contribution - TIF 120 - Proposed criteria for Exchange Area consolidation | 2024-10-16 |
| CNCO264C – CSCN contribution - TIF 120 - Proposed criteria for Exchange Area consolidation | 2024-10-17 |
| CNCO264D – Bell contribution - TIF 120 - Proposed criteria for Exchange Area consolidation | 2024-10-18 |

# TIF 125 - TBP Controlled Production Rollout

This TIF was approved by the CSCN on 19 September 2025 and approved by the CISC on 29 September 2025. This TIF is used to coordinate the rollout implementation by way of various scheduling and planning documents.

The kick-off meeting for the first of six implementation phases was held on 24 March 2026.

Kick-off meetings for the next 5 phases are currently scheduled as follows:

| Phase Order | Phase Name | Date |
| --- | --- | --- |
| 2 | Phase 1A | 2026-09-02 |
| 3 | Phase 1B | 2026-10-14 |
| 4 | Phase 2 | 2026-11-25 |
| 5 | Phase 3 | 2027-02-24 |
| 6 | Phase 4 | 2027-04-29 |

The following TBP implementation planning documents have been approved for use by the CSCN under CSCN TIF 125. The documents are updated regularly and describe the overall plan to implement TBP in Canada in a selection of the most impactful Exchange Areas. The documents may be updated regularly by the CSCN as implementation work continues. The most current versions of these planning documents are provided with this report for information purposes to the CRTC.

- CNCO312L - TIF 125 - TBP Canada Rollout Schedule (CSCN-approved 2026-05-12)

- CNCO318D - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges (CSCN-approved 2026-05-12)

The most current versions of these documents are ‘published’ on the CNA website’s Thousands-Block Pooling (TBP) Implementation Page at the following URL:

- https://cnac.ca/co_codes/TBP/TBP_Implementation.htm

The following contributions have been received by the CSCN for TIF 125:

| Contribution Description | Date posted |
| --- | --- |
| CNCO292A - Bell contribution - TIF 125 (Proposed) - TBP Trial Contribution | 2025-09-11 |
| CNCO292B - CSCN contribution - TIF 125 - TBP Trial Contribution | 2025-09-19 |
| CNCO292C - CSCN contribution - TIF 125 - TBP Trial Contribution | 2025-10-27 |
| CNCO292D - Bell contribution - TIF 125 - TBP Trial Contribution | 2025-10-29 |
| CNCO293A - CNA contribution - TIF 125 (Proposed) - TIF form for Proposed TIF 125 | 2025-09-11 |
| CNCO294A - CNA contribution - TIF 125 (Proposed) - TIF report coversheet for Proposed TIF 125( | 2025-09-11 |
| CNCO294B - Bell contribution - TIF 125 - TIF report coversheet for Proposed TIF 125 | 2025-09-26 |
| CNCO306A - CSCN contribution - TIF 125 - TBP Implementation Milestones | 2025-10-27 |
| CNCO307A - CNA contribution - TIF 125 - Exchange Areas and Counts of OCNs, Codes and Codes Assigned in previous years | 2025-10-28 |
| CNCO292D - Bell contribution - TIF 125 - TBP Trial Contribution | 2025-10-29 |
| CNCO312A - Bell contribution - TIF 125 - Proposed TBP Rollout Schedule | 2026-01-12 |
| CNCO313A - CNA contribution - TIF 125 - Exchange Areas and Counts of OCNs, Codes and Codes Assigned in previous years | 2026-01-12 |
| CNCO313B - CNA contribution - TIF 125 - Exchange Areas and Counts of OCNs, Codes and Codes Assigned in previous years | 2026-01-16 |
| CNCO312B - Bell contribution - TIF 125 - Proposed TBP Rollout Schedule | 2026-01-16 |
| CNCO312C - CSCN contribution - TIF 125 - Proposed TBP Rollout Schedule | 2026-01-16 |
| CNCO312D - Bell contribution - TIF 125 - Proposed TBP Rollout Schedule | 2026-02-06 |
| CNCO318A - CSCN contribution - TIF 125 - Steps for rolling out TBP in 1 or more Exchanges | 2026-02-12 |
| CNCO312E - CSCN contribution - TIF 125 - Proposed TBP Rollout Schedule | 2026-02-13 |
| CNCO319A - TIF 125 CDT contribution - TIF 125 - Draft of Carrier Affirmation of Thousands-Block Pooling Readiness form | 2026-02-18 |
| CNCO320A - TIF 125 CDT contribution - TIF 125 - TIF report for TBP Readiness Affirmation Form and Recommendations to Facilitate the Rollout of Thousands-Block Pooling | 2026-02-18 |
| CNCO312F - CNA contribution - TIF 125 - Proposed TBP Rollout Schedule | 2026-02-18 |
| CNCO319B - CSCN contribution - TIF 125 - Draft of Carrier Affirmation of Thousands-Block Pooling Readiness form | 2026-03-09 |
| CNRE160A - TIF 125 - Draft TIF Report - TBP Readiness Affirmation Form and Recommendations to Facilitate the Rollout of Thousands-Block Pooling | 2026-03-09 |
| CNCO312G - Bell-CNA Contribution - TIF 125 - TBP Rollout Schedule 16 March 2026 | 2026-03-17 |
| CNCO322A - Bell Canada Contribution - TIF 125 - TIF Report cover page for TBP rollout | 2026-03-17 |
| CNCO319C - Bell contribution - TIF 125 - Draft of Carrier Affirmation of Thousands-Block Pooling Readiness form | 2026-03-19 |
| CNRE160B - Bell contribution - TIF 125 - Draft TIF Report - TBP Readiness Affirmation Form and Recommendations to Facilitate the Rollout of Thousands-Block Pooling | 2026-03-19 |
| CNCO323A - CSCN contribution - TIF 125 - TBP Phase 1-LaunchTrial Implementation Plan | 2026-03-26 |
| CNCO318B - CSCN contribution - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges | 2026-03-26 |
| CNCO323B - CSCN Contribution - TIF 125 - TBP Phase 1-LaunchTrial Implementation Plan | 2026-03-26 |
| CNCO318C - CSCN Contribution - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges | 2026-03-26 |
| CNCO319D - CSCN Contribution - TIF 125 - Carrier Affirmation of Thousands-Block Pooling (TBP) Readiness form | 2026-03-26 |
| DRAFT CNRE160C - TIF 125 - TBP Readiness Affirmation Form and Recommendations to Facilitate the Rollout of Thousands-Block Pooling | 2026-03-26 |
| CNCO312H - CSCN Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada | 2026-03-26 |
| DRAFT CNRE161A - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada | 2026-03-26 |
| CNCO312I - CSCN Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada | 2026-04-23 |
| CNCO312J - Gosfield Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada | 2026-04-30 |
| CNCO312K - CNA Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada | 2026-05-04 |
| CNCO318D - CNA Contribution - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges | 2026-05-04 |
| CNCO319E - CNA Contribution - TIF 125 - Carrier Affirmation of Thousands-Block Pooling (TBP) Readiness form | 2026-05-04 |
| CNCO312L - CSCN Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada | 2026-05-13 |
| CNCO319F - CSCN Contribution - TIF 125 - Carrier Affirmation of Thousands-Block Pooling (TBP) Readiness form | 2026-05-13 |
| CNCO326A - CNA Contribution - TIF 125 - Task Schedule for all TBP Implementation Phases | 2026-05-27 |

# TIF 126 - Update the Canadian TBCOCAG and Appendix A (Audits)

This TIF was approved by the CSCN 13 February 2026 and approved by the CISC on 31 March 2026.

The CSCN Chair has sent an extension request letter to the CRTC on 2 March 2026. The extension date requested was 26 March 2027.

On 21 April 2026, the CRTC issued a response letter which “suspends the deadline to file the Audit Report. It will reconsider this matter following the conclusion of NOC 2026-61”.

At CSCN 135, the CSCN reached an agreement to Defer/Suspend TIF 126 until some time after the results from proceeding related to Notice of Consultation 2026-61.

| Contribution Description | Date posted |
| --- | --- |
| CNCO314A - Bell contribution - TIF 126 (Proposed) - TIF coversheet for proposed TIF 126 (Update to Appendix A of the Central Office Assignment Guidelines) | 2026-01-14 |
| CNTF126A - CSCN contribution - TIF 126 (Proposed) - Update to Appendix A of the Canadian TBCOCAG | 2026-01-22 |
| CNCO237B - CSCN contribution - TIF 126 - TBP implementation plan & milestones | 2026-01-29 |
| CNCO317A - CNA contribution - TIF 126 - Draft letter from CSCN Chair to the CRTC regarding updates to Appendix A of the CO Code | 2026-02-10 |
| CNCO317B - CSCN contribution - TIF 126 - Draft letter from CSCN Chair to the CRTC regarding updates to Appendix A of the CO Code | 2026-02-12 |

# Appendix A:

CNCO312M - TIF 125 - TBP Canada Rollout Schedule (MS Word document)

# Appendix B:

CNCO318E - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges

# Appendix C:

CNCO326B - TIF 125 - TBP Task Schedule for All Phases (MS Excel file)