NPA 367/418/581 Planning Document (PD)

Version 1.0 – 12 March 2025

TABLE OF CONTENTS

1.	INTRODUCTION	1

2.	NPA RELIEF PLANNING PROCESS	2

3.	NPA RELIEF METHODS	3

4.	NPA EXHAUST INFORMATION	3

5.	RELIEF OPTION	3

5.1.	Distributed Overlay	4

6.	SUMMARY OF RELIEF OPTION	4

7.	DIALLING CHANGES FOR LOCAL CALLS	4

8.	PROPOSED SCHEDULE	5

9.	JEOPARDY CONTINGENCY PLAN (JCP)	0

10.	SELECTION OF RELIEF NPA CODE	7

11.	RECOMMENDATIONS	8

ANNEXES	9

LIST OF ANNEXES

ANNEX A

Figure 1 – Overview Map of NPA 367/418/581	1

Figure 2 – NPA 367/418/581 Actual and Forecast CO Code Assignments	2

Figure 3 – NPA 367/418/581 CO Code Exhaust – July 2024 R-NRUF	2

Figure 4 – Distributed Overlay	3

ANNEX B

Table 1 – NPA 367/418/581 Exchange Areas After Distributed Overlay 	B-1

ANNEX C

Distribution List

ACRONYM LIST

| CATF | Consumer Awareness Task Force |
| --- | --- |
| CNA | Canadian Numbering Administrator |
| CISC | CRTC Interconnection Steering Committee |
| CLEC | Competitive Local Exchange Carrier |
| CLNPC | Canadian Local Number Portability Consortium |
| CO | Central Office |
| CRTC | Canadian Radio-television and Telecommunications Commission |
| CSCN | Canadian Steering Committee on Numbering |
| EAS | Extended Area Service |
| G-NRUF | General Numbering Resource Utilization Forecast |
| ILEC | Incumbent Local Exchange Carrier |
| IPD | Initial Planning Document |
| ISP | Internet Service Provider |
| JCP | Jeopardy Contingency Plan |
| J-NRUF | Jeopardy Numbering Resource Utilization Forecast |
| LEC | Local Exchange Carrier |
| LIR | Local Interconnection Region |
| LNP | Local Number Portability |
| NANP | North American Numbering Plan |
| NANPA | North American Numbering Plan Administrator |
| NITF | Network Implementation Task Force |
| NoC | Notice of Consultation |
| NPA | Numbering Plan Area (Area Code) |
| NRUF | Numbering Resource Utilization Forecast |
| PD | Planning Document |
| PED | Projected Exhaust Date |
| PL | Planning Letter |
| POI | Point of Interconnection |
| PROC | Proposal for Relief of an Overlay NPA Complex |
| PSAP | Public Safety Answering Point |
| RIP | Relief Implementation Plan |
| R-NRUF | Relief Planning Numbering Resource Utilization Forecast |
| RPC | Relief Planning Committee |
| TSP | Telecommunications Service Provider |
| WNP | Wireless Number Portability |
| WSP | Wireless Service Provider |

Planning Document (PD) Numbering Plan Area (NPA) 367/418/581

# INTRODUCTION

Numbering Plan Areas NPA 418, commonly referred to as area code, were originally assigned to Québec by AT&T in 1947 as one of the 86 area codes to be used in Canada and the continental United States.

The following table provides a high-level summary of the history of area code usage in the area currently served by NPA 367/418/581 since 1947.

| Year | Activity |
| --- | --- |
| 1947 | Area Codes 418 to northeast Québec by AT&T |
| 2008 | New area code 581 provided relief using the Distributed Overlay method and mandatory ten-digit local dialling was implemented. |
| 2018 | New area code 367 was implemented using the Distributed Overlay method. |

Forecast results from the July 2024 R-NRUF indicate NPA 367/418/581 is projected to exhaust in August 2027.

NPAs neighbouring NPA 367/418/581 that could be affected by this relief activity include 428/506, 468/819/873, and 709/879.

Area code 367/418/581 consists of 258 Exchange Areas, including Exchange Areas of Alma, Chicoutimi and Québec in the northern and eastern parts of the province of Québec in Canada. A list of the Exchange Areas in NPA 367/418/581 is provided in Annex B.

The table below provides a brief overview of recent activities leading to the development of this PD for NPA 367/418/581.

| Date | Activity |
| --- | --- |
| 30 October 2023 | The CSCN submitted CNRE137B which included a recommendation to set aside NPA 273 for future relief of NPA 367/418/581. For the purposes of this document the new NPA will be 273. |
| 28 March 2024 | January 2024 R-NRUF results indicated a PED of July 2027. |
| 11 September 2024 | July 2024 R-NRUF results indicated a PED of August 2027. This put NPA 367/418/581 in the Relief Planning window, in accordance with the Canadian NPA Relief Planning Guideline, Version 8.0, dated 15 May 2023. The CNA notified Canadian Radio-television and Telecommunications Commission (CRTC) staff and requested a Notice of Consultation. |

This Planning Document is prepared by the RPC in accordance with Telecom Notice of Consultation CRTC 2025-15 and the Canadian NPA Relief Planning Guideline (the Guideline).  A copy of the Guideline is available from the Canadian Radio-Television and Telecommunications Commission (CRTC), CRTC Interconnection Steering Committee (CISC), Canadian Steering Committee on Numbering (CSCN) guidelines web page at: https://crtc.gc.ca/cisc/eng/cisf3fg.htm.

The objective of the NPA Relief Planning process is to ensure that CO Codes and telephone numbers are always available for use by TSPs and their customers in the geographic area requiring relief.

It is very important to closely monitor the CO Code requirements of all existing and prospective CO Code Holders so that relief can be timed to ensure that CO Codes and telephone numbers are always available for service providers and customers.

In this PD, a single option is identified for providing NPA relief in the NPA 367/418/581 geographic area. Given the magnitude of this undertaking, intercompany commitment and co-operation are essential throughout the planning, provisioning and implementation stages of the introduction of the new NPA.

# NPA RELIEF PLANNING PROCESS

The NPA Relief Planning process and the roles of the participants (i.e. CRTC, CNA, CISC, Relief Planning Committee (RPC) participants and Interested Parties) for NPA Relief Planning are identified in the Guideline.

To increase public awareness and participation in the NPA Relief Planning process, the CRTC has determined that NPA RPCs will be established as ad hoc committees of the CISC.  Generally, a separate ad hoc committee is created to deal with relief in each area code.  The CNA, in its function as NPA Relief Planning Coordinator, acts as chair of these ad hoc committees.  Meetings and conference calls of the ad hoc NPA RPCs are all open to public participation and are conducted in accordance with the CISC Administrative Guidelines which are available from the CRTC website at: https://www.crtc.gc.ca/cisc/eng/cag.htm.

NPA Relief Planning is conducted under the regulatory oversight of the CRTC.  Notwithstanding the process detailed in the Guideline, the CRTC may exercise its authority under the Telecommunications Act to alter this process at any time.  The CRTC has the authority under the Telecommunications Act to review, modify and give final approval to the Planning Document (PD) and the Relief Implementation Plan (RIP) developed and submitted by the RPC to the CRTC via the CISC process.

Section 7.1.6 of the Canadian NPA Relief Planning Guideline requires the CNA to create and maintain a distribution list of parties who may be interested in participating in the RPC and to provide them with advance notice of the initial RPC meeting and the release of a PROC.

Any person wishing to participate in the NPA Relief Planning process can contact the CNA and request to be added to the RPC distribution list.  More information on how to participate in CRTC public processes is available at: http://www.crtc.gc.ca/eng/info_sht/g4.htm.

A summary of Canadian geographic area code relief history is available at: https://www.cnac.ca/npa_codes/NPA_History.pdf.

# NPA RELIEF METHODS

The purpose of this section is to identify and briefly describe NPA Relief Methods.

The Guideline states that: “The only NPA Relief Method considered in Canada is the Distributed Overlay Method which superimposes or “overlays” a Relief NPA on top of an entire existing NPA or NPAs.” There are three types of Distributed Overlay:

- a Distributed Overlay over an existing geographic area served by a single existing NPA (a new NPA is overlaid over a single existing NPA (i.e., the geographic area) that is served by a single NPA);

- a Distributed Overlay over an existing geographic area served by multiple existing overlay NPAs (a new NPA is overlaid over a single existing NPA (i.e., the geographic area) that is served by multiple existing overlay NPAs) and,

- a Distributed Overlay over multiple existing geographic areas, each served by one or more existing NPAs (a new NPA is overlaid over multiple existing NPAs (i.e., different geographic areas served by multiple NPAs. This type of overlay may be considered for NPA relief for two or more adjacent NPAs (i.e., geographic areas) within a province).

# NPA EXHAUST INFORMATION

As indicated in the following table, NRUFs for NPA 367/418/581 were used to determine PEDs, (i.e. the dates when CO Codes in NPA 367/418/581 would be expected to exhaust).

| NRUF | Projected Exhaust Date (PED) |
| --- | --- |
| January 2023 G-NRUF | June 2027 |
| July 2023 R-NRUF | June 2027 |
| January 2024 R-NRUF | July 2027 |
| July 2024 R-NRUF | August 2027 |

Refer to Annex A, Figures 2 & 3 for graphs of forecast CO Code demand from current and prospective CO Code Holders and Administrative Codes set aside in area code 367/418/581 for the most recent NRUF (July 2024).

# RELIEF OPTION

The Relief Option as identified and examined in this PD is a Distributed Overlay over an existing geographic area served by multiple existing overlay NPAs.

Using this method, a new NPA is overlaid over an existing NPA (i.e., the geographic area) that is served by the overlay complex of NPAs 367/418/581.

The Relief Option identified above was evaluated using the following assumption:

- The Relief Date for the Distributed Overlay will be 27 February 2027 (approximately 6 months prior to the NPA 367/418/581 PED of August 2027 identified using the July 2024 R-NRUF results).

See Annex A, Figure 4 for diagram of the Distributed Overlay Relief Option identified by the RPC.

## Distributed Overlay

A Distributed Overlay Relief Option was evaluated which would overlay the NPA 273 over all 258 Exchange Areas comprising the NPA 367/418/581 area.  See Annex A, Figure 5.

The introduction of a Distributed Overlay would keep the same number of NPA Relief Planning areas in Québec.

After this Distributed Overlay, CO Codes in NPA 367/418/581 would be expected to exhaust in Q4 2038.

The average historical growth of 51 CO Codes was used to identify the subsequent PED for this Relief Option by comparing the data in the table below:

| Statistical Method | Data | Period | Quantity of CO Codes |
| --- | --- | --- | --- |
| average | forecast growth | next six years | 168 |
| average | forecast growth | five-year period (Jan 2025 to Jan 2030) | 149 |
| average | historical growth | past five years | 51 |

# SUMMARY OF RELIEF OPTION

| Relief Option | Projected Exhaust Dates |  | Subsequent Relief Dates |
| --- | --- | --- | --- |
|  | NPA 367/418/581 | NPA 273/367/418/581 |  |
| Distributed Overlay | August 2027 | December 2038 | June 2038 |

Note:  Distributed Overlay NPA 273 would be in service on 27 February 2027.

# DIALLING CHANGES FOR LOCAL CALLS

Currently 10-digit dialling is mandatory for local calls originating within area code NPA 367/418/581 and all neighbouring NPAs (i.e., NPA 428/506, 468/819/873 and 709/879).  Local dialling plans will not change with this relief.

# PROPOSED SCHEDULE

The RPC submits the following schedule for NPA 367/418/581 relief based on the recommendations contained in this PD and the current PED of August 2027. The RPC will monitor the PED, and if it changes significantly in the future, the RPC will assess the situation and, if necessary, submit recommendations including a revised schedule to the CRTC for consideration and approval.

The relief implementation schedule details tasks that various parties must perform. In most cases the term Telecom Service Provider (TSP) used in the schedule refers to all telecommunication service providers that operate within the boundaries of the exhausting NPA Complex. Other references to TSP will include a qualifier (i.e., “all”) that indicates that all carriers both nationwide and international are required to perform the task.

RELIEF IMPLEMENTATION SCHEDULE

For a Distributed Overlay of NPA 273 over NPA 367/418/581

| Item | Task or Event | PRIME | START | END |
| --- | --- | --- | --- | --- |
| 1 | CNA identifies NPA exhaust and notifies by e-mail CRTC staff, CSCN, NANPA & CISC that the NPA will exhaust within the future three-year time period | CNA |  | 2025-09-11 |
| 2 | CRTC issues Telecom Notice of Consultation regarding establishment of an ad hoc Relief Planning Committee | CRTC |  | 2025-01-20 |
| 3 | CNA conducts initial R-NRUF and releases results | CNA | 2025-09-11 | 2024-09-11 |
| 4 | RPC Chair starts preparing and submitting RPC Chair Reports to the CISC, on an as required basis. | RPC Chair | 2025-01-20 | 2027-05-27 |
| 5 | CNA develops the PROC | CNA | 2025-09-11 | 2025-01-30 |
| 6 | CNA distributes the PROC to RPC | CNA | 2025-01-30 | 2025-02-13 |
| 7 | RPC participants review PROC & submit contributions to RPC |  | 2025-02-13 | 2025-03-13 |
| 8 | CNA chairs initial RPC conference call to start development of PD, RIP & PL, & schedules future meetings/conference calls including creation & consultation with CATF and NITF | CNA, RPC | 2025-02-25 | 2025-02-25 |
| 9 | CNA distributed revised PD and RIP based upon initial conference call discussions | CNA | 2025-02-26 | 2025-03-12 |
| 10 | CNA chairs subsequent RPC conference calls to finalize PD & RIP | CNA, RPC | 2025-03-12 | 2025-05-12 |
| 13 | Special Types of Telecommunications Service Users (911 PSAPs, alarm companies, ISPs, paging companies, etc.) to identify any concerns to RPC & CRTC | Special Users | 2025-02-25 | 2025-05-27 |
| 11 | CNA forwards the PD and RIP to the CISC and CRTC for approval | CNA | 2025-05-12 | 2025-05-27 |
| 12 | CISC reviews and forwards PD and RIP to the CRTC for approval | CISC | 2025-05-27 | 2025-06-27 |
| 14 | CRTC issues Telecom Decision approving the Relief Method, Relief Date, New NPA & Relief Implementation Plan (RIP) | CRTC | 2025-06-27 | 2025-09-27 |
| 15 | CNA obtains relief NPA from NANPA | CNA | 2025-09-27 | 2025-10-06 |
| 16 | CNA submits the Planning Letter (PL) to NANPA | RPC | 2025-10-06 | 2025-10-14 |
| 17 | Task Forces, TSPs and users implement relief (starts upon CRTC approval of RIP and ends on Relief Date) | TSPs | 2025-09-27 | 2027-02-27 |
| 18 | Telecom Service Providers (TSPs) to develop and file individual consumer awareness programs with the CRTC (may be done collectively by Telecommunications Alliance) (starts upon CRTC approval of RIP and must be completed 9 months prior to the Relief Date) | TSPs | 2025-09-27 | 2026-05-27 |
| 19 | TSPs and/or Telecommunication Alliance issue media release (may start upon CRTC approval of RIP) | CNA | 2026-05-27 | 2026-08-27 |
| 20 | NANPA receives and posts Planning Letter to NANPA website (within 2 weeks of receipt from the CNA) | NANPA | 2025-10-14 | 2025-10-28 |
| 21 | TSPs implement consumer awareness activities (starts upon filing of Consumer Awareness Programs with the CRTC and is completed on the Relief Date) | TSPs | 2026-05-27 | 2027-02-27 |
| 22 | TSPs to notify all customers (including residence, business & special customers) of the new overlay NPA (may start upon the filing of Consumer Awareness Programs with the CRTC) | TSPs | 2026-05-27 | 2026-08-27 |
| 23 | TSPs to submit Progress Report #1 to NITF and CATF (starts after completion date for TSPs to notify their customers and requires 2 weeks) | TSPs | 2026-08-27 | 2026-09-11 |
| 24 | NITF and CATF develop & submit Progress Report #1 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2026-09-11 | 2026-09-25 |
| 25 | RPC submits Progress Report #1 to CISC/CRTC (linked to NITF and CATF reports) | RPC | 2026-10-13 | 2026-10-27 |
| 26 | CNA sends relief implementation information for updating BIRRDS to iconectiv | CNA | 2026-04-20 | 2026-04-27 |
| 27 | iconectiv TRA database updates to add Exchange Areas to new overlay NPA (starts 7 months before Inter-carrier test date and ends 6 months before Inter-carrier test date) | iconectiv TRA | 2026-04-27 | 2026-05-27 |
| 28 | All Telecommunications Service Users (including Special Users 911 PSAPs, alarm companies, ISPs, paging companies, etc.) to implement changes to their telecom equipment & systems to accommodate the new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Telecom Service Users | 2025-09-27 | 2027-02-27 |
| 29 | Payphone Providers Reprogram Payphones (starts upon CRTC approval of RIP and ends on the Relief Date) | Payphone Providers | 2025-09-27 | 2027-02-27 |
| 30 | TSPs and database owners/operators to modify systems and industry databases (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs & Database Owners | 2025-09-27 | 2027-02-27 |
| 31 | Operator Services & Directory Assistance Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2025-09-27 | 2027-02-27 |
| 32 | Directory Publisher Readiness for overlays (ability to identify the NPA in telephone numbers in the directory published after the Overlay NPA is activated) (starts upon CRTC approval of RIP and ends on the Relief Date) | Directory Publishers | 2025-09-27 | 2027-02-27 |
| 33 | 9-1-1 Systems and Databases Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | PSAPS, 9 1 1 Service Providers & TSPs | 2025-09-27 | 2027-02-27 |
| 34 | Network Systems & Equipment Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2025-09-27 | 2027-02-27 |
| 35 | Service Order & Business System Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2025-09-27 | 2027-02-27 |
| 36 | International Gateway Switch Translations Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Int’l TSPs | 2025-09-27 | 2027-02-27 |
| 37 | Canadian Local Number Portability Consortium (CLNPC) Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | CLNPC & NPAC | 2025-09-27 | 2027-02-27 |
| 38 | Toll Free SMS Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Toll TSPs | 2025-09-27 | 2027-02-27 |
| 39 | TSPs apply for Test CO Codes in new NPA (applications may be submitted no more than 6 months and no less than 66 days prior to the start date for the Inter-Carrier Testing Period) (Section 7.16.4 Canadian RP GL) | TSPs | 2026-05-27 | 2026-09-22 |
| 40 | Develop Inter-Carrier Network Test Plans and prepare for testing (individual TSPs to make arrangements in accordance with interconnection agreements) (may start upon CRTC approval of RIP and must be completed by start date for the Inter-Carrier Testing Period) | NITF & TSPs | 2025-09-27 | 2026-11-27 |
| 41 | All international and domestic Telecommunications Service Providers (TSPs) must activate the new NPA in their networks by the start date for the Inter-Carrier Testing Period | TSPs | 2025-09-27 | 2026-11-27 |
| 42 | Activation date for Overlay NPA Test CO Codes and Test Numbers in network (should be completed by the start date for the Inter-Carrier Testing Period) | TSPs |  | 2026-11-27 |
| 43 | Inter-Carrier Testing Period (subject to Inter-Carrier Network Test Plans) (starts about 3 months prior to the Relief Date, and ends about 1 month after the Relief Date) | NITF & TSPs | 2026-11-27 | 2027-03-27 |
| 44 | TSPs to submit Progress Report #2 to NITF (starts on commencement of Inter-Carrier Testing Period) | TSPs | 2026-11-27 | 2026-12-11 |
| 45 | NITF develop & submit Progress Report #2 to RPC (linked to TSP reports to NITF) | NITF | 2026-12-11 | 2026-12-28 |
| 46 | RPC submits Progress Report #2 to CRTC staff (linked to NITF report) | RPC | 2026-12-28 | 2027-01-12 |
| 47 | Relief Date (earliest date when CO Codes in new NPA may be activated) |  |  | 2027-02-27 |
| 48 | TSPs submit Final Report to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs | 2027-02-27 | 2027-03-12 |
| 49 | NITF and CATF develop & submit Final Progress Report to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2027-03-12 | 2027-03-30 |
| 50 | The RPC submits Final Progress Report to CRTC staff (linked to NITF and CATF reports) | RPC | 2027-03-30 | 2027-04-13 |
| 51 | TSPs disconnect Test Codes & Numbers, and submit Part 1 form to return Test Codes (starts 1 month after Relief Date and allows 1 month for completion) | TSPs | 2027-03-27 | 2027-04-27 |
| 52 | RPC Chair submits, to the CISC, the final RPC Chair report indicating that the ad hoc RPC is no longer required | RPC Chair | 2027-04-27 | 2027-05-27 |

# JEOPARDY CONTINGENCY PLAN (JCP)

The RPC has developed the following JCP for inclusion in the PD for NPA 367/418/581. This JCP is based on the example contained in Appendix F to the Canadian NPA Relief Planning Guideline.

This JCP shall remain in effect until superseded by a CRTC-approved JCP, the Jeopardy Condition is suspended or 66 days prior to the Relief Date.

The following measures shall be implemented in NPA 367/418/581 while a Jeopardy Condition is in effect.

During a Jeopardy Condition, CO Code Applicants shall submit all CO Code applications and related correspondence for the Jeopardy NPA to CRTC staff in addition to the CNA.  The CNA shall only assign CO Codes from the exhausting NPA to a CO Code Applicant when instructed by CRTC staff.

- Carriers and/or Telecommunications Service Providers (TSPs):

  - shall age disconnected residential wireline telephone numbers for a maximum of two months;

  - shall age disconnected wireless telephone numbers for a maximum of three months;

  - shall age disconnected business wireline telephone numbers for a maximum of six months. Under special circumstances, the six month aging limit for business telephone numbers may be extended to twelve months, if required, to accommodate local directory publishing dates for high volume call-in applications (e.g., heavily advertised local business numbers such as radio talk shows, food ordering services, ticket sales, chat lines), or for numbers associated with public service emergency applications or for numbers advertised in directories for which customers have requested reference of calls;

  - shall return all CO Codes that are not being used, nor intended to be used to directly serve customers to the assignment pool within two months (e.g., plant test codes);

  - should work towards, and encourage existing customers, to either activate or return the reserved numbers to bring the reserved quantity down to a maximum of 10% of the quantity of numbers In-Service for that customer;

  - shall not allow the quantity of reserved numbers to be increased by new reservation requests by existing customers to more than 10% of the quantity of numbers in service for that customer. In the case of new customers, number reservations shall be limited to 10% of the total quantity of telephone numbers being placed into service for that customer;

  - shall, within 45 days from the date that the CNA declares a Jeopardy Condition submit a Part 1 Form for each remaining reserved CO Code either returning the reserved CO Code to the CNA or requesting assignment of the reserved CO Code. Once the 45-day period has elapsed, the CNA shall make available for general assignment all CO Codes that are still reserved and have not been applied for as assignments on a Part 1 Form received by the CNA. Within 60 days from the date that the CNA declares a Jeopardy Condition, the CNA shall report to CRTC staff and the RPC as to how many of these codes have been assigned or made available for general assignment;

  - shall not be permitted to obtain a new CO Code reservation;

  - shall place all CO Codes assigned prior to the Jeopardy Condition being declared In-Service within three months of the effective date for CO Code activation in the network, or within three months of the date that the Jeopardy Condition was declared. If the CO Code is an Initial Code and the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-Service date has been delayed beyond the applicable timeframe, then the CNA may grant an extension of up to two months to the In-Service date. The CNA shall initiate reclamation procedures for all CO Codes that have not been placed In-Service within these timeframes unless CRTC staff provides a further extension.

- For new applications for Initial Codes, each CO Code Holder shall certify that the CO Code will be activated in the network and placed In-Service within four months of the date of application for the Code. If the CNA does not receive a Part 4 Form within this timeframe, confirming that the CO Code has been placed In-Service, the CNA will initiate reclamation measures. If the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-Service date has been delayed not more than six months from the original application date, then the CNA may grant an extension to the In-Service date, so long as the In-Service date is not more than six months beyond the original application date. If the In-Service date has been delayed more than six months from the original application date, then the CNA shall reclaim the Code unless CRTC staff provides a further extension.

- When applying for an Additional Code for Growth, a CO Code Holder who is submitting a Part 1 Form and Appendix B worksheet shall also submit a completed Supplementary Form for a Growth CO Code Application (attached) which certifies and/or provides the following information for the specific switching entity/POI and Exchange Area when the Growth CO Code is being requested in a Jeopardy Condition:

  - certification that all held telephone numbers have been released;

  - certification that reserved numbers do not exceed ten percent of the total quantity of numbers as defined in Appendix G of the Canadian CO Code (NXX) Assignment Guideline;

  - certification that each reseller/dealer had been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two times the highest quantity of customer numbers assigned in any month during the previous 12 months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three months' inventory;

  - confirmation that the Part 1 form submitted with the application has the Jeopardy Condition box in section 1.6 checked to certify that the existing CO Codes are projected to exhaust within 4 months of the date of application and that the months-to-exhaust is documented on an Appendix B submitted to the CNA;

  - a completed Telephone Number Utilization Report for the applicable switching entity signed by both a company officer and the company’s authorized representative;

  - confirmation that the requested Growth CO Code was forecasted in the most recent NRUF or an explanation as to why it was not is attached; and,

  - confirmation that the requested Growth CO Code will be placed In-Service within four months of the date of assignment.

- Any CO Codes for growth assigned after the implementation of this JCP must be activated in the network and placed In-Service within four months of assignment. In the event that a CO Code Holder is unable to place the CO Code In-Service within four months of the date of assignment, the CO Code Holder must return the assigned CO Codes or submit a written request for extension to the CNA. Such written requests must include documentation explaining the reason(s) for the missed date and proposing the new In-Service date. If the explanation includes reasons beyond the control of the CO Code Holder, the CNA may extend the In-Service date a maximum of one month. If the CO Code Holder does not place the CO Code In-Service within the one-month extension, the CNA shall initiate the reclamation process at the end of the one-month extension unless CRTC staff provides a further extension.

- A Carrier that has multiple switching entities within an Exchange Area shall examine the possibility of, and implement where feasible, number sharing between those switches as a potential method to delay requirements for additional CO Codes.

- The CNA will request two versions (two separate worksheets (Form 1 and Form 2)) of the J-NRUF input from all current and prospective CO Code Holders quarterly until three (3) months before relief is provided.

  - The forecast quantities in Form 1 should be the same as or lower than the last R-NRUF input submitted, prior to declaration of a Jeopardy Condition. CO Code Holder forecasts may reflect an increase in demand in the period subsequent to the Relief Date.

  - Form 2 will reflect the actual demand required by the CO Code Holder's current business plan and will be provided for information purposes only.

- The CNA will compare the initial J-NRUF input to the recent NRUF inputs, to assess forecasting trends. The CNA shall monitor all inputs and shall test them for reasonableness in consultation with the Carrier. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the deviations, then the matter will be referred to the CRTC staff.

- The CNA will request subsequent J-NRUF input from all current and prospective CO Code Holders quarterly until 3 months before relief is provided. If one or more R-NRUFs have already been conducted, and depending on the severity of the Jeopardy Condition, the CNA may defer a J-NRUF by up to two months if such a deferral brings the timing of that J-NRUF and subsequent J-NRUFs into alignment with other NRUFs that are conducted at 12, 6 or 3 month intervals. Subsequent J-NRUF input will be compared with the initial J-NRUF input to evaluate the effectiveness of the JCP. The CNA shall monitor all J-NRUF inputs and shall test them for reasonableness in consultation with the Telecommunications Service Providers. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the changed forecasts, then the matter will be referred to CRTC staff.

- A CO Code Applicant must have submitted a completed J-NRUF to the CNA before the CNA may assign a CO Code to that CO Code Applicant.

- If a CO Code applicant wishes to request more CO Codes than it identified in its most recent J NRUF, the CO Code Applicant should discuss the matter with the CNA. If the CO Code Applicant wishes to proceed with the request, the CO Code Applicant will forward the request and revised forecast to CRTC staff and the CNA for consideration.

- The CO Codes identified in the NPA CO Code Inventory Chart as “Assignable CO Codes in a Jeopardy Condition” will be assigned in the order determined by the RPC after all CO Codes which are “Available for Assignment as of [day month year] have been assigned.

- After each J-NRUF, the CNA shall provide CRTC staff, the RPC and CSCN participants with a report providing an updated NPA CO Code Inventory Chart for the NPA in jeopardy as well as the aggregate results of the most recent J-NRUF.

- Exceptional issues or concerns may be referred by the CNA, or by individual entities (with a courtesy copy to the CNA), to the CRTC staff for resolution.

- In a situation where the Relief Date is on or after the PED, the quantity of CO Codes that may be assigned to a CO Code Applicant prior to the end of the Jeopardy Condition (i.e. 66 days prior to the Relief Date) shall be limited to the quantity forecasted by the CO Code Applicant in its most recent NRUF forecast submitted prior to the Jeopardy Condition being declared by the CNA (if no previous NRUF was submitted, then the previous forecast will be deemed to be zero codes). When making requests to obtain CO Codes prior to the end of the Jeopardy Condition (i.e. 66 days prior to the Relief Date), the CO Code Applicant may change the Exchange Area or the month when the CO Code assignment is required, provided a new J-NRUF and explanation accompanies the application. The control imposed by this option may be relaxed if subsequent J-NRUFs defer the PED to after the Relief Date. CO Codes that become available for assignment due to future reduced demand from other current and prospective CO Code Holders may be assigned at the discretion of CRTC staff.

- If the CNA determines that the implementation of the JCP has not extended the Projected Exhaust Date of the NPA beyond the Relief Date, the CNA will consult with CRTC staff and further CO Code conservation and assignment procedures may be ordered by the Commission (e.g., rationing, lottery, etc.).

Supplementary form for a Growth CO Code Application – Page 1 of 2 – Telephone Number Utilization Report

This form is required with each request for an Additional Code for Growth in an NPA where a Jeopardy Condition is in effect. It should be submitted to the CNA together with the Part 1 and Appendix B forms that are required for an application for an Additional Code for Growth. See the Part 1 form for information on how and where to submit the form.

I hereby certify that the following information is true and accurate to the best of my knowledge and has been prepared in accordance with Special Conservation Procedures for a Jeopardy Condition contained in the Canadian NPA Relief Planning Guideline or the applicable approved Jeopardy Contingency Plan.

Name & Signature of Authorized Representative of Code Holder	Title	Date

Name & Signature of Company Officer (see item 3 of this JCP)	Title	Date

Contact information:	Entity Name: 	__________________	Contact Name:	_____________

Address: 	__________________	City, Province, Postal Code:	_____________

Telephone: 	__________________	Facsimile:	_____________

E-mail: 	__________________

Switch Identification (Switching Entity/POI) CLLI: _______________ 	Exchange Area: ________________

For the above Switch Identification and Exchange Area for which a Growth CO Code is requested:

I certify that all held telephone numbers have been released

I certify the total quantity of reserved numbers does not exceed ten percent (10%) of the total quantity of telephone numbers as defined in Appendix G of the Canadian CO Code (NXX) Assignment Guideline

I certify that each reseller/dealer has been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two (2) times the highest quantity of customer numbers assigned in any month during the previous twelve (12) months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three months' inventory.

The Part 1 form submitted with the application has the Jeopardy Condition box in section 6 checked (this certifies that the existing CO Codes are projected to exhaust within four (4) months of the date of the application or within the period specified in an approved Jeopardy Contingency Plan, and that the months-to-exhaust is documented on an Appendix B submitted to the CNA).

The Telephone Number Utilization Report on page 2 of this form has been completed.

The requested Growth CO Code was forecasted in the most recent NRUF, or an explanation as to why it was not is attached.

The requested Growth CO Code will be placed In-Service within four (4) months of the date of assignment.

Supplementary Form for a Growth CO Code Application – Page 2 of 2 – Telephone Number Utilization Report

Use Arial 9 to complete this form. (Note: If the spreadsheet below does not show on your display, please change the Work view to "Print Layout" or "Reading Layout")

Remarks: _______________________________________________________________________________

________________________________________________________________________________________

NPA 367/418/581 CO Code Inventory Chart

The following chart and the instructions it contains will apply in NPA 367/418/581 in a Jeopardy Condition.

The chart below lists quantities of CO Codes unassignable prior to a Jeopardy Condition, CO Codes that become assignable in a Jeopardy Condition and CO Codes in NPA 367/418/581 assigned and In-service as of 30 January 2025. The CO Codes that become assignable in a Jeopardy Condition shall only be made available for assignment when all other available CO Codes have been assigned in the order listed below.

|  |  | Quantity |
| --- | --- | --- |
| A | Total CO Codes in NPAs 367/418/581 (NXX format) | 2400 |
| B | CO Codes unassignable prior to a Jeopardy Condition |  |
|  | N11 Service Codes (211, 311, 411, 511, 611, 711, 811, 911) | 24 |
|  | Special Use Codes (555, 950, 976 & 988) | 10 |
|  | Home NPA Code(s) (367, 418, 581) | 9 |
|  | Current Neighbouring NPA Codes | 0 |
|  | Future Geographic NPA Codes | 9 |
|  | Plant Test Codes (958 & 959) | 6 |
|  | Special 7-digit Dialling Codes (310, 610 & 810) | 8 |
|  | Total B | 66 |
| C | CO Codes assignable prior to a Jeopardy Condition (C=A-B) | 2334 |
| D | CO Codes unassignable prior to a Jeopardy Condition that become assignable in a Jeopardy Condition: |  |
|  | Future Canadian Geographic NPA Codes | 9 |
|  | Current Neighbouring NPA Codes | 0 |
|  | Total D | 9 |
| E | Assignable CO Codes in a Jeopardy Condition (E=C+D) | 2343 |
| F | Assigned CO Codes as of 30 January 2025 | 1699 |
| G | Net CO Codes available for assignment as of 30 January 2025 without a Jeopardy Condition (G=C-F) | 635 |
| H | Net CO Codes available for assignment as of 30 January 2025 in a Jeopardy Condition (H=E-F) | 644 |

Notes:

- In CNRE137B, the CSCN recommend the NPA 273 be set aside for future relief in NPA 367/418/581.

# SELECTION OF RELIEF NPA CODE

In TIF Report CNRE137B, submitted to CRTC staff on 30 October 2023, the CSCN recommended that area code 273 be set aside for the future relief of NPA 367/418/581.

# RECOMMENDATIONS

The RPC recommends:

- The Relief Method should be a Distributed Overlay of a new NPA Code on NPA 367/418/581 in Québec;

- The Relief NPA Code for NPA 367/418/581 should be NPA 273 as per the CNRE137B submitted by the CSCN to the CRTC on 30 October 2023 and

- The Relief Date should be 27 February 2027 to provide Carriers and customers with advanced notification and sufficient lead-time to implement relief in NPA 367/418/581.

ANNEXES

Planning Document (PD)

Numbering Plan Area (NPA) 367/418/581

- MAPS AND FIGURES

Figure 1 – Overview Map of NPA 367/418/581

Figure 2 – NPA 367/418/581 Actual and Forecast CO Code Assignments

Figure 3 – NPA 367/418/581 CO Code Exhaust – July 2024 R-NRUF

Figure 4 –  Distributed Overlay

- NPA 367/418/581 EXCHANGE AREAS

Exchange Area

Aguanish

Albanel

Alma

Amqui

Anse-St-Jean

Armagh

Baie-Comeau

Baie-Comeau (Hauterive)

Baie-des-Sables

Baie-Johan-Beetz

Baie-St-Paul

Baie-Ste-Catherine

Baie-Trinite

Barachois

Batiscan

Beauceville

Bergeronnes

Bic

Biencourt

Black Lake

Blanc-Sablon

Boischatel

Bonaventure

Bonne-Esperance

Cabano

Cap-aux-Meules

Cap-Chat

Cap-des-Rosiers

Cap-Saint-Ignace

Caplan

Carleton

Causapscal

Chambord

Chandler

Chapais

Charny

Chateau-Richer

Chevery

Chibougamau

Chicoutimi

Chute-aux-Outardes

Chute-des-Passes

Clarke City

Clermont

Cloridorme

Colombier

Courcelles

Delisle

Desbiens

Disraeli

Dolbeau

Donnacona

East Broughton

Esprit-Saint

Ferland

Fermont

Forestville

Frampton

Garthby

Gaspe

Girardville

Godbout

Grande-Entree

Grande-Riviere

Grande-Vallee

Harrington Harbour

Havre-Aubert

Havre-aux-Maisons

Havre-Saint-Pierre

Hebertville

Hebertville-Station

Ile-aux-Coudres

Inverness

Jonquiere

L'Ile-Verte

L'Islet

La Baie (Chicoutimi Co.)

La Dore

La Guadeloupe

La Malbaie

La Martre

La Pocatiere

La Romaine

Lac Bouchette

Lac-au-Saumon

Lac-aux-Sables

Lac-Etchemin

Lac-Frontiere

Lambton

Laterriere

Leeds

Les Boules

Les Eboulements

Les Escoumins

Les Mechins

Levis

Loretteville

Luceville

Manicouagan 5

Maria

Matane

Matapedia

Metabetchouan

Milot

Mistissini

Moisie

Mont-Joli

Mont-Louis

Montmagny

Murdochville

Mutton Bay

Natashquan

Neuville

New Carlisle

New Richmond

Newport

Normandin

Notre-Dame-des-Laurentides

Notre-Dame-du-Lac

Nouvelle

Parc-des-Laurentides

Pentecote

Perce

Peribonka

Petite-Riviere-St-Francois

Pointe-a-la-Croix

Pont-Rouge

Port-Cartier

Port-Daniel

Port-Menier

Portneuf

Quebec

Rimouski

Riviere-a-Pierre

Riviere-au-Renard

Riviere-au-Tonnerre

Riviere-Bleue

Riviere-du-Loup

Riviere-Saint-Jean

Roberval

Sacre-Coeur

Saint-Adelphe

Saint-Agapit

Saint-Alexis-de-Matapedia

Saint-Anselme

Saint-Antoine-de-Tilly

Saint-Apollinaire

Saint-Augustin

Saint-Augustin (Duplessis)

Saint-Basile

Saint-Bernard-de-Dorchester

Saint-Camille

Saint-Casimir

Saint-Charles

Saint-Come

Saint-Damien-de-Buckland

Saint-Edouard-de-Lotbiniere

Saint-Fabien

Saint-Fabien-de-Panet

Saint-Flavien

Saint-Francois

Saint-Gabriel

Saint-Gedeon-de-Beauce

Saint-Georges-de-Beauce

Saint-Henri-de-Levis

Saint-Jean-Port-Joli

Saint-Joseph-de-Beauce

Saint-Lambert-de-Lauzon

Saint-Leon-le-Grand

Saint-Luc

Saint-Magloire

Saint-Malachie

Saint-Marc-des-Carrieres

Saint-Martin

Saint-Michel

Saint-Moise

Saint-Odilon

Saint-Pamphile

Saint-Patrice-de-Beaurivage

Saint-Paul-de-Montminy

Saint-Prosper-de-Dorchester

Saint-Raphael

Saint-Raymond

Saint-Rene-de-Matane

Saint-Roch-des-Aulnaies

Saint-Simon-de-Rimouski

Saint-Stanislas

Saint-Theophile

Saint-Tite

Saint-Ubalde

Saint-Ulric

Saint-Zacharie

Sainte-Agathe-de-Lotbiniere

Sainte-Anne-de-la-Perade

Sainte-Anne-des-Monts

Sainte-Blandine

Sainte-Claire

Sainte-Croix

Sainte-Felicite

Sainte-Henedine

Sainte-Justine

Sainte-Lucie

Sainte-Marie-de-Beauce

Sainte-Perpetue

Sainte-Rose

Sainte-Thecle

Sault-au-Mouton

Sayabec

Schefferville

Sept-Iles

Squatec

St-Alexandre

St-Ambroise-de-Chicoutimi

St-Andre

St-Eleuthere

St-Ephrem-de-Beauce

St-Felicien

St-Ferdinand-D'Halifax

St-Fereol

St-Fidele

St-Fulgence

St-Gedeon

St-Hilarion

St-Honore

St-Honore (Chicoutimi Co.)

St-Honore (Temiscouata Co.)

St-Irenee

St-Jean-de-Dieu

St-Jean-ile-d'Orleans

St-Just-de-Bretenieres

St-Methode-de-Frontenac

St-Nicolas

St-Pacome

St-Pascal

St-Philippe-de-Neri

St-Prime

St-Simeon

St-Tite-des-Caps

St-Urbain

St-Victor-de-Beauce

Ste-Anne-de-Beaupre

Ste-Anne-de-Portneuf

Ste-Brigitte-de-Laval

Ste-Catherine

Ste-Petronille

Ste-Rose-du-Nord

Stoneham

Stratford

Tadoussac

Tete-a-la-Baleine

Thetford Mines

Tring Jonction

Trois-Pistoles

Val-Alain

Val-Brillant

Valcartier

Vallee-Jonction

Ville Degelis