## ReadMe
Appendix B - Canadian NPA Relief Planning Timeline
NPA Relief Activities can be viewed as consisting of 3 phases:
1 | R-NRUF and PROC or IPD Phase – The Canadian Numbering Administration (CNA) conducts the initial Relief Planning Numbering Resource Utilization Forecast (R NRUF) and develops the Proposal for Relief of an Overlay Complex (PROC) or an Initial Planning Document (IPD).
2 | PD, RIP and CRTC Decision Phase – The Relief Planning Committee (RPC) develops the Planning Document (PD) and Relief Implementation Plan (RIP) and submits them to the CRTC for approval (i.e., proposed Relief Option, proposed relief NPA, and Relief Date), and the CRTC issues a Decision.
3 | Relief Implementation Phase – The Relief Planning Committee (RPC), Telecommunications Service Providers (TSPs) and users implement relief in accordance with the Relief Implementation Plan.
Tips:
To add additional years to the "Holidays" sheet, select the entire preceding year of dates (from the year header to Boxing Day) and paste it below. The year should calculate from the preceding year header and all the dates will calculate based on the new year header.

## 10-Digit Relief Template
| Highlight means that the date is in either Jan or Dec |  |  | CRTC Decision | 2027-02-06
| Highlight is a field that needs to be filled in manually (yyyy-mm-dd) |  |  | Relief Date | 2028-08-05
Highlight means you should have a look at the overall period
Item | Task or Event | PRIME | START | END | NOTES | # of Weeks for item
1 | CNA identifies NPA exhaust and notifies by email CRTC staff, CSCN, NANPA & CISC that the NPA will exhaust within the future three-year time period | CNA |  | 2026-03-25 | End: Publication date of first NRUF with NPA in Relief Planning window
2 | CRTC issues Telecom Notice of Consultation regarding establishment of an ad hoc Relief Planning Committee | CRTC |  | 2026-05-14 | End: Publication date of NoC
3 | CNA conducts initial R-NRUF and releases results | CNA | 2026-03-25 | 2026-09-30 | Start: Date CNA published NRUF showing pending exhaust End: Publication date of initial R-NRUF results | 27
4 | RPC Chair starts preparing and submitting RPC Chair Reports to the CISC, on an as required basis. | RPC Chair | 2026-05-14 | 2028-11-05 | Start: Date of NoC End: End date of RPC last chair report to CISC | 129.4
5 | CNA develops the PROC | CNA | 2026-03-25 | 2026-05-22 | Start: Date CNA published NRUF showing pending exhaust End: Date of PROC publication | 8.3 | FLAG
6 | CNA distributes the PROC to RPC | CNA | 2026-05-22 | 2026-05-29 | Start: End of CNA develops PROC End: End of CNA develops PROC | 1
7 | RPC participants review PROC & submit contributions to RPC | RPC | 2026-05-29 | 2026-06-29 | Start: PROC publication date End: 1 month | 4.4
8 | CNA chairs initial RPC conference call to start development of PD, RIP & PL, & schedules future meetings/conference calls including creation & consultation with CATF and NITF | CNA, RPC | 2026-06-29 | 2026-07-07 | Start: End of RPC participants review PROC End: 1 week | 1.1
9 | CNA distributed revised PD and RIP based upon initial conference call discussions | CNA | 2026-07-07 | 2026-07-21 | Start: End of initial RPC conference call End: 2 weeks | 2
10 | CNA chairs subsequent RPC conference calls to finalize PD & RIP | CNA, RPC | 2026-07-21 | 2026-09-21 | Start: End of CNA distributed revised PD & RIP End: 2 months | 8.9
13 | Special Types of Telecommunications Service Users (911 PSAPs, alarm companies, ISPs, paging companies, etc.) to identify any concerns to RPC & CRTC | Special Users | 2026-07-07 | 2026-10-06 | Start: End of initial RPC meeting End: CNA forwards the PD and RIP | 13
11 | CNA forwards the PD and RIP to the CISC and CRTC for approval | CNA | 2026-09-21 | 2026-10-06 | Start: End of CNA chairs subsequent conference calls End: 2 weeks | 2.1
12 | CISC reviews and forwards PD and RIP to the CRTC for approval | CISC | 2026-10-06 | 2026-11-06 | Start: End of CNA forwards the PD and RIP End: 1 month | 4.4
14 | CRTC issues Telecom Decision approving the Relief Method, Relief Date, New NPA & Relief Implementation Plan (RIP) | CRTC | 2026-11-06 | 2027-02-06 | Start: End of CISC reviews and forwards PD and RIP End: 3 months | 13.1
15 | CNA obtains relief NPA from NANPA | CNA | 2027-02-06 | 2027-02-12 | Start: End of CRTC issues Telecom Decision End: 1 week | 0.9
16 | CNA submits the Planning Letter (PL) to NANPA | RPC | 2027-02-12 | 2027-02-22 | Start: End of CNA obtains relief NPA End: 1 week | 1.4
17 | Task Forces, TSPs and users implement relief (starts upon CRTC approval of RIP and ends on Relief Date) | TSPs | 2027-02-06 | 2028-08-05 | Start: End of CRTC issues Telecom Decision End: Relief Date | 78
18 | All Telecom Service Providers (TSPs) to develop and file individual consumer awareness programs with the CRTC (may be done collectively by Telecommunications Alliance) (starts upon CRTC approval of RIP and must be completed 9 months prior to the Relief Date) | TSPs | 2027-02-06 | 2027-11-05 | Start: End of CRTC issues Telecom Decision End: 9 months before Relief Date | 38.9 | FLAG
19 | TSPs and/or Telecommunication Alliance issue media release (may start upon CRTC approval of RIP) | CNA | 2027-02-06 | 2027-02-12 | Start: End of CRTC issues Telecom Decision End: 1 week | 0.9 | FLAG
20 | NANPA receives and posts Planning Letter to NANPA website (within 2 weeks of receipt from the CNA) | NANPA | 2027-02-22 | 2027-03-08 | Start: End of CNA submits the Planning Letter End: 2 weeks | 2
21 | All TSPs implement consumer awareness activities (starts upon filing of Consumer Awareness Programs with the CRTC and is completed on the Relief Date) | TSPs | 2027-11-05 | 2028-08-05 | Start: End of TSPs filing Consumer Awareness Program End: Relief Date | 39.1
22 | All TSPs to notify all customers (including residence, business & special customers) of the new overlay NPA (may start upon the filing of Consumer Awareness Programs with the CRTC) | TSPs | 2027-11-05 | 2028-02-05 | Start: End of TSPs filing Consumer Awareness Program End: 6 months before Relief Date | 13.1 | FLAG
23 | TSPs to submit Progress Report #1 to NITF and CATF (starts after completion date for all TSPs to notify their customers and requires 2 weeks) | TSPs | 2028-02-05 | 2028-02-18 | Start: End of TSPs to notify all customers End: 2 weeks | 1.9
24 | NITF and CATF develop & submit Progress Report #1 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2028-02-18 | 2028-03-06 | Start: End of TSPs to submit Progress Report to TFs End: 2 weeks | 2.4
25 | RPC submits Progress Report #1 to CISC/CRTC (linked to NITF and CATF reports) | RPC | 2028-03-20 | 2028-04-03 | Start: End of TFs to submit Progress Report to RPC End: 2 weeks | 2
26 | CNA sends relief implementation information for updating BIRRDS to iconectiv | CNA | 2027-09-28 | 2027-10-05 | Start: 1 week before start of inconectiv TRA database updates End: Start of iconectiv TRA database updates | 1 | FLAG
27 | iconectiv TRA database updates to add Exchange Areas to new overlay NPA (starts 7 months before Inter-carrier test date and ends 6 months before Inter-carrier test date) | iconectiv TRA | 2027-10-05 | 2027-11-05 | Start: End of NANPA receives and posts Planning Letter End: 6 months before start of intercarrier testing | 4.4
28 | All Telecommunications Service Users (including Special Users 911 PSAPs, alarm companies, ISPs, paging companies, etc.) to implement changes to their telecom equipment & systems to accommodate the new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Telecom Service Users | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
29 | Payphone Providers Reprogram Payphones (starts upon CRTC approval of RIP and ends on the Relief Date) | Payphone Providers | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
30 | TSPs and database owners/operators to modify systems and industry databases (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs & Database Owners | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
31 | Operator Services & Directory Assistance Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
32 | Directory Publisher Readiness for overlays (ability to identify the NPA in telephone numbers in the directory published after the Overlay NPA is activated) (starts upon CRTC approval of RIP and ends on the Relief Date) | Directory Publishers | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
33 | 9-1-1 Systems and Databases Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | PSAPS, 9 1 1 Service Providers & TSPs | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
34 | Network Systems & Equipment Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
35 | Service Order & Business System Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
36 | International Gateway Switch Translations Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Int’l TSPs | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
37 | Canadian Local Number Portability Consortium (CLNPC) Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | CLNPC & NPAC | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
38 | Toll Free SMS Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Toll TSPs | 2027-02-06 | 2028-08-05 | Start: End of CRTC Decision End: Relief Date | 78
39 | TSPs apply for Test CO Codes in new NPA (applications may be submitted no more than 6 months and no less than 66 days prior to the start date for the Inter-Carrier Testing Period) (Section 7.16.4 Canadian RP GL) | TSPs | 2027-11-05 | 2028-02-29 | Start: 6 months before start of Inter-Carrier testing End: 66 days before the start of Inter-Carrier testing | 16.6 | FLAG
40 | Develop Inter-Carrier Network Test Plans and prepare for testing (individual TSPs to make arrangements in accordance with interconnection agreements) (may start upon CRTC approval of RIP and must be completed by start date for the Inter-Carrier Testing Period) | NITF & TSPs | 2027-02-06 | 2028-05-05 | Start: End of CRTC Decision End: Start of Inter-Carrier testing | 64.9
41 | All international and domestic Telecommunications Service Providers (TSPs) must activate the new NPA in their networks by the start date for the Inter-Carrier Testing Period | TSPs | 2027-02-06 | 2028-05-05 | Start: End of CRTC Decision End: Start of Inter-Carrier testing | 64.9
42 | Activation date for Overlay NPA Test CO Codes and Test Numbers in network (should be completed by the start date for the Inter-Carrier Testing Period) | TSPs |  | 2028-05-05 | End: 3 months before Relief Date
43 | Inter-Carrier Testing Period (subject to Inter-Carrier Network Test Plans) (starts about 3 months prior to the Relief Date, and ends about 1 month after the Relief Date) | NITF & TSPs | 2028-05-05 | 2028-09-05 | Start: 3 months before Relief Date End: 1 month after Relief Date | 17.6
44 | TSPs to submit Progress Report #2 to NITF and CATF (starts on commencement of Inter-Carrier Testing Period) | TSPs | 2028-05-05 | 2028-05-19 | Start: Start of Inter-Carrier testing End: 2 weeks | 2 | FLAG
45 | NITF and CATF develop & submit Progress Report #2 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2028-05-19 | 2028-06-05 | Start: End of TSPs to submit Progress Report #2 End: 2 weeks | 2.4
46 | RPC submits Progress Report #2 to CRTC staff (linked to NITF and CATF reports) | RPC | 2028-06-05 | 2028-06-19 | Start: End of NITF and CATF deveop & submit Progress Report #2 End: 2 weeks | 2
47 | Relief Date (earliest date when CO Codes in new NPA may be activated) |  |  | 2028-08-05 | End: Relief date (approximately 6 months before PED)
48 | TSPs submit Final Report to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs | 2028-08-05 | 2028-08-21 | Start: Relief Date End: 2 weeks | 2.3
49 | NITF and CATF develop & submit Final Progress Report to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2028-08-21 | 2028-09-05 | Start: TSPs submit Final Report End: 2 weeks | 2.1
50 | The RPC submits Final Progress Report to CRTC staff (linked to NITF and CATF reports) | RPC | 2028-09-05 | 2028-09-19 | Start: NITF & CATF develop & submit Final Progress Report End: 2 weeks | 2
51 | TSPs disconnect Test Codes & Numbers, and submit Part 1 form to return Test Codes (starts 1 month after Relief Date and allows 1 month for completion) | TSPs | 2028-09-05 | 2028-10-05 | Start: 1 month after Relief Date End: 1 month | 4.3
52 | RPC Chair submits, to the CISC, the final RPC Chair report indicating that the ad hoc RPC is no longer required | RPC Chair | 2028-10-05 | 2028-11-05 | Start: End of TSPs disconnect Test Codes End: 1 month | 4.4
Formulas:
START = [END, row above]
START = IF(ISERROR(WORKDAY([END, row above],10,Holidays!$B2:B310)),"needs Relief Date",WORKDAY([END, row above],10,Holidays!$B2:B310))
END = WORKDAY([START],5,Holidays!$B2:B310)
END = EDATE([START],1)

## Holidays
2016
2016-01-01 | 2016-01-01 | New Years's Day
2016-02-15 | 2016-02-15 | Family Day
2016-03-25 | 2016-03-25 | Good Friday
2016-03-28 | 2016-03-28 | Easter Monday
2016-05-23 | 2016-05-23 | Victoria Day
2016-06-24 | 2016-06-24 | St Jean Baptiste Day
2016-01-01 | 2016-01-01 | Canada Day
2016-08-01 | 2016-08-01 | Civic Holiday
2016-09-05 | 2016-09-05 | Labour Day
2016-10-10 | 2016-10-10 | Thanksgiving
2016-11-11 | 2016-11-11 | Remember Day
2016-12-26 | 2016-12-26 | Christmas Day
2016-12-27 | 2016-12-27 | Boxing Day
2017
2017-01-02 | 2017-01-02 | New Years's Day
2017-02-20 | 2017-02-20 | Family Day
2017-04-14 | 2017-04-14 | Good Friday
2017-04-17 | 2017-04-17 | Easter Monday
2017-05-22 | 2017-05-22 | Victoria Day
2017-06-23 | 2017-06-23 | St Jean Baptiste Day
2017-07-03 | 2017-07-03 | Canada Day
2017-08-07 | 2017-08-07 | Civic Holiday
2017-09-04 | 2017-09-04 | Labour Day
2017-10-09 | 2017-10-09 | Thanksgiving
2017-11-13 | 2017-11-13 | Remember Day
2017-12-25 | 2017-12-25 | Christmas Day
2017-12-26 | 2017-12-26 | Boxing Day
2018
2018-01-01 | 2018-01-01 | New Years's Day
2018-02-19 | 2018-02-19 | Family Day
2018-03-30 | 2018-03-30 | Good Friday
2018-04-02 | 2018-04-02 | Easter Monday
2018-05-21 | 2018-05-21 | Victoria Day
2018-06-22 | 2018-06-22 | St Jean Baptiste Day
2018-07-02 | 2018-07-02 | Canada Day
2018-08-06 | 2018-08-06 | Civic Holiday
2018-09-03 | 2018-09-03 | Labour Day
2018-10-08 | 2018-10-08 | Thanksgiving
2018-11-12 | 2018-11-12 | Remember Day
2018-12-25 | 2018-12-25 | Christmas Day
2018-12-26 | 2018-12-26 | Boxing Day
2019
2019-01-01 | 2019-01-01 | New Years's Day
2019-02-18 | 2019-02-18 | Family Day
2019-04-19 | 2019-04-19 | Good Friday
2019-04-22 | 2019-04-22 | Easter Monday
2019-05-20 | 2019-05-20 | Victoria Day
2019-06-24 | 2019-06-24 | St Jean Baptiste Day
2019-07-01 | 2019-07-01 | Canada Day
2019-08-05 | 2019-08-05 | Civic Holiday
2019-09-02 | 2019-09-02 | Labour Day
2019-10-14 | 2019-10-14 | Thanksgiving
2019-11-11 | 2019-11-11 | Remember Day
2019-12-25 | 2019-12-25 | Christmas Day
2019-12-26 | 2019-12-26 | Boxing Day
2020
2020-01-01 | 2020-01-01 | New Years's Day
2020-02-17 | 2020-02-17 | Family Day
2020-04-10 | 2020-04-10 | Good Friday
2020-04-13 | 2020-04-13 | Easter Monday
2020-05-18 | 2020-05-18 | Victoria Day
2020-05-18 | 2020-05-18 | St Jean Baptiste Day
2020-07-01 | 2020-07-01 | Canada Day
2020-08-03 | 2020-08-03 | Civic Holiday
2020-09-07 | 2020-09-07 | Labour Day
2020-10-12 | 2020-10-12 | Thanksgiving
2020-11-11 | 2020-11-11 | Remember Day
2020-12-25 | 2020-12-25 | Christmas Day
2020-12-28 | 2020-12-28 | Boxing Day
2021
2021-01-01 | 2021-01-01 | New Years's Day | January 1
2021-02-15 | 2021-02-15 | Family Day | Third Monday in February
2021-04-02 | 2021-04-02 | Good Friday | Friday before Easter Sunday
2021-04-05 | 2021-04-05 | Easter Monday | Monday after Easter Sunday
2021-05-24 | 2021-05-24 | Victoria Day | Monday preceding May 25th
2021-06-24 | 2021-06-24 | St Jean Baptiste Day | June 24
2021-07-01 | 2021-07-01 | Canada Day | July 1
2021-08-02 | 2021-08-02 | Civic Holiday | First Monday in August
2021-09-06 | 2021-09-06 | Labour Day | First Monday of September
2021-09-30 | 2021-09-30 | National Day for Truth and Reconciliation | September 30
2021-10-11 | 2021-10-11 | Thanksgiving | Second Monday in October
2021-11-11 | 2021-11-11 | Remember Day | November 11
2021-12-25 | 2021-12-25 | Christmas Day | December 25
2021-12-26 | 2021-12-26 | Boxing Day | December 26
2022
2022-01-01 | 2022-01-01 | New Years's Day | January 1
2022-02-21 | 2022-02-21 | Family Day | Third Monday in February
2022-04-15 | 2022-04-15 | Good Friday | Friday before Easter Sunday
2022-04-18 | 2022-04-18 | Easter Monday | Monday after Easter Sunday
2022-05-23 | 2022-05-23 | Victoria Day | Monday preceding May 25th
2022-06-24 | 2022-06-24 | St Jean Baptiste Day | June 24
2022-07-01 | 2022-07-01 | Canada Day | July 1
2022-08-01 | 2022-08-01 | Civic Holiday | First Monday in August
2022-09-05 | 2022-09-05 | Labour Day | First Monday of September
2022-09-30 | 2022-09-30 | National Day for Truth and Reconciliation | September 30
2022-10-10 | 2022-10-10 | Thanksgiving | Second Monday in October
2022-11-11 | 2022-11-11 | Remember Day | November 11
2022-12-25 | 2022-12-25 | Christmas Day | December 25
2022-12-26 | 2022-12-26 | Boxing Day | December 26
2023
2023-01-01 | 2023-01-01 | New Years's Day | January 1
2023-02-20 | 2023-02-20 | Family Day | Third Monday in February
2023-04-07 | 2023-04-07 | Good Friday | Friday before Easter Sunday
2023-04-10 | 2023-04-10 | Easter Monday | Monday after Easter Sunday
2023-05-22 | 2023-05-22 | Victoria Day | Monday preceding May 25th
2023-06-24 | 2023-06-24 | St Jean Baptiste Day | June 24
2023-07-01 | 2023-07-01 | Canada Day | July 1
2023-08-07 | 2023-08-07 | Civic Holiday | First Monday in August
2023-09-04 | 2023-09-04 | Labour Day | First Monday of September
2023-09-30 | 2023-09-30 | National Day for Truth and Reconciliation | September 30
2023-10-09 | 2023-10-09 | Thanksgiving | Second Monday in October
2023-11-11 | 2023-11-11 | Remember Day | November 11
2023-12-25 | 2023-12-25 | Christmas Day | December 25
2023-12-26 | 2023-12-26 | Boxing Day | December 26
2024
2024-01-01 | 2024-01-01 | New Years's Day | January 1
2024-02-19 | 2024-02-19 | Family Day | Third Monday in February
2024-03-29 | 2024-03-29 | Good Friday | Friday before Easter Sunday
2024-04-01 | 2024-04-01 | Easter Monday | Monday after Easter Sunday
2024-05-20 | 2024-05-20 | Victoria Day | Monday preceding May 25th
2024-06-24 | 2024-06-24 | St Jean Baptiste Day | June 24
2024-07-01 | 2024-07-01 | Canada Day | July 1
2024-08-05 | 2024-08-05 | Civic Holiday | First Monday in August
2024-09-02 | 2024-09-02 | Labour Day | First Monday of September
2024-09-30 | 2024-09-30 | National Day for Truth and Reconciliation | September 30
2024-10-14 | 2024-10-14 | Thanksgiving | Second Monday in October
2024-11-11 | 2024-11-11 | Remember Day | November 11
2024-12-25 | 2024-12-25 | Christmas Day | December 25
2024-12-26 | 2024-12-26 | Boxing Day | December 26
2025
2025-01-01 | 2025-01-01 | New Years's Day | January 1
2025-02-17 | 2025-02-17 | Family Day | Third Monday in February
2025-04-18 | 2025-04-18 | Good Friday | Friday before Easter Sunday
2025-04-21 | 2025-04-21 | Easter Monday | Monday after Easter Sunday
2025-05-19 | 2025-05-19 | Victoria Day | Monday preceding May 25th
2025-06-24 | 2025-06-24 | St Jean Baptiste Day | June 24
2025-07-01 | 2025-07-01 | Canada Day | July 1
2025-08-04 | 2025-08-04 | Civic Holiday | First Monday in August
2025-09-01 | 2025-09-01 | Labour Day | First Monday of September
2025-09-30 | 2025-09-30 | National Day for Truth and Reconciliation | September 30
2025-10-13 | 2025-10-13 | Thanksgiving | Second Monday in October
2025-11-11 | 2025-11-11 | Remember Day | November 11
2025-12-25 | 2025-12-25 | Christmas Day | December 25
2025-12-26 | 2025-12-26 | Boxing Day | December 26
2026
2026-01-01 | 2026-01-01 | New Years's Day | January 1
2026-02-16 | 2026-02-16 | Family Day | Third Monday in February
2026-04-03 | 2026-04-03 | Good Friday | Friday before Easter Sunday
2026-04-06 | 2026-04-06 | Easter Monday | Monday after Easter Sunday
2026-05-18 | 2026-05-18 | Victoria Day | Monday preceding May 25th
2026-06-24 | 2026-06-24 | St Jean Baptiste Day | June 24
2026-07-01 | 2026-07-01 | Canada Day | July 1
2026-08-03 | 2026-08-03 | Civic Holiday | First Monday in August
2026-09-07 | 2026-09-07 | Labour Day | First Monday of September
2026-09-30 | 2026-09-30 | National Day for Truth and Reconciliation | September 30
2026-10-12 | 2026-10-12 | Thanksgiving | Second Monday in October
2026-11-11 | 2026-11-11 | Remember Day | November 11
2026-12-25 | 2026-12-25 | Christmas Day | December 25
2026-12-26 | 2026-12-26 | Boxing Day | December 26
2027
2027-01-01 | 2027-01-01 | New Years's Day | January 1
2027-02-15 | 2027-02-15 | Family Day | Third Monday in February
2027-03-26 | 2027-03-26 | Good Friday | Friday before Easter Sunday
2027-03-29 | 2027-03-29 | Easter Monday | Monday after Easter Sunday
2027-05-24 | 2027-05-24 | Victoria Day | Monday preceding May 25th
2027-06-24 | 2027-06-24 | St Jean Baptiste Day | June 24
2027-07-01 | 2027-07-01 | Canada Day | July 1
2027-08-02 | 2027-08-02 | Civic Holiday | First Monday in August
2027-09-06 | 2027-09-06 | Labour Day | First Monday of September
2027-09-30 | 2027-09-30 | National Day for Truth and Reconciliation | September 30
2027-10-11 | 2027-10-11 | Thanksgiving | Second Monday in October
2027-11-11 | 2027-11-11 | Remember Day | November 11
2027-12-25 | 2027-12-25 | Christmas Day | December 25
2027-12-26 | 2027-12-26 | Boxing Day | December 26
2028
2028-01-01 | 2028-01-01 | New Years's Day | January 1
2028-02-21 | 2028-02-21 | Family Day | Third Monday in February
2028-04-14 | 2028-04-14 | Good Friday | Friday before Easter Sunday
2028-04-17 | 2028-04-17 | Easter Monday | Monday after Easter Sunday
2028-05-22 | 2028-05-22 | Victoria Day | Monday preceding May 25th
2028-06-24 | 2028-06-24 | St Jean Baptiste Day | June 24
2028-07-01 | 2028-07-01 | Canada Day | July 1
2028-08-07 | 2028-08-07 | Civic Holiday | First Monday in August
2028-09-04 | 2028-09-04 | Labour Day | First Monday of September
2028-09-30 | 2028-09-30 | National Day for Truth and Reconciliation | September 30
2028-10-09 | 2028-10-09 | Thanksgiving | Second Monday in October
2028-11-11 | 2028-11-11 | Remember Day | November 11
2028-12-25 | 2028-12-25 | Christmas Day | December 25
2028-12-26 | 2028-12-26 | Boxing Day | December 26
2029
2029-01-01 | 2029-01-01 | New Years's Day | January 1
2029-02-19 | 2029-02-19 | Family Day | Third Monday in February
2029-03-30 | 2029-03-30 | Good Friday | Friday before Easter Sunday
2029-04-02 | 2029-04-02 | Easter Monday | Monday after Easter Sunday
2029-05-21 | 2029-05-21 | Victoria Day | Monday preceding May 25th
2029-06-24 | 2029-06-24 | St Jean Baptiste Day | June 24
2029-07-01 | 2029-07-01 | Canada Day | July 1
2029-08-06 | 2029-08-06 | Civic Holiday | First Monday in August
2029-09-03 | 2029-09-03 | Labour Day | First Monday of September
2029-09-30 | 2029-09-30 | National Day for Truth and Reconciliation | September 30
2029-10-08 | 2029-10-08 | Thanksgiving | Second Monday in October
2029-11-11 | 2029-11-11 | Remember Day | November 11
2029-12-25 | 2029-12-25 | Christmas Day | December 25
2029-12-26 | 2029-12-26 | Boxing Day | December 26
2030
2030-01-01 | 2030-01-01 | New Years's Day | January 1
2030-02-18 | 2030-02-18 | Family Day | Third Monday in February
2030-04-19 | 2030-04-19 | Good Friday | Friday before Easter Sunday
2030-04-22 | 2030-04-22 | Easter Monday | Monday after Easter Sunday
2030-05-20 | 2030-05-20 | Victoria Day | Monday preceding May 25th
2030-06-24 | 2030-06-24 | St Jean Baptiste Day | June 24
2030-07-01 | 2030-07-01 | Canada Day | July 1
2030-08-05 | 2030-08-05 | Civic Holiday | First Monday in August
2030-09-02 | 2030-09-02 | Labour Day | First Monday of September
2030-09-30 | 2030-09-30 | National Day for Truth and Reconciliation | September 30
2030-10-14 | 2030-10-14 | Thanksgiving | Second Monday in October
2030-11-11 | 2030-11-11 | Remember Day | November 11
2030-12-25 | 2030-12-25 | Christmas Day | December 25
2030-12-26 | 2030-12-26 | Boxing Day | December 26
2031
2031-01-01 | 2031-01-01 | New Years's Day | January 1
2031-02-17 | 2031-02-17 | Family Day | Third Monday in February
2031-04-11 | 2031-04-11 | Good Friday | Friday before Easter Sunday
2031-04-14 | 2031-04-14 | Easter Monday | Monday after Easter Sunday
2031-05-19 | 2031-05-19 | Victoria Day | Monday preceding May 25th
2031-06-24 | 2031-06-24 | St Jean Baptiste Day | June 24
2031-07-01 | 2031-07-01 | Canada Day | July 1
2031-08-04 | 2031-08-04 | Civic Holiday | First Monday in August
2031-09-01 | 2031-09-01 | Labour Day | First Monday of September
2031-09-30 | 2031-09-30 | National Day for Truth and Reconciliation | September 30
2031-10-13 | 2031-10-13 | Thanksgiving | Second Monday in October
2031-11-11 | 2031-11-11 | Remember Day | November 11
2031-12-25 | 2031-12-25 | Christmas Day | December 25
2031-12-26 | 2031-12-26 | Boxing Day | December 26
2032
2032-01-01 | 2032-01-01 | New Years's Day | January 1
2032-02-16 | 2032-02-16 | Family Day | Third Monday in February
2032-03-26 | 2032-03-26 | Good Friday | Friday before Easter Sunday
2032-03-29 | 2032-03-29 | Easter Monday | Monday after Easter Sunday
2032-05-24 | 2032-05-24 | Victoria Day | Monday preceding May 25th
2032-06-24 | 2032-06-24 | St Jean Baptiste Day | June 24
2032-07-01 | 2032-07-01 | Canada Day | July 1
2032-08-02 | 2032-08-02 | Civic Holiday | First Monday in August
2032-09-06 | 2032-09-06 | Labour Day | First Monday of September
2032-09-30 | 2032-09-30 | National Day for Truth and Reconciliation | September 30
2032-10-11 | 2032-10-11 | Thanksgiving | Second Monday in October
2032-11-11 | 2032-11-11 | Remember Day | November 11
2032-12-25 | 2032-12-25 | Christmas Day | December 25
2032-12-26 | 2032-12-26 | Boxing Day | December 26
2033
2033-01-01 | 2033-01-01 | New Years's Day | January 1
2033-02-21 | 2033-02-21 | Family Day | Third Monday in February
2033-04-15 | 2033-04-15 | Good Friday | Friday before Easter Sunday
2033-04-18 | 2033-04-18 | Easter Monday | Monday after Easter Sunday
2033-05-23 | 2033-05-23 | Victoria Day | Monday preceding May 25th
2033-06-24 | 2033-06-24 | St Jean Baptiste Day | June 24
2033-07-01 | 2033-07-01 | Canada Day | July 1
2033-08-01 | 2033-08-01 | Civic Holiday | First Monday in August
2033-09-05 | 2033-09-05 | Labour Day | First Monday of September
2033-09-30 | 2033-09-30 | National Day for Truth and Reconciliation | September 30
2033-10-10 | 2033-10-10 | Thanksgiving | Second Monday in October
2033-11-11 | 2033-11-11 | Remember Day | November 11
2033-12-25 | 2033-12-25 | Christmas Day | December 25
2033-12-26 | 2033-12-26 | Boxing Day | December 26
2034
2034-01-01 | 2034-01-01 | New Years's Day | January 1
2034-02-20 | 2034-02-20 | Family Day | Third Monday in February
2034-04-07 | 2034-04-07 | Good Friday | Friday before Easter Sunday
2034-04-10 | 2034-04-10 | Easter Monday | Monday after Easter Sunday
2034-05-22 | 2034-05-22 | Victoria Day | Monday preceding May 25th
2034-06-24 | 2034-06-24 | St Jean Baptiste Day | June 24
2034-07-01 | 2034-07-01 | Canada Day | July 1
2034-08-07 | 2034-08-07 | Civic Holiday | First Monday in August
2034-09-04 | 2034-09-04 | Labour Day | First Monday of September
2034-09-30 | 2034-09-30 | National Day for Truth and Reconciliation | September 30
2034-10-09 | 2034-10-09 | Thanksgiving | Second Monday in October
2034-11-11 | 2034-11-11 | Remember Day | November 11
2034-12-25 | 2034-12-25 | Christmas Day | December 25
2034-12-26 | 2034-12-26 | Boxing Day | December 26
2035
2035-01-01 | 2035-01-01 | New Years's Day | January 1
2035-02-19 | 2035-02-19 | Family Day | Third Monday in February
2035-03-23 | 2035-03-23 | Good Friday | Friday before Easter Sunday
2035-03-26 | 2035-03-26 | Easter Monday | Monday after Easter Sunday
2035-05-21 | 2035-05-21 | Victoria Day | Monday preceding May 25th
2035-06-24 | 2035-06-24 | St Jean Baptiste Day | June 24
2035-07-01 | 2035-07-01 | Canada Day | July 1
2035-08-06 | 2035-08-06 | Civic Holiday | First Monday in August
2035-09-03 | 2035-09-03 | Labour Day | First Monday of September
2035-09-30 | 2035-09-30 | National Day for Truth and Reconciliation | September 30
2035-10-08 | 2035-10-08 | Thanksgiving | Second Monday in October
2035-11-11 | 2035-11-11 | Remember Day | November 11
2035-12-25 | 2035-12-25 | Christmas Day | December 25
2035-12-26 | 2035-12-26 | Boxing Day | December 26
2036
2036-01-01 | 2036-01-01 | New Years's Day | January 1
2036-02-18 | 2036-02-18 | Family Day | Third Monday in February
2036-04-11 | 2036-04-11 | Good Friday | Friday before Easter Sunday
2036-04-14 | 2036-04-14 | Easter Monday | Monday after Easter Sunday
2036-05-19 | 2036-05-19 | Victoria Day | Monday preceding May 25th
2036-06-24 | 2036-06-24 | St Jean Baptiste Day | June 24
2036-07-01 | 2036-07-01 | Canada Day | July 1
2036-08-04 | 2036-08-04 | Civic Holiday | First Monday in August
2036-09-01 | 2036-09-01 | Labour Day | First Monday of September
2036-09-30 | 2036-09-30 | National Day for Truth and Reconciliation | September 30
2036-10-13 | 2036-10-13 | Thanksgiving | Second Monday in October
2036-11-11 | 2036-11-11 | Remember Day | November 11
2036-12-25 | 2036-12-25 | Christmas Day | December 25
2036-12-26 | 2036-12-26 | Boxing Day | December 26
2037
2037-01-01 | 2037-01-01 | New Years's Day | January 1
2037-02-16 | 2037-02-16 | Family Day | Third Monday in February
2037-04-03 | 2037-04-03 | Good Friday | Friday before Easter Sunday
2037-04-06 | 2037-04-06 | Easter Monday | Monday after Easter Sunday
2037-05-18 | 2037-05-18 | Victoria Day | Monday preceding May 25th
2037-06-24 | 2037-06-24 | St Jean Baptiste Day | June 24
2037-07-01 | 2037-07-01 | Canada Day | July 1
2037-08-03 | 2037-08-03 | Civic Holiday | First Monday in August
2037-09-07 | 2037-09-07 | Labour Day | First Monday of September
2037-09-30 | 2037-09-30 | National Day for Truth and Reconciliation | September 30
2037-10-12 | 2037-10-12 | Thanksgiving | Second Monday in October
2037-11-11 | 2037-11-11 | Remember Day | November 11
2037-12-25 | 2037-12-25 | Christmas Day | December 25
2037-12-26 | 2037-12-26 | Boxing Day | December 26
2038
2038-01-01 | 2038-01-01 | New Years's Day | January 1
2038-02-15 | 2038-02-15 | Family Day | Third Monday in February
2038-04-23 | 2038-04-23 | Good Friday | Friday before Easter Sunday
2038-04-26 | 2038-04-26 | Easter Monday | Monday after Easter Sunday
2038-05-24 | 2038-05-24 | Victoria Day | Monday preceding May 25th
2038-06-24 | 2038-06-24 | St Jean Baptiste Day | June 24
2038-07-01 | 2038-07-01 | Canada Day | July 1
2038-08-02 | 2038-08-02 | Civic Holiday | First Monday in August
2038-09-06 | 2038-09-06 | Labour Day | First Monday of September
2038-09-30 | 2038-09-30 | National Day for Truth and Reconciliation | September 30
2038-10-11 | 2038-10-11 | Thanksgiving | Second Monday in October
2038-11-11 | 2038-11-11 | Remember Day | November 11
2038-12-25 | 2038-12-25 | Christmas Day | December 25
2038-12-26 | 2038-12-26 | Boxing Day | December 26
2039
2039-01-01 | 2039-01-01 | New Years's Day | January 1
2039-02-21 | 2039-02-21 | Family Day | Third Monday in February
2039-04-08 | 2039-04-08 | Good Friday | Friday before Easter Sunday
2039-04-11 | 2039-04-11 | Easter Monday | Monday after Easter Sunday
2039-05-23 | 2039-05-23 | Victoria Day | Monday preceding May 25th
2039-06-24 | 2039-06-24 | St Jean Baptiste Day | June 24
2039-07-01 | 2039-07-01 | Canada Day | July 1
2039-08-01 | 2039-08-01 | Civic Holiday | First Monday in August
2039-09-05 | 2039-09-05 | Labour Day | First Monday of September
2039-09-30 | 2039-09-30 | National Day for Truth and Reconciliation | September 30
2039-10-10 | 2039-10-10 | Thanksgiving | Second Monday in October
2039-11-11 | 2039-11-11 | Remember Day | November 11
2039-12-25 | 2039-12-25 | Christmas Day | December 25
2039-12-26 | 2039-12-26 | Boxing Day | December 26
2040
2040-01-01 | 2040-01-01 | New Years's Day | January 1
2040-02-20 | 2040-02-20 | Family Day | Third Monday in February
2040-03-30 | 2040-03-30 | Good Friday | Friday before Easter Sunday
2040-04-02 | 2040-04-02 | Easter Monday | Monday after Easter Sunday
2040-05-21 | 2040-05-21 | Victoria Day | Monday preceding May 25th
2040-06-24 | 2040-06-24 | St Jean Baptiste Day | June 24
2040-07-01 | 2040-07-01 | Canada Day | July 1
2040-08-06 | 2040-08-06 | Civic Holiday | First Monday in August
2040-09-03 | 2040-09-03 | Labour Day | First Monday of September
2040-09-30 | 2040-09-30 | National Day for Truth and Reconciliation | September 30
2040-10-08 | 2040-10-08 | Thanksgiving | Second Monday in October
2040-11-11 | 2040-11-11 | Remember Day | November 11
2040-12-25 | 2040-12-25 | Christmas Day | December 25
2040-12-26 | 2040-12-26 | Boxing Day | December 26
2041
2041-01-01 | 2041-01-01 | New Years's Day | January 1
2041-02-18 | 2041-02-18 | Family Day | Third Monday in February
2041-04-19 | 2041-04-19 | Good Friday | Friday before Easter Sunday
2041-04-22 | 2041-04-22 | Easter Monday | Monday after Easter Sunday
2041-05-20 | 2041-05-20 | Victoria Day | Monday preceding May 25th
2041-06-24 | 2041-06-24 | St Jean Baptiste Day | June 24
2041-07-01 | 2041-07-01 | Canada Day | July 1
2041-08-05 | 2041-08-05 | Civic Holiday | First Monday in August
2041-09-02 | 2041-09-02 | Labour Day | First Monday of September
2041-09-30 | 2041-09-30 | National Day for Truth and Reconciliation | September 30
2041-10-14 | 2041-10-14 | Thanksgiving | Second Monday in October
2041-11-11 | 2041-11-11 | Remember Day | November 11
2041-12-25 | 2041-12-25 | Christmas Day | December 25
2041-12-26 | 2041-12-26 | Boxing Day | December 26
2042
2042-01-01 | 2042-01-01 | New Years's Day | January 1
2042-02-17 | 2042-02-17 | Family Day | Third Monday in February
2042-04-04 | 2042-04-04 | Good Friday | Friday before Easter Sunday
2042-04-07 | 2042-04-07 | Easter Monday | Monday after Easter Sunday
2042-05-19 | 2042-05-19 | Victoria Day | Monday preceding May 25th
2042-06-24 | 2042-06-24 | St Jean Baptiste Day | June 24
2042-07-01 | 2042-07-01 | Canada Day | July 1
2042-08-04 | 2042-08-04 | Civic Holiday | First Monday in August
2042-09-01 | 2042-09-01 | Labour Day | First Monday of September
2042-09-30 | 2042-09-30 | National Day for Truth and Reconciliation | September 30
2042-10-13 | 2042-10-13 | Thanksgiving | Second Monday in October
2042-11-11 | 2042-11-11 | Remember Day | November 11
2042-12-25 | 2042-12-25 | Christmas Day | December 25
2042-12-26 | 2042-12-26 | Boxing Day | December 26
2043
2043-01-01 | 2043-01-01 | New Years's Day | January 1
2043-02-16 | 2043-02-16 | Family Day | Third Monday in February
2043-03-27 | 2043-03-27 | Good Friday | Friday before Easter Sunday
2043-03-30 | 2043-03-30 | Easter Monday | Monday after Easter Sunday
2043-05-18 | 2043-05-18 | Victoria Day | Monday preceding May 25th
2043-06-24 | 2043-06-24 | St Jean Baptiste Day | June 24
2043-07-01 | 2043-07-01 | Canada Day | July 1
2043-08-03 | 2043-08-03 | Civic Holiday | First Monday in August
2043-09-07 | 2043-09-07 | Labour Day | First Monday of September
2043-09-30 | 2043-09-30 | National Day for Truth and Reconciliation | September 30
2043-10-12 | 2043-10-12 | Thanksgiving | Second Monday in October
2043-11-11 | 2043-11-11 | Remember Day | November 11
2043-12-25 | 2043-12-25 | Christmas Day | December 25
2043-12-26 | 2043-12-26 | Boxing Day | December 26
2044
2044-01-01 | 2044-01-01 | New Years's Day | January 1
2044-02-15 | 2044-02-15 | Family Day | Third Monday in February
2044-04-15 | 2044-04-15 | Good Friday | Friday before Easter Sunday
2044-04-18 | 2044-04-18 | Easter Monday | Monday after Easter Sunday
2044-05-23 | 2044-05-23 | Victoria Day | Monday preceding May 25th
2044-06-24 | 2044-06-24 | St Jean Baptiste Day | June 24
2044-07-01 | 2044-07-01 | Canada Day | July 1
2044-08-01 | 2044-08-01 | Civic Holiday | First Monday in August
2044-09-05 | 2044-09-05 | Labour Day | First Monday of September
2044-09-30 | 2044-09-30 | National Day for Truth and Reconciliation | September 30
2044-10-10 | 2044-10-10 | Thanksgiving | Second Monday in October
2044-11-11 | 2044-11-11 | Remember Day | November 11
2044-12-25 | 2044-12-25 | Christmas Day | December 25
2044-12-26 | 2044-12-26 | Boxing Day | December 26