**NPA 416-437-647 RELIEF**

**(Implementation of New Overlay NPA 942)**

**NETWORK IMPLEMENTATION TASK FORCE (NITF)**

**PROGRESS REPORT TO THE RELIEF PLANNING COMMITTEE (RPC)**

**21 February 2025**

**INTRODUCTION**

This NITF Progress Report is submitted to the Relief Planning Committee (RPC) and CRTC staff for NPA 942 as required under Telecom Decision CRTC 2023-135.

The objective of the Network Implementation Plan (NIP) is as follow:

1. Make all network and interconnection modifications to implement the new NPA Code 942 in the NPA 416-437-647 area.

The role of the NITF is to identify and address network implementation issues that affect all carriers. The responsibilities of the NITF include, but are not limited to:

1. Develop and agree on a NIP and schedule;
2. Develop and submit progress reports;
3. Identify and address NIP issues;
4. Act as single point of contact on NIP issues;
5. Identify any network concerns or issues regarding the implementation of relief and advise the RPC, the Commission or Commission staff as appropriate; and,
6. Develop inter-network test plans, as necessary.

The role of the individual NITF representative of each TSP is to ensure that its TSP organization develops, submits and implements its individual network implementation plan in accordance with the NIP and associated schedule. Each representative acts as the single point of contact for implementation of the NIP and activities for its organization. Each TSP is responsible to develop, submit and implement its individual network implementation plan in accordance with the industry level NIP.

All TSPs are required to provide progress reports to the NITF for submission to the RPC in accordance with the Relief Implementation Schedule.

Test Plans and Tests, if required, shall be arranged on a bilateral basis between interconnecting TSPs in accordance with bilateral agreements and the Relief Implementation Schedule.

Individual TSPs and industry database owners/operators (e.g., Canadian Local Number Portability Consortium) should notify the NITF, or Commission staff, or the Commission, as appropriate, if there are any problems or concerns with modifying their systems and databases in time to implement relief in accordance with the RIP.

The NPA Relief Implementation Plan (RIP) requires periodic progress reports by each Telecommunications Service Provider (TSP) operating in the NPA and by the Network Implementation Task Forces (NITF) established for each NPA relief project.

The Relief Implementation Plan Schedule indicates that the following Progress Reports are required:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 28 | TSPs to submit **Progress Report #1** to NITF and CATF (starts after completion date for all TSPs to notify their customers and requires 2 weeks) | TSPs | 2024-10-26 | 2024-11-08 |
| 29 | NITF and CATF develop & submit Progress Report #1 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2024-11-08 | 2024-11-22 |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 49 | TSPs to submit **Progress Report #2** to NITF (starts on commencement of Inter-Carrier Testing Period) | | TSPs | 2025-01-26 | 2025-02-07 |
| 50 | NITF develop & submit Progress Report #2 to RPC (linked to TSP reports to NITF and CATF) | | NITF | 2025-02-07 | 2025-02-21 |
| 51 | RPC submits Progress Report #2 to CRTC staff (linked to NITF reports) | RPC | | 2025-02-21 | 2025-03-07 |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 53 | TSPs submit **Final Report** to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs | 2025-04-28 | 2025-05-12 |
| 54 | NITF and CATF develop & submit Final Progress Report to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2025-05-13 | 2025-05-26 |

**CARRIER PROGRESS REPORTS**

Attached to this NITF Progress Report are the individual Progress Reports submitted by the following Carriers (CO Code Holders):

* Allstream
* Bell Canada (including Bell Mobility)
* Comwave
* Distributel (including Primus)
* Fibernetics
* Freedom Mobile
* Rogers Communications (including Fido & Shaw Telecom)
* TekSavvy
* TELUS (TELUS Mobility and TELUS Integrated Communications)
* Vianet/ExaTEL
* Vidéotron

The known TSPs that did not submit a progress report to the NITF are:

* Beanfield Technologies
* Bragg Communications (Eastlink)
* InnsysVoice
* ISP Telecom
* Iristel
* Ixica Communications
* Managed Network Systems

The NITF is not aware of any other current or future TSPs that may decide to operate in the affected NPA prior to the relief date.

**NETWORK IMPLEMENTATION PLAN PROGRESS**

The NITF is following the schedule in the RIP for this NPA (see Attachment 1). All network implementation activities are proceeding according to the schedule contained in the Relief Implementation Plan (RIP).

The NITF has no concerns to identify at this time and no major problems have been identified to date or are foreseen that could jeopardize implementation of relief in accordance with the current Relief Implementation Plan.

However, the NITF advises that there are several known TSPs that did not submit a progress report to the NITF. It is expected that those TSPs will submit their reports directly to the CRTC.

Submitted by:

Marie-Christine Hudon

Chair NITF

**Attachment 1**

**RELIEF IMPLEMENTATION SCHEDULE**

**For a Distributed Overlay of new NPA 942 over NPA 416/437/647**

| **Item** | **Task or Event** | **PRIME** | **START** | **END** |
| --- | --- | --- | --- | --- |
| 1 | CNA identifies NPA exhaust of January 2024 and notifies by e-mail CRTC staff, CSCN, NANPA & CISC that the NPA will exhaust within the future six year time period | CNA |  | 2019-03-26 |
| 2 | CNA conducts initial R-NRUF and releases results indicating a PED of June 2025 | CNA | 2019-06-15 | 2019-09-20 |
| 3 | CRTC issues Telecom Notice of Consultation regarding establishment of an ad hoc Relief Planning Committee | CRTC |  | 2020-01-30 |
| 4 | CNA releases January 2020 R-NRUF showing a PED of January 2025 | CNA |  | 2020-03-24 |
| 5 | CNA releases July 2020 R-NRUF showing a PED of November 2025 | CNA |  | 2020-08-18 |
| 6 | CNA releases January 2021 R-NRUF showing a PED of July 2026 | CNA |  | 2021-02-23 |
| 7 | CNA releases July 2021 R-NRUF showing a PED of November 2025 | CNA |  | 2021-08-19 |
| 8 | CNA releases January 2022 R-NRUF showing a PED of March 2026 | CNA |  | 2022-03-01 |
| 9 | CNA releases July 2022 R-NRUF showing a PED of November 2026 | CNA |  | 2022-08-19 |
| 10 | RPC Chair starts preparing and submitting RPC Chair Reports to the CISC, on an as required basis. | RPC Chair | 2020-01-30 | 2025-08-01 |
| 11 | CNA develops and distributes PROC | CNA | 2019-03-26 | 2022-09-15 |
| 12 | RPC participants review PROC & submit contributions to RPC |  | 2022-09-15 | 2022-09-26 |
| 13 | CNA chairs initial RPC conference call to start development of PD, RIP & PL, & schedules future meetings/conference calls including creation & consultation with CATF and NITF | CNA, RPC | 2022-10-20 | 2022-10-20 |
| 14 | CNA chairs subsequent RPC conference calls to finalize PD & RIP | CNA, RPC | 2022-10-21 | 2022-11-21 |
| 15 | CNA forwards the PD and RIP to the CISC for approval | CNA | 2022-11-21 | 2022-12-05 |
| 16 | Special Types of Telecommunications Service Users (911 PSAPs, alarm companies, ISPs, paging companies, etc.) to identify any concerns to RPC & CRTC | Special Users | 2022-10-20 | 2022-12-05 |
| 17 | CISC reviews and forwards PD and RIP to the CRTC for approval | CISC | 2022-12-05 | 2023-01-05 |
| 18 | CRTC issues Telecom Decision approving the Relief Method, Relief Date, New NPA & Relief Implementation Plan (RIP) | CRTC | 2023-01-05 | 2023-06-05 |
| 19 | CNA obtains relief NPA from NANPA | CNA | 2023-06-05 | 2023-06-19 |
| 20 | CNA develops and RPC approves the Planning Letter (PL) | RPC | 2023-06-19 | 2023-07-04 |
| 21 | Task Forces, TSPs and users implement relief (starts upon CRTC approval of RIP and ends on Relief Date) | TSPs | 2023-06-05 | 2025-04-26 |
| 22 | All Telecom Service Providers (TSPs) to develop and file individual consumer awareness programs with the CRTC (may be done collectively by Telecommunications Alliance) (starts upon CRTC approval of RIP) | TSPs | 2023-06-05 | 2024-07-26 |
| 23 | CNA submits PL to NANPA | CNA | 2023-07-04 | 2023-07-18 |
| 24 | NANPA receives and posts Planning Letter to NANPA website (within 2 weeks of receipt from the CNA) | NANPA | 2023-07-18 | 2023-08-01 |
| 25 | All TSPs implement consumer awareness activities (starts upon filing of Consumer Awareness Programs with the CRTC and is completed on the Relief Date) | TSPs | 2024-07-26 | 2025-04-26 |
| 26 | TSPs and/or Telecommunication Alliance issue media release (may start upon CRTC approval of RIP) | CNA | 2023-06-05 | 2024-10-26 |
| 27 | All TSPs to notify all customers (including residence, business & special customers) of the new overlay NPA (may start upon the filing of Consumer Awareness Programs with the CRTC) | TSPs | 2024-07-26 | 2024-10-26 |
| 28 | TSPs to submit **Progress Report #1** to NITF and CATF (starts after completion date for all TSPs to notify their customers and requires 2 weeks) | TSPs | 2024-10-26 | 2024-11-08 |
| 29 | NITF and CATF develop & submit Progress Report #1 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2024-11-08 | 2024-11-22 |
| 30 | RPC submits Progress Report #1 to CISC/CRTC (linked to NITF and CATF reports) | RPC | 2024-11-22 | 2024-12-06 |
| 31 | CNA sends relief implementation information for updating BIRRDS to iconectiv |  | 2024-06-19 | 2024-06-26 |
| 32 | iconectiv TRA database updates to add Exchange Areas to new overlay NPA (starts on the date that the PL is posted to the NANPA web site and must be completed by 6 months prior to the Relief Date) | iconectiv TRA | 2024-06-26 | 2024-07-26 |
| 33 | All Telecommunications Service Users (including Special Users 911 PSAPs, alarm companies, ISPs, paging companies, etc.) to implement changes to their telecom equipment & systems to accommodate the new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Telecom Service Users | 2023-06-05 | 2025-04-26 |
| 34 | Payphone Providers Reprogram Payphones (starts upon CRTC approval of RIP and ends on the Relief Date) | Payphone Providers | 2023-06-05 | 2025-04-26 |
| 35 | TSPs and database owners/operators to modify systems and industry databases (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs & Database Owners | 2023-06-05 | 2025-04-26 |
| 36 | Operator Services & Directory Assistance Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2023-06-05 | 2025-04-26 |
| 37 | Directory Publisher Readiness for overlays (ability to identify the NPA in telephone numbers in the directory published after the Overlay NPA is activated) (starts upon CRTC approval of RIP and ends on the Relief Date) | Directory Publishers | 2023-06-05 | 2025-04-26 |
| 38 | 9-1-1 Systems and Databases Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | PSAPS, 9 1 1 Service Providers & TSPs | 2023-06-05 | 2025-04-26 |
| 39 | Network Systems & Equipment Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2023-06-05 | 2025-04-26 |
| 40 | Service Order & Business System Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2023-06-05 | 2025-04-26 |
| 41 | International Gateway Switch Translations Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Int’l TSPs | 2023-06-05 | 2025-04-26 |
| 42 | Canadian Local Number Portability Consortium (CLNPC) Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | CLNPC & NPAC | 2023-06-05 | 2025-04-26 |
| 43 | Toll Free SMS Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Toll TSPs | 2023-06-05 | 2025-04-26 |
| 44 | TSPs apply for Test CO Codes in new NPA (applications may be submitted no more than 6 months and no less than 66 days prior to the start date for the Inter-Carrier Testing Period) (Section 7.16.4 Canadian RP GL) | TSPs | 2024-07-26 | 2024-11-21 |
| 45 | Develop Inter-Carrier Network Test Plans and prepare for testing (individual TSPs to make arrangements in accordance with interconnection agreements) (may start upon CRTC approval of RIP and must be completed by start date for the Inter-Carrier Testing Period) | NITF & TSPs | 2023-06-05 | 2025-01-26 |
| 46 | All international and domestic Telecommunications Service Providers (TSPs) must activate the new NPA in their networks by the start date for the Inter-Carrier Testing Period | TSPs | 2023-06-05 | 2025-01-26 |
| 47 | Activation date for Overlay NPA Test CO Codes and Test Numbers in network (should be completed by the start date for the Inter-Carrier Testing Period) | TSPs |  | 2025-01-26 |
| 48 | Inter-Carrier Testing Period (subject to Inter-Carrier Network Test Plans) (starts about 3 months prior to the Relief Date, and ends about 1 month after the Relief Date) | NITF & TSPs | 2025-01-26 | 2025-05-23 |
| 49 | TSPs to submit **Progress Report #2** to NITF (starts on commencement of Inter-Carrier Testing Period) | TSPs | 2025-01-26 | 2025-02-07 |
| 50 | NITF develop & submit Progress Report #2 to RPC (linked to TSP reports to NITF and CATF) | NITF | 2025-02-07 | 2025-02-21 |
| 51 | RPC submits Progress Report #2 to CRTC staff (linked to NITF reports) | RPC | 2025-02-21 | 2025-03-07 |
| 52 | Relief Date (earliest date when CO Codes in new NPA may be activated) |  |  | 2025-04-26 |
| 53 | TSPs submit **Final Report** to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs | 2025-04-28 | 2025-05-12 |
| 54 | NITF and CATF develop & submit Final Progress Report to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2025-05-13 | 2025-05-26 |
| 55 | The RPC submits Final Progress Report to CRTC staff (linked to NITF and CATF reports) | RPC | 2025-05-26 | 2025-06-09 |
| 56 | TSPs disconnect Test Codes & Numbers, and submit Part 1 form to return Test Codes (starts 1 month after Relief Date and allows 1 month for completion) | TSPs | 2025-05-23 | 2025-06-27 |
| 57 | RPC Chair submits, to the CISC, the final RPC Chair report indicating that the **NPA 416/437/647** ad hoc RPC is no longer required | RPC Chair | 2025-06-27 | 2025-08-01 |





















