## Schedule
| Highlight means that the date is in either Jan or Dec |  |  | CRTC Decision |  | First PED in Relief Window | 2024-01-01
| Highlight is a field that needs to be filled in manually (yyyy-mm-dd) |  |  | Relief Date
Highlight means you should have a look at the overall period
Item | Task or Event | PRIME | START | END | Notes
1 | CNA identifies NPA exhaust of January 2024 and notifies by e-mail CRTC staff, CSCN, NANPA & CISC that the NPA will exhaust within the future six year time period | CNA |  | 2019-03-26 | Enter date
2 | CNA conducts initial R-NRUF and releases results indicating a PED of June 2025 | CNA | 2019-06-15 | 2019-09-20
3 | CNA releases January 2020 R-NRUF showing a PED of January 2025 | CNA |  | 2020-03-24
4 | CRTC issues Telecom Notice of Consultation regarding establishment of an ad hoc Relief Planning Committee | CRTC |  | 2020-01-30
5 | CNA releases July 2020 R-NRUF showing a PED of November 2025 | CNA |  | 2020-08-18
6 | CNA releases January 2021 R-NRUF showing a PED of July 2026 | CNA |  | 2021-02-23
7 | CNA releases July 2021 R-NRUF showing a PED of November 2025 | CNA |  | 2021-08-19
8 | CNA releases January 2022 R-NRUF showing a PED of March 2026 | CNA |  | 2022-03-01
9 | CNA releases July 2022 R-NRUF showing a PED of November 2026 | CNA |  | 2022-08-19
10 | RPC Chair starts preparing and submitting RPC Chair Reports to the CISC, on an as required basis. | RPC Chair | 2020-01-30 | 2025-08-01
11 | CNA develops and distributes PROC | CNA | 2019-03-26 |  | Enter date PROC is released
12 | RPC participants review PROC & submit contributions to RPC |  | 0
13 | CNA chairs initial RPC conference call to start development of PD, RIP & PL, & schedules future meetings/conference calls including creation & consultation with CATF and NITF | CNA, RPC
14 | CNA chairs subsequent RPC conference calls to finalize PD & RIP | CNA, RPC | 1900-01-01 |  | Enter target end date for finalized PD&RIP
15 | CNA forwards the PD and RIP to the CISC and CRTC for approval | CNA | 0 | 1900-01-12
16 | Special Types of Telecommunications Service Users (911 PSAPs, alarm companies, ISPs, paging companies, etc.) to identify any concerns to RPC & CRTC | Special Users | 0 | 1900-01-12
17 | CRTC issues Telecom Decision approving the Relief Method, Relief Date, New NPA & Relief Implementation Plan (RIP) | CRTC | 1900-01-12 |  | Enter best guess on when the CRTC issues a Decision
18 | CNA obtains relief NPA from NANPA | CNA | 0 | 1900-01-12
19 | RPC develops the Planning Letter (PL) | RPC | 1900-01-12 | 1900-01-26
20 | Task Forces, TSPs and users implement relief (starts upon CRTC approval of RIP and ends on Relief Date) | TSPs | 0
21 | All Telecom Service Providers (TSPs) to develop and file individual consumer awareness programs with the CRTC (may be done collectively by Telecommunications Alliance) (starts upon CRTC approval of RIP) | TSPs | 0 | 2024-07-26
22 | CNA submits PL and RIP to NANPA | CNA | 1900-01-26 | 1900-02-09
23 | NANPA receives and posts Planning Letter to NANPA website (within 2 weeks of receipt from the CNA) | NANPA | 1900-02-09 | 1900-02-23
24 | All TSPs implement consumer awareness activities (starts upon filing of Consumer Awareness Programs with the CRTC and is completed on the Relief Date) | TSPs | 2024-07-26 | 2025-04-26
25 | CNA issues media release (in coordination with TSPs and/or Telecommunication Alliance) (may start upon CRTC approval of RIP) | CNA | 0 | 2024-10-26
26 | All TSPs to notify all customers (including residence, business & special customers) of the new overlay NPA (may start upon the filing of Consumer Awareness Programs with the CRTC) | TSPs | 2024-07-26 | 2024-10-26 | Enter date (initial date is 12 months before relief)
27 | TSPs to submit Progress Report #1 to NITF and CATF (starts after completion date for all TSPs to notify their customers and requires 2 weeks) | TSPs | 2024-10-26 | 2024-11-08
28 | NITF and CATF develop & submit Progress Report #1 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2024-11-08 | 2024-11-22
29 | RPC submits Progress Report #1 to CISC/CRTC (linked to NITF and CATF reports) | RPC | 2024-11-22 | 2024-12-06
30 | iconectiv TRA database updates to add Exchange Areas to new overlay NPA (starts on the date that the PL is posted to the NANPA web site and must be completed by 6 months prior to the Relief Date) | iconectiv TRA | 1900-02-23 | 2024-11-21
31 | All Telecommunications Service Users (including Special Users 911 PSAPs, alarm companies, ISPs, paging companies, etc.) to implement changes to their telecom equipment & systems to accommodate the new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Telecom Service Users | 0 | 2025-04-26
32 | Payphone Providers Reprogram Payphones (starts upon CRTC approval of RIP and ends on the Relief Date) | Payphone Providers | 0 | 2025-04-26
33 | TSPs and database owners/operators to modify systems and industry databases (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs & Database Owners | 0 | 2025-04-26
34 | Operator Services & Directory Assistance Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 0 | 2025-04-26
35 | Directory Publisher Readiness for overlays (ability to identify the NPA in telephone numbers in the directory published after the Overlay NPA is activated) (starts upon CRTC approval of RIP and ends on the Relief Date) | Directory Publishers | 0 | 2025-04-26
36 | 9-1-1 Systems and Databases Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | PSAPS, 9 1 1 Service Providers & TSPs | 0 | 2025-04-26
37 | Network Systems & Equipment Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 0 | 2025-04-26
38 | Service Order & Business System Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 0 | 2025-04-26
39 | International Gateway Switch Translations Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Int’l TSPs | 0 | 2025-04-26
40 | Canadian Local Number Portability Consortium (CLNPC) Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | CLNPC & NPAC | 0 | 2025-04-26
41 | Toll Free SMS Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Toll TSPs | 0 | 2025-04-26
42 | TSPs apply for Test CO Codes in new NPA (applications may be submitted no more than 6 months and no less than 66 days prior to the start date for the Inter-Carrier Testing Period) (Section 7.16.4 Canadian RP GL) | TSPs | 2024-07-26 | 2024-11-21
43 | Develop Inter-Carrier Network Test Plans and prepare for testing (individual TSPs to make arrangements in accordance with interconnection agreements) (may start upon CRTC approval of RIP and must be completed by start date for the Inter-Carrier Testing Period) | NITF & TSPs | 0 | 2025-01-26
44 | All international and domestic Telecommunications Service Providers (TSPs) must activate the new NPA in their networks by the start date for the Inter-Carrier Testing Period | TSPs | 0 | 2025-01-26
45 | Activation date for Overlay NPA Test CO Codes and Test Numbers in network (should be completed by the start date for the Inter-Carrier Testing Period) | TSPs |  | 2025-01-26
46 | Inter-Carrier Testing Period (subject to Inter-Carrier Network Test Plans) (starts about 3 months prior to the Relief Date, and ends about 1 month after the Relief Date) | NITF & TSPs | 2025-01-26 | 2025-05-23 | Look at overall period
47 | TSPs to submit Progress Report #2 to NITF and CATF (starts on commencement of Inter-Carrier Testing Period) | TSPs | 2025-01-26 | 2025-02-07
48 | NITF and CATF develop & submit Progress Report #2 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2025-02-07 | 2025-02-21
49 | RPC submits Progress Report #2 to CRTC staff (linked to NITF and CATF reports) | RPC | 2025-02-21 | 2025-03-07
50 | Relief Date (earliest date when CO Codes in new NPA may be activated) |  |  | 2025-04-26 | Enter relief date
51 | TSPs submit Final Report to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs | 2025-04-28 | 2025-05-12
52 | NITF and CATF develop & submit Final Progress Report to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2025-05-13 | 2025-05-26
53 | The RPC submits Final Progress Report to CRTC staff (linked to NITF and CATF reports) | RPC | 2025-05-26 | 2025-06-09 | Look at overall period
54 | TSPs disconnect Test Codes & Numbers, and submit Part 1 form to return Test Codes (starts 1 month after Relief Date and allows 1 month for completion) | TSPs | 2025-05-23 | 2025-06-27
55 | RPC Chair submits, to the CISC, the final RPC Chair report indicating that the NPA 416/437/647 ad hoc RPC is no longer required | RPC Chair | 2025-06-27 | 2025-08-01 | Update NPA as required
Formulas:
START = [END, row above]
START = WORKDAY([END, row above],1,Holidays!$B2:B210)

## Holidays
2016
2016-01-01 | 2016-01-01 | New Years's Day
2016-02-15 | 2016-02-15 | Family Day
2016-03-25 | 2016-03-25 | Good Friday
2016-03-28 | 2016-03-28 | Easter Monday
2016-05-23 | 2016-05-23 | Victoria Day
2016-06-24 | 2016-06-24 | St Jean Baptiste Day
2016-01-01 | 2016-01-01 | Canada Day
2016-08-01 | 2016-08-01 | Civic Holiday
2016-09-05 | 2016-09-05 | Labour Day
2016-10-10 | 2016-10-10 | Thanksgiving
2016-11-11 | 2016-11-11 | Remember Day
2016-12-26 | 2016-12-26 | Christmas Day
2016-12-27 | 2016-12-27 | Boxing Day
2017
2017-01-02 | 2017-01-02 | New Years's Day
2017-02-20 | 2017-02-20 | Family Day
2017-04-14 | 2017-04-14 | Good Friday
2017-04-17 | 2017-04-17 | Easter Monday
2017-05-22 | 2017-05-22 | Victoria Day
2017-06-23 | 2017-06-23 | St Jean Baptiste Day
2017-07-03 | 2017-07-03 | Canada Day
2017-08-07 | 2017-08-07 | Civic Holiday
2017-09-04 | 2017-09-04 | Labour Day
2017-10-09 | 2017-10-09 | Thanksgiving
2017-11-13 | 2017-11-13 | Remember Day
2017-12-25 | 2017-12-25 | Christmas Day
2017-12-26 | 2017-12-26 | Boxing Day
2018
2018-01-01 | 2018-01-01 | New Years's Day
2018-02-19 | 2018-02-19 | Family Day
2018-03-30 | 2018-03-30 | Good Friday
2018-04-02 | 2018-04-02 | Easter Monday
2018-05-21 | 2018-05-21 | Victoria Day
2018-06-22 | 2018-06-22 | St Jean Baptiste Day
2018-07-02 | 2018-07-02 | Canada Day
2018-08-06 | 2018-08-06 | Civic Holiday
2018-09-03 | 2018-09-03 | Labour Day
2018-10-08 | 2018-10-08 | Thanksgiving
2018-11-12 | 2018-11-12 | Remember Day
2018-12-25 | 2018-12-25 | Christmas Day
2018-12-26 | 2018-12-26 | Boxing Day
2019
2019-01-01 | 2019-01-01 | New Years's Day
2019-02-18 | 2019-02-18 | Family Day
2019-04-19 | 2019-04-19 | Good Friday
2019-04-22 | 2019-04-22 | Easter Monday
2019-05-20 | 2019-05-20 | Victoria Day
2019-06-24 | 2019-06-24 | St Jean Baptiste Day
2019-07-01 | 2019-07-01 | Canada Day
2019-08-05 | 2019-08-05 | Civic Holiday
2019-09-02 | 2019-09-02 | Labour Day
2019-10-14 | 2019-10-14 | Thanksgiving
2019-11-11 | 2019-11-11 | Remember Day
2019-12-25 | 2019-12-25 | Christmas Day
2019-12-26 | 2019-12-26 | Boxing Day
2020
2020-01-01 | 2020-01-01 | New Years's Day
2020-02-17 | 2020-02-17 | Family Day
2020-04-10 | 2020-04-10 | Good Friday
2020-04-13 | 2020-04-13 | Easter Monday
2020-05-18 | 2020-05-18 | Victoria Day
2020-05-18 | 2020-05-18 | St Jean Baptiste Day
2020-07-01 | 2020-07-01 | Canada Day
2020-08-03 | 2020-08-03 | Civic Holiday
2020-09-07 | 2020-09-07 | Labour Day
2020-10-12 | 2020-10-12 | Thanksgiving
2020-11-11 | 2020-11-11 | Remember Day
2020-12-25 | 2020-12-25 | Christmas Day
2020-12-28 | 2020-12-28 | Boxing Day
2021
2021-01-01 | 2021-01-01 | New Years's Day
2021-02-15 | 2021-02-15 | Family Day
2021-04-02 | 2021-04-02 | Good Friday
2021-04-05 | 2021-04-05 | Easter Monday
2021-05-24 | 2021-05-24 | Victoria Day
2021-06-24 | 2021-06-24 | St Jean Baptiste Day
2021-07-01 | 2021-07-01 | Canada Day
2021-08-02 | 2021-08-02 | Civic Holiday
2021-09-06 | 2021-09-06 | Labour Day
2021-10-11 | 2021-10-11 | Thanksgiving
2021-11-11 | 2021-11-11 | Remember Day
2021-12-25 | 2021-12-25 | Christmas Day
2021-12-26 | 2021-12-26 | Boxing Day
2022
2022-01-01 | 2022-01-01 | New Years's Day
2022-02-22 | 2022-02-22 | Family Day
2022-04-15 | 2022-04-15 | Good Friday
2022-04-18 | 2022-04-18 | Easter Monday
2022-05-23 | 2022-05-23 | Victoria Day
2022-06-24 | 2022-06-24 | St Jean Baptiste Day
2022-07-01 | 2022-07-01 | Canada Day
2022-08-01 | 2022-08-01 | Civic Holiday
2022-09-05 | 2022-09-05 | Labour Day
2022-10-10 | 2022-10-10 | Thanksgiving
2022-11-11 | 2022-11-11 | Remember Day
2022-12-25 | 2022-12-25 | Christmas Day
2022-12-26 | 2022-12-26 | Boxing Day
2023
2023-01-01 | 2023-01-01 | New Years's Day
2023-02-20 | 2023-02-20 | Family Day
2023-04-07 | 2023-04-07 | Good Friday
2023-04-10 | 2023-04-10 | Easter Monday
2023-05-22 | 2023-05-22 | Victoria Day
2023-06-24 | 2023-06-24 | St Jean Baptiste Day
2023-07-03 | 2023-07-03 | Canada Day
2023-08-07 | 2023-08-07 | Civic Holiday
2023-09-04 | 2023-09-04 | Labour Day
2023-10-09 | 2023-10-09 | Thanksgiving
2023-11-11 | 2023-11-11 | Remember Day
2023-12-25 | 2023-12-25 | Christmas Day
2023-12-26 | 2023-12-26 | Boxing Day
2024
2024-01-01 | 2024-01-01 | New Years's Day
2024-02-19 | 2024-02-19 | Family Day
2024-03-29 | 2024-03-29 | Good Friday
2024-04-01 | 2024-04-01 | Easter Monday
2024-05-20 | 2024-05-20 | Victoria Day
2024-06-24 | 2024-06-24 | St Jean Baptiste Day
2024-07-01 | 2024-07-01 | Canada Day
2024-08-05 | 2024-08-05 | Civic Holiday
2024-09-02 | 2024-09-02 | Labour Day
2024-10-14 | 2024-10-14 | Thanksgiving
2020-11-11 | 2020-11-11 | Remember Day
2024-12-25 | 2024-12-25 | Christmas Day
2024-12-26 | 2024-12-26 | Boxing Day
2025
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2026
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2027
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2028
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2029
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2030
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
2030-12-26 | 2030-12-26 | Boxing Day