**NPA 709 RELIEF**

**(Implementation of New Overlay NPA 879)**

**NETWORK IMPLEMENTATION TASK FORCE (NITF)**

**PROGRESS REPORT TO THE RELIEF PLANNING COMMITTEE (RPC)**

**11 January 2024**

**INTRODUCTION**

This NITF Progress Report is submitted to the Relief Planning Committee (RPC) and CRTC staff for NPA 709 as required under Telecom Decision CRTC 2017-23.

The objective of the Network Implementation Plan (NIP) is as follow:

1. Make all network and interconnection modifications to implement the new NPA Code 879 in the NPA 709 area.

The role of the NITF is to identify and address network implementation issues that affect all carriers. The responsibilities of the NITF include, but are not limited to:

1. Develop and agree on a NIP and schedule;
2. Develop and submit progress reports;
3. Identify and address NIP issues;
4. Act as single point of contact on NIP issues;
5. Identify any network concerns or issues regarding the implementation of relief and advise the RPC, the Commission or Commission staff as appropriate; and,
6. Develop inter-network test plans, as necessary.

The role of the individual NITF representative of each TSP is to ensure that its TSP organization develops, submits and implements its individual network implementation plan in accordance with the NIP and associated schedule. Each representative acts as the single point of contact for implementation of the NIP and activities for its organization. Each TSP is responsible to develop, submit and implement its individual network implementation plan in accordance with the industry level NIP.

All TSPs are required to provide progress reports to the NITF for submission to the RPC in accordance with the Relief Implementation Schedule.

Test Plans and Tests, if required, shall be arranged on a bilateral basis between interconnecting TSPs in accordance with bilateral agreements and the Relief Implementation Schedule.

Individual TSPs and industry database owners/operators (e.g., Canadian Local Number Portability Consortium) should notify the NITF, or Commission staff, or the Commission, as appropriate, if there are any problems or concerns with modifying their systems and databases in time to implement relief in accordance with the RIP.

The NPA Relief Implementation Plan (RIP) requires periodic progress reports by each Telecommunications Service Provider (TSP) operating in the NPA and by the Network Implementation Task Forces (NITF) established for each NPA relief project.

The Relief Implementation Plan Schedule indicates that the following Progress Reports are required:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 57 | TSPs to submit Communications Progress Report #2 to NITF & CATF (starts after completion date for all TSPs to file their revised CAP and requires 2 weeks) | TSPs | 2023-11-30 | 2023-12-14 |
| 58 | NITF & CATF develop & submit Progress Report #2 to RPC (linked to TSP reports to CATF) | NITF & CATF | 2023-12-14 | 2024-01-11 |
| 59 | RPC submits NITF & CATF Progress Report #2 to CRTC staff (linked to CATF reports) | RPC | 2024-01-11 | 2024-01-25 |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 77 | TSPs submit Final Progress Reports to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs | 2024-02-17 | 2024-03-02 |
| 78 | NITF and CATF develop & submit Final Progress Reports to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2024-03-02 | 2024-03-16 |
| 79 | RPC submits Final Progress Reports to CRTC staff (linked to NITF and CATF reports) | RPC | 2024-03-16 | 2024-03-30 |

**CARRIER PROGRESS REPORTS**

Attached to this NITF Progress Report are the individual Progress Reports submitted by the following Carriers (CO Code Holders):

* Bell Canada (including Bell Mobility)
* Bragg Communications (Eastlink)
* Distributel
* Rogers Communications (including Fido)
* TELUS (TELUS Mobility and TELUS Integrated Communications)

The known TSPs that did not submit a progress report to the NITF are:

* Allstream
* Comwave
* Iristel

The NITF is not aware of any other current or future TSPs that may decide to operate in the affected NPA prior to the relief date.

**NETWORK IMPLEMENTATION PLAN PROGRESS**

The NITF is following the schedule in the RIP for this NPA (see Attachment 1). All network implementation activities are proceeding according to the schedule contained in the Relief Implementation Plan (RIP).

The NITF has no concerns to identify at this time and no major problems have been identified to date or are foreseen that could jeopardize implementation of relief in accordance with the current Relief Implementation Plan.

However, the NITF advises that there are several known TSPs that did not submit a progress report to the NITF. It is expected that those TSPs will submit their reports directly to the CRTC.

Submitted by:

Marie-Christine Hudon

Chair NITF

**Attachment 1**

**For a Distributed Overlay of new NPA 879 over NPA 709**

| **Item #** | **Task or Event** | **PRIME** | **START** | **END** |
| --- | --- | --- | --- | --- |
| 1 | CNA identifies NPA exhaust and notifies by e-mail CRTC staff, CSCN, NANPA & CISC that the NPA will exhaust within 72 months | CNA |   | 2016-03-11 |
| 2 | CNA conducts J-NRUF & releases results | CNA | 2016-03-14 | 2016-05-16 |
| 3 | CRTC issues Telecom Notice of Consultation regarding establishment of an ad hoc Relief Planning Committee (RPC) | CRTC |   | 2016-05-31 |
| 4 | CNA announces the date for the initial NPA Relief Planning face-to-face meeting & requests contributions | CNA | 2016-08-05 | 2016-09-20 |
| 5 | CNA develops and distributes Initial Planning Document (IPD) to RPC | CNA | 2016-05-31 | 2016-08-05 |
| 6 | RPC participants review IPD & submit contributions to RPC | RPC | 2016-08-05 | 2016-09-13 |
| 7 | CNA chairs initial RPC meeting to start development of Planning Document (PD) & Relief Implementation Plan (RIP) & schedules future meetings/conference calls | CNA, RPC | 2016-09-20 | 2016-09-22 |
| 8 | CNA chairs subsequent RPC meetings/conference calls to finalize PD and RIP | CNA, RPC | 2016-09-23 | 2016-10-07 |
| 9 | The RPC creates Consumer Awareness (CATF) and Network Implementation (NITF) Task Forces | RPC | 2016-09-21 | 2016-10-21 |
| 10 | CNA forwards PD and RIP to the CISC and CRTC for approval | CNA | 2016-10-11 | 2016-10-11 |
| 11 | Special Types of Telecommunications Service Users (9-1-1 Public Safety Answering Points (PSAPs), alarm companies, Internet Service Providers (ISPs), paging companies, etc.) to identify any concerns to RPC & CRTC | Special Users | 2016-05-31 | 2016-10-07 |
| 12 | CRTC issues Telecom Decision approving a Relief Option, Relief Date, & New NPA, and RIP (Telecom Decision CRTC 2017-35) | CRTC | 2016-10-11 | 2017-02-02 |
| 13 | CNA obtains relief NPA from NANPA | CNA | 2017-02-02 | 2017-02-06 |
| 14 | RPC develops the Planning Letter (PL) | RPC | 2017-02-03 | 2017-03-14 |
| 15 | Task Forces, Telecommunications Service Providers (TSPs) and users implement relief (starts at CRTC approval of Relief Option & Date and ends on Relief Date) | TSPs | 2017-02-02 | 2018-11-24 |
| 16 | All TSPs to develop and file individual consumer awareness programs with the CRTC (may be done collectively by Telecommunications Alliance) (starts at CRTC approval of RIP and should be completed about 24 months prior to the Relief Date) | TSPs | 2017-02-02 | 2017-02-24 |
| 17 | CNA issues media release (in coordination with Telecommunications Alliance) (may start upon CRTC approval of RIP and should be issued at least 18 months prior to the Relief Date) | CNA | 2017-02-02 | 2017-02-24 |
| 18 | CNA submits PL and RIP to NANPA (should be submitted at least 18 months prior to the Relief Date) | CNA | 2017-03-14 | 2017-03-14 |
| 19 | NANPA receives and posts Planning Letter to NANPA website (within 2 weeks of receipt from the CNA) | NANPA | 2017-03-14 | 2017-03-15 |
| 20 | All TSPs implement consumer awareness activities (starts upon filing of Consumer Awareness Programs with the CRTC and is completed on the Relief Date) | TSPs | 2017-02-24 | 2018-11-24 |
| 21 | All TSPs to notify all customers (residence, business & special customers) of the new NPA and, if applicable, of the need to transition from 7- to 10-digit local dialling (may start with the filing of Consumer Awareness Programs with the CRTC and all customers should be notified at least 18 months prior to the Relief Date) | TSPs | 2017-02-24 | 2017-05-24 |
| 22 | TSPs to submit Progress Report #1 to NITF and CATF (starts after completion date for all TSPs to notify their customers and requires 2 weeks) | TSPs | 2017-05-24 | 2017-06-07 |
| 23 | NITF and CATF develop & submit Progress Report #1 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2017-06-07 | 2017-06-21 |
| 24 | RPC submits Progress Report #1 to CRTC staff (linked to NITF and CATF reports) | RPC | 2017-06-21 | 2017-07-05 |
| 25 | CNA issues July 2017 J-NRUF results | CNA |   | 2017-09-05 |
| 26 | CNA holds RPC meetings to reach agreement on deferral of Relief Date and development of revised Relief Implementation Plan | RPC | 2017-10-25 | 2017-11-17 |
| 27 | Dispute filed with the CISC/CRTC | RPC/TSPs |   | 2017-11-29 |
| 28 | CRTC issues Telecom Decision CRTC 2018-59 approving the deferral of the Relief Date and directing the RPC to recommend an appropriate Relief Date based on the January 2018 R-NRUF results | CRTC | 2017-11-29 | 2018-02-14 |
| 29 | CNA issues January 2018 R-NRUF results | CNA |   | 2018-03-08 |
| 30 | Telecommunications Alliance issued media release to inform the media and population of the deferral of the introduction of 10 digit dialling and the new NPA in Newfoundland and Labrador. | Telecom Alliance | 2018-02-14 | 2018-02-28 |
| 31 | Telecommunications Alliance advised key stakeholders including municipalities, governements, chamber of commerce, etc. of deferral of 10-digit dialling and New NPA | TSPs, Telecom Alliance | 2018-02-14 | 2018-02-28 |
| 32 | RPC updates the PL to advise of the deferral of Relief | RPC | 2018-02-14 | 2018-03-30 |
| 33 | CNA submits PL to NANP | CNA | 2018-03-30 | 2018-04-09 |
| 34 | CNA holds RPC meetings to reach agreement on appropriate Relief Date and development of revised Relief Implementation Plan | RPC | 2018-04-25 | 2018-04-25 |
| 35 | CNA forwards revised RIP to Secretary General of CRTC | CNA | 2018-04-25 | 2018-05-16 |
| 36 | CRTC issues Telecom Decision CRTC 2018-333 approving the revised Relief Date of 20 May 2022 | CRTC | 2018-05-16 | 2019-08-30 |
| 37 | RPC updates the Planning Letter (PL) | RPC | 2018-09-06 | 2018-09-24 |
| 38 | CNA issues January 2020 R-NRUF results indicating the Projected Exhaust Date is March 2024 | CNA | 2020-03-24 | 2020-03-24 |
| 39 | CNA announces the date for RPC conference call to review contribution on revised Relief Date (27 May 2023) | CNA | 2020-05-01 | 2020-05-08 |
| 40 | CNA chairs conference call to review contributions | RPC | 2020-05-22 | 2020-05-29 |
| 41 | CNA chairs subsequent conference calls if necessary to finalize TIF report, schedule and revised RIP | CNA | 2020-05-29 | 2020-06-12 |
| 42 | CNA forwards revised RIP to CISC/CRTC | CNA | 2020-06-12 | 2020-06-26 |
| 43 | CRTC issues Telecom Decision on revised Relief Date (27 May 2023), schedule and RIP | CRTC | 2020-06-26 | 2020-10-30 |
| 44 | CNA issues July 2020 R-NRUF results indicating the Projected Exhaust Date is December 2026 | CNA | 2021-08-19 | 2021-08-19 |
| 45 | CNA forwards revised RIP to CISC/CRTC | CNA | 2020-09-30 | 2020-09-30 |
| 46 | CRTC issues Telecom Decision CRTC 2021-13 indefinitely deferring relief planning until the area code re-enters the relief planning window. | CRTC | 2021-01-18 | 2021-01-18 |
| 47 | CNA issues January 2023 G-NRUF results indicating the Projected Exhaust Date is December 2024 | CNA | 2023-03-29 | 2023-03-29 |
| 48 | CNA announces the date for RPC conference call to review contribution on revised Relief Date (27 May 2023) | CNA | 2023-04-26 | 2023-04-26 |
| 49 | CNA issues April 2023 J-NRUF results indicating the Projected Exhaust Date is March 2025 | CNA | 2023-05-04 | 2023-05-04 |
| 50 | CNA chairs subsequent conference calls if necessary to finalize TIF report, schedule and revised RIP | CNA | 2023-04-26 | 2023-05-18 |
| 51 | CNA forwards revised RIP to CISC/CRTC | CNA | 2023-05-18 | 2023-05-25 |
| 52 | CRTC issues Telecom Decision on revised Relief Date (27 May 2023), schedule and RIP | CRTC | 2023-05-25 | 2023-08-30 |
| 53 | CNA submits revised PL to NANPA (should be submitted at least 18 months prior to the Relief Date) | CNA | 2023-08-30 | 2023-09-05 |
| 54 | NANPA receives and posts revised Planning Letter to NANPA website (within 2 weeks of receipt from the CNA) | NANPA | 2023-09-05 | 2023-09-19 |
| 55 | All TSPs to develop and file any changes to individual consumer awareness programs with the CRTC (may be done collectively by Telecommunications Alliance) (starts at CRTC approval of RIP and should be completed about 24 months prior to the Relief Date) | TSPs | 2023-08-30 | 2023-09-30 |
| 56 | All TSPs to notify all customers (including residence, business & special customers) of the new overlay NPA (may start upon the filing of Consumer Awareness Programs with the CRTC) | TSPs | 2023-09-30 | 2023-11-30 |
| 57 | TSPs to submit Communications Progress Report #2 to NITF & CATF (starts after completion date for all TSPs to file their revised CAP and requires 2 weeks) | TSPs | 2023-11-30 | 2023-12-14 |
| 58 | NITF & CATF develop & submit Progress Report #2 to RPC (linked to TSP reports to CATF) | NITF & CATF | 2023-12-14 | 2024-01-11 |
| 59 | RPC submits NITF & CATF Progress Report #2 to CRTC staff (linked to CATF reports) | RPC | 2024-01-11 | 2024-01-25 |
| 60 | iconectiv TRA database updates to add Exchanges to new overlay NPA (starts on the date that the PL is posted to the NANPA web site and must be completed by 6 months prior to the Relief Date) | iconectiv TRA | 2023-08-30 | 2023-09-12 |
| 61 | Payphone Providers reprogram payphones (starts upon CRTC approval of RIP and ends on the Relief Date) | Payphone Providers | 2023-08-30 | 2024-02-17 |
| 62 | TSPs and database owners/operators to modify systems and industry databases (starts on CRTC approval of RIP and ends on the Relief Date) | TSPs & Database Owners | 2023-08-30 | 2024-02-17 |
| 63 | Operator Services & Directory Assistance Readiness (starts on CRTC approval of RIP and ends on the Relief Date) | TSPs | 2023-08-30 | 2024-02-17 |
| 64 | Directory Publisher Readiness for relief (ability to identify the NPA in telephone numbers in the directory published after the new NPA is activated) (starts upon CRTC approval of RIP and ends on the Relief Date) | Directory Publishers | 2023-08-30 | 2024-02-17 |
| 65 | 9-1-1 Systems and Databases Readiness (starts on CRTC approval of RIP and ends on the Relief Date) | PSAPS, 9‑1‑1 Service Providers & TSPs | 2023-08-30 | 2024-02-17 |
| 66 | Network Systems & Equipment Readiness (starts on CRTC approval of RIP and ends on the Relief Date) | TSPs | 2023-08-30 | 2024-02-17 |
| 67 | Service Order & Business System Readiness (starts on CRTC approval of RIP and ends on the Relief Date) | TSPs | 2023-08-30 | 2024-02-17 |
| 68 | International Gateway Switch Translations Readiness for new NPA (starts on CRTC approval of RIP and ends on the Relief Date) | Int’l TSPs | 2023-08-30 | 2024-02-17 |
| 69 | Canadian Local Number Portability Consortium (CLNPC) Database Readiness for new NPA (starts on CRTC approval of RIP and ends on the Relief Date) | CLNPC & NPAC | 2023-08-30 | 2024-02-17 |
| 70 | Toll Free SMS Database Readiness for new NPA (starts on CRTC approval of RIP and ends on the Relief Date) | Toll TSPs | 2023-08-30 | 2024-02-17 |
| 71 | TSPs apply for Test CO Codes in new NPA | TSPs | 2023-08-30 | 2023-09-12 |
| 72 | Develop Inter-Carrier Network Test Plans and prepare for testing (individual TSPs to make arrangements in accordance with interconnection agreements) (may start upon CRTC approval of RIP and must be completed by start date for the Inter-Carrier Testing Period) | NITF & TSPs | 2023-08-30 | 2023-11-17 |
| 73 | All international and domestic TSPs must activate the new NPA in their networks by the start date for the Inter-Carrier Testing Period | TSPs | 2023-08-30 | 2023-11-17 |
| 74 | Activation date for new NPA Test CO Codes and Test Numbers in network must be completed by the start date for the Inter-Carrier Testing Period) | TSPs | - | 2023-11-17 |
| 75 | Inter-Carrier Testing Period (subject to Inter-Carrier Network Test Plans) (starts about 3 months prior to the Relief Date) | NITF & TSPs | 2023-11-17 | 2024-02-17 |
| 76 | Relief Date (earliest date when CO Codes in new NPA may be activated) |   | - | 2024-02-17 |
| 77 | TSPs submit Final Progress Reports to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs | 2024-02-17 | 2024-03-02 |
| 78 | NITF and CATF develop & submit Final Progress Reports to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2024-03-02 | 2024-03-16 |
| 79 | RPC submits Final Progress Reports to CRTC staff (linked to NITF and CATF reports) | RPC | 2024-03-16 | 2024-03-30 |
| 80 | TSPs disconnect Test Codes & Numbers, and submit Part 1 form to return Test Codes (starts 1 month after Relief Date and allows 1 month for completion) | TSPs | 2024-03-17 | 2024-04-17 |
| 81 | RPC Chair submits, to the CISC, the final RPC Chair Report indicating that the NPA 709 ad hoc RPC is no longer required. | RPC Chair | 2024-03-30 | 2024-04-13 |









