NPA 249/705 Proposal for Relief of an Overlay NPA Complex (PROC)

Version 1.0 – 3 March 2021

| Canadian Numbering Administrator (CNA) Suresh Khare 613-702-0016 ext. 201 150 Isabella Street, Suite 605 Ottawa ON K1S 5H3 suresh.khare@cnac.ca |  |
| --- | --- |

TABLE OF CONTENTS

1.	INTRODUCTION	1

2.	NPA RELIEF PLANNING PROCESS	2

3.	NPA RELIEF METHODS	3

4.	NPA EXHAUST INFORMATION	3

5.	RELIEF OPTIONS	4

5.1.	Distributed Overlay	4

6.	SUMMARY OF RELIEF OPTIONS	5

7.	DIALLING CHANGES FOR LOCAL CALLS	5

8.	PROPOSED SCHEDULE	5

9.	JEOPARDY CONTINGENCY PLAN (JCP)	7

10.	SELECTION OF RELIEF NPA CODE	14

11.	RECOMMENDATIONS	15

ANNEXES	16

LIST OF ANNEXES

ANNEX A

Figure 1 – Overview Map of NPA 249/705	A-1

Figure 2 – NPA 249/705 Actual and Forecast CO Code Assignments	A-2

Figure 3 – NPA 249/705 CO Code Exhaust: January 2021 R-NRUF	A-3

Figure 4 – NPA 249/705 CO Code Exhaust: July 2020 R-NRUF	A-3

Figure 5 – Distributed Overlay	A-4

ANNEX B

Table 1 – NPA 249/683/705 Exchange Areas After Distributed Overlay	B-1

ANNEX C

Distribution List

ACRONYM LIST

| CATF | Consumer Awareness Task Force |
| --- | --- |
| CNA | Canadian Numbering Administrator |
| CISC | CRTC Interconnection Steering Committee |
| CLEC | Competitive Local Exchange Carrier |
| CLNPC | Canadian Local Number Portability Consortium |
| CO | Central Office |
| CRTC | Canadian Radio-television and Telecommunications Commission |
| CSCN | Canadian Steering Committee on Numbering |
| EAS | Extended Area Service |
| G-NRUF | General Numbering Resource Utilization Forecast |
| ILEC | Incumbent Local Exchange Carrier |
| IPD | Initial Planning Document |
| ISP | Internet Service Provider |
| JCP | Jeopardy Contingency Plan |
| J-NRUF | Jeopardy Numbering Resource Utilization Forecast |
| LEC | Local Exchange Carrier |
| LIR | Local Interconnection Region |
| LNP | Local Number Portability |
| NANP | North American Numbering Plan |
| NANPA | North American Numbering Plan Administrator |
| NITF | Network Implementation Task Force |
| NoC | Notice of Consultation |
| NPA | Numbering Plan Area (Area Code) |
| NRUF | Numbering Resource Utilization Forecast |
| PD | Planning Document |
| PED | Projected Exhaust Date |
| PL | Planning Letter |
| POI | Point of Interconnection |
| PROC | Proposal for Relief of an Overlay NPA Complex |
| PSAP | Public Safety Answering Point |
| RIP | Relief Implementation Plan |
| R-NRUF | Relief Planning Numbering Resource Utilization Forecast |
| RPC | Relief Planning Committee |
| TSP | Telecommunications Service Provider |
| WNP | Wireless Number Portability |
| WSP | Wireless Service Provider |

Proposal for Relief of an Overlay NPA Complex (PROC)

Numbering Plan Area (NPA) 249/705

Yellow highlight implies that these sections should be reviewed and updated in any planning document contribution(s).

# INTRODUCTION

Numbering Plan Areas (NPAs) 416 and 613, commonly referred to as area codes, were originally assigned to Ontario by AT&T in 1947 as two of the 86 area codes to be used in Canada and the continental United States. In 1953 NPA 519 was split from NPA 416 and NPA 613 and in 1957 NPA 705 was split from NPA 519 and NPA 613.

In 2011 new Area Code 249 was introduced in central and northeastern Ontario.

The following table provides a high-level summary of the history of area code usage in the area currently served by NPA 249/705 since 1947.

| Year | Activity |
| --- | --- |
| 1947 | Area Codes 416 and 613 are assigned to Ontario by AT&T |
| 1953 | Area Code 519 is split from 416 and 613 |
| 1957 | Area Code 705 is split from 519 and 613 |
| 2006 | 10-digit local dialling mandated to provide relief for NPA 613 |
| 2011 | New Area Code 249 overlays 705 |

NPA 249/705 consists of 203 Exchange Areas serving mainly serving central and northeastern Ontario.  Ontario, which includes the major communities of Barrie, Sudbury, Peterborough, Sault Ste. Marie, North Bay, Lindsay, Huntsville, Mattawa, Timmins and Midland.

A list of the Exchange Areas in NPA 249/705 is provided in Annex B, Table 1.

| Date | Activity |
| --- | --- |
| 3 February 2017 | In Telecom Decision CRTC 2017-38, the Commission determined that area code 683 should be set aside as a potential future relief area code for area codes 249 and 705. For the purposes of this document the new NPA will be 683. |
| 20 March 2018 | The Canadian Numbering Administrator (CNA) published the January 2018 G-NRUF results which indicated that the Projected Exhaust Date (PED) had advanced to February 2024. |
| 27 August 2018 | The CNA published the July 2018 R-NRUF results which indicated that the PED had moved out to July 2025. |
| 26 March 2019 | The CNA published the January 2019 R-NRUF results which indicated that the PED remained unchanged at July 2025. |
| 20 September 2019 | The CNA published the July 2019 R-NRUF results which indicated that the PED had moved out to March 2026. |
| 30 January 2020 | The CRTC released Telecom Notice of Consultation CRTC 2020-36 - Establishment of a CISC ad hoc committee for relief planning for area codes 249 and 705 in Ontario in which the CRTC announced the establishment of a CRTC Interconnection Steering Committee ad hoc Relief Planning Committee (RPC) to examine options and make recommendations for providing numbering relief to area codes 249 and 705 in Ontario. |
| 24 March 2020 | The CNA published the January 2020 R-NRUF results which indicated that the PED had moved out to April 2026. |
| 18 August 2020 | The CNA published the July 2020 R-NRUF results which indicated that the PED had advanced to May 2025. |
| 23 February 2021 | The CNA published the January 2021 R-NRUF results which indicated that the PED had advanced to April 2023 which puts NPA 249/705 in a Jeopardy Condition. |

This PROC is prepared by the CNA in accordance with Telecom Notice of Consultation CRTC 2020-36 and the Canadian NPA Relief Planning Guideline, Version 7.0 dated 29 January 2019 (the Guideline). A copy of the Guideline is available from the Canadian Radio-Television and Telecommunications Commission (CRTC), CRTC Interconnection Steering Committee (CISC), Canadian Steering Committee on Numbering (CSCN) guidelines web page at: https://crtc.gc.ca/cisc/eng/cisf3fg.htm.

The objective of the NPA Relief Planning process is to ensure that CO Codes and telephone numbers are always available for use by TSPs and their customers in the geographic area requiring relief.

It is very important to closely monitor the CO Code requirements of all existing and prospective CO Code Holders so that relief can be timed to ensure that CO Codes and telephone numbers are always available for service providers and customers.

In this PROC, a single option is identified for providing NPA relief in the NPA 249/705 geographic area. Given the magnitude of this undertaking, intercompany commitment and co-operation are essential throughout the planning, provisioning and implementation stages of the introduction of a new NPA.

# NPA RELIEF PLANNING PROCESS

The NPA Relief Planning process and the roles of the participants (i.e., CRTC, CNA, CISC, Relief Planning Committee (RPC) participants and Interested Parties) for NPA Relief Planning are identified in the Guideline.

To increase public awareness and participation in the NPA Relief Planning process, the CRTC has determined that NPA RPCs will be established as ad hoc committees of the CISC. Generally, a separate ad hoc committee is created to deal with relief in each area code. The CNA, in its function as NPA Relief Planning Coordinator, acts as chair of these ad hoc committees. Meetings and conference calls of the ad hoc NPA RPCs are all open to public participation and are conducted in accordance with the CISC Administrative Guidelines which are available from the CRTC website at: http://www.crtc.gc.ca/cisc/eng/cag.htm.

NPA Relief Planning is conducted under the regulatory oversight of the CRTC. Notwithstanding the process detailed in the Guideline, the CRTC may exercise its authority under the Telecommunications Act to alter this process at any time. The CRTC has the authority under the Telecommunications Act to review, modify and give final approval to the Planning Document (PD) and the Relief Implementation Plan (RIP) developed and submitted by the RPC to the CRTC via the CISC process.

Section 7.1.6 of the Canadian NPA Relief Planning Guideline requires the CNA to create and maintain a distribution list of parties who may be interested in participating in the RPC and to provide them with advance notice of the initial RPC meeting and the release of a PROC.

Any person wishing to participate in the NPA Relief Planning process can contact the CNA and request to be added to the RPC distribution list. More information about how to participate in CRTC public processes is available at: http://www.crtc.gc.ca/eng/info_sht/g4.htm.

A summary of Canadian geographic area code relief history is available at: http://www.cnac.ca/npa_codes/NPA_History.pdf.

# NPA RELIEF METHODS

The purpose of this section is to identify and briefly describe NPA Relief Methods.

The Guideline states that: “The only NPA Relief Method considered in Canada is the Distributed Overlay Method which superimposes or “overlays” a Relief NPA on top of an entire existing NPA or NPAs.” There are three types of Distributed Overlay:

- a Distributed Overlay over an existing geographic area served by a single existing NPA (A new NPA is overlaid over a single existing NPA (i.e., the geographic area) that is served by a single NPA.);

- a Distributed Overlay over an existing geographic area served by multiple existing overlay NPAs (A new NPA is overlaid over a single existing NPA (i.e., the geographic area) that is served by multiple existing overlay NPAs); and,

- a Distributed Overlay over multiple existing geographic areas, each served by one or more existing NPAs (A new NPA is overlaid over multiple existing NPAs (i.e., different geographic areas served by multiple NPAs. This type of overlay may be considered for NPA relief for two or more adjacent NPAs (i.e., geographic areas) within a province.).

# NPA EXHAUST INFORMATION

As indicated in the following table, NRUFs for NPA 249/705 were used to determine PEDs, i.e. the dates when CO Codes in NPA 249/705 would be expected to exhaust.

| NRUF | Projected Exhaust Date (PED) |
| --- | --- |
| G-NRUF January 2018 | February 2024 |
| R-NRUF July 2018 | July 2025 |
| R-NRUF January 2019 | July 2025 |
| R-NRUF July 2019 | March 2026 |
| R-NRUF January 2020 | April 2026 |
| R-NRUF July 2020 | May 2025 |
| R-NRUF January 2021 | April 2023 |

Refer to, Figures 2 through 4 for graphs of forecast CO Code demand from current and prospective CO Code Holders and charts of Administrative Codes set aside in area code 249/705 for the two most recent NRUFs (January 2021 and July 2020 ).

# RELIEF OPTIONS

The Relief Option as identified and examined in this PROC is a Distributed Overlay over an existing geographic area served by multiple existing overlay NPAs.

Using this method, a new NPA is overlaid over an existing NPA (i.e., the geographic area). In this case the new NPA 683 will be overlaid over the geographic area currently served by NPA 249/705.

The Relief Option identified above was evaluated using the following assumptions:

- The Five-Year Historical growth values of 68 CO Codes was used to identify the subsequent PED for this Relief Option by comparing the January 2021 R-NRUF data in the table below:

| Statistical Method | Data | Period | Quantity of CO Codes |
| --- | --- | --- | --- |
| median | forecast growth | next six years | 152 |
| average | forecast growth | five-year period (January 2022 until January 2027) | 137 |
| average | forecast growth | next six years | 144 |
| average | historical growth | past five years | 68 |
| median | historical growth | past five years | 71 |

- The Relief Date for the Distributed Overlay will be Q2 2022 (approximately 9 months prior to the NPA 249/705 PED of April 2023 identified using the January 2021 R-NRUF results).

See Annex A, Figure 5 for diagram of the Distributed Overlay Relief Option identified by the CNA.

## Distributed Overlay

One Distributed Overlay Relief Option was evaluated which would overlay the NPA 683 over the 132 Exchange Areas comprising the NPA 249/705 area. See Annex A, Figure 5.

The introduction of a Distributed Overlay would keep the same number of NPA Relief Planning areas in Ontario.

After this Distributed Overlay, CO Codes in NPA 249/683/705 would be expected to exhaust in Q2 2031.

# SUMMARY OF RELIEF OPTIONS

| Relief Option | Projected Exhaust Dates |  | Subsequent Relief Dates |
| --- | --- | --- | --- |
|  | NPA 249/705 | NPA 24/683/705 |  |
| Distributed Overlay | April 2023 | April 2031 | April 2030 |

Note: For a Distributed Overlay NPA 683 would be in service in Q2 2022.

# DIALLING CHANGES FOR LOCAL CALLS

Currently 10-digit dialling is mandatory for local calls originating within area code NPA 249/705 and all neighbouring NPAs (i.e., NPA 226/519/548, NPA 289/365/905, NPA 343/613, NPA 807 and NPA 819/873). Local dialling plans will not change with this relief.

# PROPOSED SCHEDULE

The CNA submits the following schedule for NPA 249/705 relief based on the recommendations contained in this PROC and the current PED of April 2023. The RPC will monitor the PED, and if it changes significantly in the future, the RPC will assess the situation and, if necessary, submit recommendations including a revised schedule to the CRTC for consideration and approval.

RELIEF IMPLEMENTATION SCHEDULE

For a Distributed Overlay of NPA 683 over NPA 249/683/705

[Insert proposed schedule from Excel worksheet]

# JEOPARDY CONTINGENCY PLAN (JCP)

The CNA has provided the template below to assist the RPC with the development of the Jeopardy Contingency Plan (JCP).

The RPC has developed the following JCP for inclusion in the PD for NPA 249/705. This JCP is based on the example contained in Appendix F to the Canadian NPA Relief Planning Guideline.

This JCP shall remain in effect until superseded by a CRTC-approved JCP, the Jeopardy Condition is suspended or 66 days prior to the Relief Date.

The following measures shall be implemented in NPA 249/705 while a Jeopardy Condition is in effect.

During a Jeopardy Condition, CO Code Applicants shall submit all CO Code applications and related correspondence for the Jeopardy NPA to CRTC staff in addition to the CNA. The CNA shall only assign CO Codes from the exhausting NPA to a CO Code Applicant when instructed by CRTC staff.

- Carriers and/or Telecommunications Service Providers (TSPs):

  - shall age disconnected residential wireline telephone numbers for a maximum of two months;

  - shall age disconnected wireless telephone numbers for a maximum of three months;

  - shall age disconnected business wireline telephone numbers for a maximum of six months. Under special circumstances, the six month aging limit for business telephone numbers may be extended to twelve months, if required, to accommodate local directory publishing dates for high volume call-in applications (e.g., heavily advertised local business numbers such as radio talk shows, food ordering services, ticket sales, chat lines), or for numbers associated with public service emergency applications or for numbers advertised in directories for which customers have requested reference of calls;

  - shall return all CO Codes that are not being used, nor intended to be used to directly serve customers to the assignment pool within two months (e.g., plant test codes);

  - should work towards, and encourage existing customers, to either activate or return the reserved numbers to bring the reserved quantity down to a maximum of 10% of the quantity of numbers In-Service for that customer;

  - shall not allow the quantity of reserved numbers to be increased by new reservation requests by existing customers to more than 10% of the quantity of numbers in service for that customer. In the case of new customers, number reservations shall be limited to 10% of the total quantity of telephone numbers being placed into service for that customer;

  - shall, within 45 days from the date that the CNA declares a Jeopardy Condition submit a Part 1 Form for each remaining reserved CO Code either returning the reserved CO Code to the CNA or requesting assignment of the reserved CO Code. Once the 45-day period has elapsed, the CNA shall make available for general assignment all CO Codes that are still reserved and have not been applied for as assignments on a Part 1 Form received by the CNA. Within 60 days from the date that the CNA declares a Jeopardy Condition, the CNA shall report to CRTC staff and the RPC as to how many of these codes have been assigned or made available for general assignment;

  - shall not be permitted to obtain a new CO Code reservation;

  - shall place all CO Codes assigned prior to the Jeopardy Condition being declared In-Service within three months of the effective date for CO Code activation in the network, or within three months of the date that the Jeopardy Condition was declared. If the CO Code is an Initial Code and the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-Service date has been delayed beyond the applicable timeframe, then the CNA may grant an extension of up to two months to the In-Service date. The CNA shall initiate reclamation procedures for all CO Codes that have not been placed In-Service within these timeframes unless CRTC staff provides a further extension.

- For new applications for Initial Codes, each CO Code Holder shall certify that the CO Code will be activated in the network and placed In-Service within four months of the date of application for the Code. If the CNA does not receive a Part 4 Form within this timeframe, confirming that the CO Code has been placed In-Service, the CNA will initiate reclamation measures. If the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-Service date has been delayed not more than six months from the original application date, then the CNA may grant an extension to the In-Service date, so long as the In-Service date is not more than six months beyond the original application date. If the In-Service date has been delayed more than six months from the original application date, then the CNA shall reclaim the Code unless CRTC staff provides a further extension.

- When applying for an Additional Code for Growth, a CO Code Holder who is submitting a Part 1 Form and Appendix B worksheet shall also submit a completed Supplementary Form for a Growth CO Code Application (attached) which certifies and/or provides the following information for the specific switching entity/POI and Exchange Area when the Growth CO Code is being requested in a Jeopardy Condition:

  - certification that all held telephone numbers have been released;

  - certification that reserved numbers do not exceed ten percent of the total quantity of numbers as defined in Appendix G of the Canadian CO Code (NXX) Assignment Guideline;

  - certification that each reseller/dealer had been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two times the highest quantity of customer numbers assigned in any month during the previous 12 months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three months' inventory;

  - confirmation that the Part 1 form submitted with the application has the Jeopardy Condition box in section 1.6 checked to certify that the existing CO Codes are projected to exhaust within 4 months of the date of application and that the months-to-exhaust is documented on an Appendix B submitted to the CNA;

  - a completed Telephone Number Utilization Report for the applicable switching entity signed by both a company officer and the company’s authorized representative;

  - confirmation that the requested Growth CO Code was forecasted in the most recent NRUF or an explanation as to why it was not is attached; and,

  - confirmation that the requested Growth CO Code will be placed In-Service within four months of the date of assignment.

- Any CO Codes for growth assigned after the implementation of this JCP must be activated in the network and placed In-Service within four months of assignment. In the event that a CO Code Holder is unable to place the CO Code In-Service within four months of the date of assignment, the CO Code Holder must return the assigned CO Codes or submit a written request for extension to the CNA. Such written requests must include documentation explaining the reason(s) for the missed date and proposing the new In-Service date. If the explanation includes reasons beyond the control of the CO Code Holder, the CNA may extend the In-Service date a maximum of one month. If the CO Code Holder does not place the CO Code In-Service within the one-month extension, the CNA shall initiate the reclamation process at the end of the one-month extension unless CRTC staff provides a further extension.

- A Carrier that has multiple switching entities within an Exchange Area shall examine the possibility of, and implement where feasible, number sharing between those switches as a potential method to delay requirements for additional CO Codes.

- The CNA will request two versions (two separate worksheets (Form 1 and Form 2)) of the J-NRUF input from all current and prospective CO Code Holders quarterly until three (3) months before relief is provided.

  - The forecast quantities in Form 1 should be the same as or lower than the last R-NRUF input submitted, prior to declaration of a Jeopardy Condition. CO Code Holder forecasts may reflect an increase in demand in the period subsequent to the Relief Date.

  - Form 2 will reflect the actual demand required by the CO Code Holder's current business plan and will be provided for information purposes only.

- The CNA will compare the initial J-NRUF input to the recent NRUF inputs, to assess forecasting trends. The CNA shall monitor all inputs and shall test them for reasonableness in consultation with the Carrier. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the deviations, then the matter will be referred to the CRTC staff.

- The CNA will request subsequent J-NRUF input from all current and prospective CO Code Holders quarterly until 3 months before relief is provided. If one or more R-NRUFs have already been conducted, and depending on the severity of the Jeopardy Condition, the CNA may defer a J-NRUF by up to two months if such a deferral brings the timing of that J-NRUF and subsequent J-NRUFs into alignment with other NRUFs that are conducted at 12, 6 or 3 month intervals. Subsequent J-NRUF input will be compared with the initial J-NRUF input to evaluate the effectiveness of the JCP. The CNA shall monitor all J-NRUF inputs and shall test them for reasonableness in consultation with the Telecommunications Service Providers. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the changed forecasts, then the matter will be referred to CRTC staff.

- A CO Code Applicant must have submitted a completed J-NRUF to the CNA before the CNA may assign a CO Code to that CO Code Applicant.

- If a CO Code applicant wishes to request more CO Codes than it identified in its most recent J NRUF, the CO Code Applicant should discuss the matter with the CNA. If the CO Code Applicant wishes to proceed with the request, the CO Code Applicant will forward the request and revised forecast to CRTC staff and the CNA for consideration.

- The CO Codes identified in the NPA CO Code Inventory Chart as “Assignable CO Codes in a Jeopardy Condition” will be assigned in the order determined by the RPC after all CO Codes which are “Available for Assignment as of [day month year] have been assigned.

- After each J-NRUF, the CNA shall provide CRTC staff, the RPC and CSCN participants with a report providing an updated NPA CO Code Inventory Chart for the NPA in jeopardy as well as the aggregate results of the most recent J-NRUF.

- Exceptional issues or concerns may be referred by the CNA, or by individual entities (with a courtesy copy to the CNA), to the CRTC staff for resolution.

- In a situation where the Relief Date is on or after the PED, the quantity of CO Codes that may be assigned to a CO Code Applicant prior to the end of the Jeopardy Condition (i.e. 66 days prior to the Relief Date) shall be limited to the quantity forecasted by the CO Code Applicant in its most recent NRUF forecast submitted prior to the Jeopardy Condition being declared by the CNA (if no previous NRUF was submitted, then the previous forecast will be deemed to be zero codes). When making requests to obtain CO Codes prior to the end of the Jeopardy Condition (i.e. 66 days prior to the Relief Date), the CO Code Applicant may change the Exchange Area or the month when the CO Code assignment is required, provided a new J-NRUF and explanation accompanies the application. The control imposed by this option may be relaxed if subsequent J-NRUFs defer the PED to after the Relief Date. CO Codes that become available for assignment due to future reduced demand from other current and prospective CO Code Holders may be assigned at the discretion of CRTC staff.

- If the CNA determines that the implementation of the JCP has not extended the Projected Exhaust Date of the NPA beyond the Relief Date, the CNA will consult with CRTC staff and further CO Code conservation and assignment procedures may be ordered by the Commission (e.g., rationing, lottery, etc.).

.

Supplementary form for a Growth CO Code Application – Page 1 of 2 – Telephone Number Utilization Report

This form is required with each request for an Additional Code for Growth in an NPA where a Jeopardy Condition is in effect. It should be submitted to the CNA together with the Part 1 and Appendix B forms that are required for an application for an Additional Code for Growth. See the Part 1 form for information on how and where to submit the form.

I hereby certify that the following information is true and accurate to the best of my knowledge and has been prepared in accordance with Special Conservation Procedures for a Jeopardy Condition contained in the Canadian NPA Relief Planning Guideline or the applicable approved Jeopardy Contingency Plan.

Name & Signature of Authorized Representative of Code Holder	Title	Date

Name & Signature of Company Officer (see item 3 of this JCP)	Title	Date

Contact information:	Entity Name: 	__________________	Contact Name:	_____________

Address: 	__________________	City, Province, Postal Code:	_____________

Telephone: 	__________________	Facsimile:	_____________

E-mail: 	__________________

Switch Identification (Switching Entity/POI) CLLI: _______________ 	Exchange Area: ________________

For the above Switch Identification and Exchange Area for which a Growth CO Code is requested:

I certify that all held telephone numbers have been released

I certify the total quantity of reserved numbers does not exceed ten percent (10%) of the total quantity of telephone numbers as defined in Appendix G of the Canadian CO Code (NXX) Assignment Guideline

I certify that each reseller/dealer has been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two (2) times the highest quantity of customer numbers assigned in any month during the previous twelve (12) months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three months' inventory.

The Part 1 form submitted with the application has the Jeopardy Condition box in section 6 checked (this certifies that the existing CO Codes are projected to exhaust within four (4) months of the date of the application or within the period specified in an approved Jeopardy Contingency Plan, and that the months-to-exhaust is documented on an Appendix B submitted to the CNA).

The Telephone Number Utilization Report on page 2 of this form has been completed.

The requested Growth CO Code was forecasted in the most recent NRUF, or an explanation as to why it was not is attached.

The requested Growth CO Code will be placed In-Service within four (4) months of the date of assignment.

Supplementary Form for a Growth CO Code Application – Page 2 of 2 – Telephone Number Utilization Report

Use Arial 9 to complete this form. (Note: If the spreadsheet below does not show on your display, please change the Work view to "Print Layout" or "Reading Layout")

Remarks: _______________________________________________________________________________

________________________________________________________________________________________

NPA 249/705 CO Code Inventory Chart

The following chart and the instructions it contains will apply in NPA 249/705 in a Jeopardy Condition.

The chart below lists quantities of CO Codes unassignable prior to a Jeopardy Condition, CO Codes that become assignable in a Jeopardy Condition and CO Codes in NPA 249/705 assigned and In-service as of 5 March 2021. The CO Codes that become assignable in a Jeopardy Condition shall only be made available for assignment when all other available CO Codes have been assigned in the order listed below.

|  |  | Quantity |
| --- | --- | --- |
| A | Total CO Codes in NPAs 249/705 (NXX format) | 1,600 |
| B | CO Codes unassignable prior to a Jeopardy Condition |  |
|  | N11 Service Codes (211, 311, 411, 511, 611, 711, 811, 911) | 16 |
|  | Special Use Codes (555, 950 & 976) | 5 |
|  | Home NPA Codes (249, 705) | 4 |
|  | Current Neighbouring NPA Codes (226, 343, 519, 548, 613, 807, 819, 873) | 16 |
|  | Future Geographic NPA Codes (460, 468, 537, 584, 683, 851, 871) (Note 1) | 14 |
|  | Plant Test Codes (958 & 959) | 4 |
|  | Special 7-digit Dialling Codes (310, 610 & 810) | 5 |
|  | Stranded Codes (705/265 & 705/490) | 2 |
|  | Total B | 66 |
| C | CO Codes assignable prior to a Jeopardy Condition (C=A-B) | 1,534 |
| D | CO Codes unassignable prior to a Jeopardy Condition that become assignable in a Jeopardy Condition: |  |
|  | Future Canadian Geographic NPA Codes (Notes 1 & 2) | 12 |
|  | Current Neighbouring NPA Codes (226, 343, 519, 548, 613, 807, 819, 873) (Note 3) | 16 |
|  | Total D | 28 |
| E | Assignable CO Codes in a Jeopardy Condition (E=C+D) | 1,534 |
| F | Assigned CO Codes as of 5 March 2021 | 1154 |
| G | Net CO Codes available for assignment as of 5 March 2021 without a Jeopardy Condition (G=C-F) | 381 |
| H | Net CO Codes available for assignment as of 5 March 2021 in a Jeopardy Condition (H=E-F) | 309 |

Notes:

- In Telecom Decision CRTC 2017-38, the Commission determined that area code 683 should be set aside as a potential future relief area code for area codes 343 and 613.

- CO Codes 460, 468, 537, 584, 851 and 871should become assignable in a Jeopardy Condition.

- In an extreme Jeopardy Condition (i.e., when the Projected Exhaust Date is earlier than the Relief Date), the current Neighbouring NPA Codes 226, 343, 519, 548, 613, 807, 819 and 873, could be assignable with CRTC staff approval.

# SELECTION OF RELIEF NPA CODE

In the event that the recommended relief option requires a new NPA Code, the criteria for selection of an appropriate area code for relief is addressed in section 4.10 of the Canadian NPA Relief Planning Guideline. The criteria that should be taken into account when Future Canadian Geographic NPAs are being considered as candidates for relief of a specific current Canadian Geographic NPA include the following:

- The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in the area that is being relieved (Home NPA(s)).

- The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in another NPA within the same province where there is a possibility that a single new NPA Code could be overlaid on more than one NPA within the province, or where boundary realignment could occur that affects another NPA.

- The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in an Exchange Area in a neighbouring NPA, if the neighbouring NPA has 7-digit local calling within the NPA and i) the Exchange Area in the neighbouring NPA where the CO Code is assigned has local calling to the NPA being relieved or ii) the Exchange Area in the neighbouring NPA where the CO Code is assigned does not have local calling to the NPA being relieved, but other Exchange Areas within that neighbouring NPA have 7-digit local calling to the Exchange Area where the CO Code is assigned as well as local calling to the new NPA.

CO Codes corresponding to Future Canadian Geographic NPA Codes which are not assigned in NPA 249/705 and therefore meet criterion a) above are 460, 468, 537, 584, 683, 851 and 871.

Section 5 of the Canadian NPA Relief Planning Guideline says “[the] only Relief Method that should be included in the IPD and PD is the Distributed Overlay Relief Method which includes three types of overlays that may be identified and assessed.” Accordingly, criterion b) does not apply.

CO Codes 468, 537, 584 and 683 are all assigned in NPA 807 but none are assigned in Exchange Areas with local dialling to NPA 249/705.

CO Codes 460, 851 and 871 are not assigned in NPA 807 which has 7-digit local dialling to NPA 249/705. These Future NPAs meet criterion c) and could be considered for relief of NPA 249/705.

The NPA Code Selection Tool located on the CNA web site at http://www.cnac.ca/npa_codes/relief/NPA_Selection_Tool.xlsx can assist in selecting a relief NPA Code from the pool of NPA Codes reserved for relief of geographic Canadian NPAs. The following table, extracted from the NPA Code Selection Tool, shows all CO Codes corresponding to Future Canadian Geographic NPA Codes that are designated as unassignable CO Codes in the Home NPA, and therefore are preferred candidates when selecting a relief NPA Code for NPA 249/705.

| NXX corresponding to Future NPA | 460 | 468 | 537 | 683 | 851 | 871 |
| --- | --- | --- | --- | --- | --- | --- |
| Distributed Overlay |  |  |  |  |  |  |

Indicates that corresponding CO Code is designated as unassignable in Home NPA(s)

All of these Future NPA Codes (460, 468, 537, 584, 683, 851 and 871) are suitable as a new NPA Code for the relief of NPA 249/705, unless analysis of potential future code reservations for NPA reliefs in other areas of Canada, or TSP cost considerations indicate a preference for one code over another for the relief of NPA 249/705.

In Telecom Decision CRTC 2017-38, the Commission determined that area code 683 should be set aside as a potential future relief of Eastern NPA complex 249/705 but could be used elsewhere if required based on a recommendation by the CSCN.

# RECOMMENDATIONS

The CNA recommends:

- The Relief Method should be a distributed overlay of a new NPA Code on Eastern Ontario NPA 249/705;

- The Relief NPA Code for NPA 249/705 should be NPA 683 as per Telecom Decision CRTC 2017-38; and

- The Relief Date should be 18 June 2022 to provide Carriers and customers with advanced notification and sufficient lead-time to implement relief in NPA 249/705.

ANNEXES

Proposal for Relief of an Overlay NPA Complex (PROC)

Numbering Plan Area (NPA) 249/705

- Maps and Figures

Maps and Figures

Figure 1 – Overview Map of NPA 249/705

Figure 2 – NPA 249/705 Actual and Forecast CO Code Assignments

Figure 3 – NPA 249/705 CO Code Exhaust: January 2021 R-NRUF

Figure 4 – NPA 249/705 CO Code Exhaust: July 2020 R-NRUF

Figure 5 – Distributed Overlay

NPA 249/683/705 Exchange Areas

Table 1 – NPA 249/683/705 Exchange Areas After Distributed Overlay

NPA 249/683/705 Exchange Areas

Abitibi Canyon

Alban

Algoma Mills

Algonquin Park

Alliston

Apsley

Attawapiskat

Azilda

Bailieboro

Bala

Barrie

Batchawana Bay

Baysville

Beaverton

Bethany

Biscotasing

Blezard Valley

Blind River

Bluewater

Bobcaygeon

Bonfield

Borden-Angus

Bracebridge

Brechin

Bridgenorth

Britt

Bruce Mines

Buckhorn

Burk's Falls

Burleigh Falls

Callander

Calstock

Cambray

Cameron

Campbellford

Cannington

Capreol

Carnarvon

Cartier

Cavan

Chapleau

Chelmsford

Christian Island

Chub Lake

Cobalt

Coboconk

Cochrane

Coldwater

Collingwood

Coniston

Connaught

Cookstown

Creemore

Desbarats

Deux Rivieres

Dokis

Dorset

Dubreuilville

Dunsford

Dwight

Earlton

Echo Bay

Elk Lake

Elliot Lake

Elmvale

Emsdale

Englehart

Espanola

Estaire

Fauquier

Fenelon Falls

Field

Foleyet

Fort Albany

Garson

Gogama

Gooderham

Gore Bay

Goulais

Gowganda

Gravenhurst

Haileybury

Haliburton

Hanmer

Hastings

Havelock

Hawk Junction

Hearst

Honey Harbour

Huntsville

Iron Bridge

Iroquois Falls AP

Iroquois Falls NT

Kamiskotia

Kapuskasing

Kashechewan

Keene

Killarney

Kinmount

Kirkfield

Kirkland Lake

Lafontaine

Lakefield

Larder Lake

Latchford

Lefroy

Levack

Lindsay

Little Britain

Little Current

Lively

Mactier

Magnetawan

Manitowaning/Wikwemikong

Markstay

Marten River

Massey

Matachewan

Matheson

Mattawa

Mattice

McKellar

Midland

Milford Bay

Millbrook

Mindemoya

Minden

Missanabie

Moonbeam

Moonstone

Moose Factory

Moosonee

Nephton

New Liskeard

Nobel

Noelville

North Bay

Norwood

Oakwood

Oba

Omemee

Opasatika

Ophir

Orillia

Oro

Otter Lake

Parry Sound

Peawanuck

Pefferlaw

Penetanguishene

Peterborough

Pineal Lake

Pointe Au Baril

Port Carling

Port Loring

Port McNicoll

Port Sydney

Powassan

Ramore

Ramsay

Redbridge

Restoule

Rosseau

Sault Ste. Marie

Searchmont

Sebright

Severn Bridge

Silverwater

Smooth Rock Falls

South Porcupine

South River

Spanish

Sprucedale

St. Charles

St. Joseph Island

Stayner

Stroud

Sturgeon Falls

Sudbury

Sultan

Sunderland

Sundridge

Swastika

Temagami

Thessalon

Thorne

Timmins

Trout Creek

Udora

Verner

Virginiatown

Warkworth

Warren

Wasaga Beach

Waubaushene

Wawa

West Guilford

Westree

Whitefish

Whitefish Falls

Wilberforce

Windermere

Woodville

Distribution List

| Doug Birdwise Interested Party 109 Westpark Drive Ottawa, ON Canada K1B 3G4 Telephone: 613-830-0081 douglas.birdwise@sympatico.ca | Nicola McLaughlin Team Lead Allstream 200 Wellington St W. F12 Toronto, ON Canada M5V 3G2 Telephone: 416-640-5271 Nicola.mclaughlin@allstream.com |
| --- | --- |
| Catherine O’Grady Senior Manager, Provisioning Allstream 200 Wellington St W. F12 Toronto, ON Canada M5V 3G2 Telephone: 416-644-9703 catherine.ogrady@allstream.com | NXX Admin Bell Canada nxx.admin@bell.ca |
| Diane Faillant Associate - Network Management/NSS (National Numbering Solution) Bell Canada 671 LAGAUCHETIERE Ouest. 11 Montreal, QC Canada H3B 2M8 Telephone: 514-870-6044 Fax: 514-786-9062 diane.faillant@bell.ca | Marie-Christine Hudon Network Provisioning Bell Canada 671 Rue De La Gauchetière, O.11 Montreal, QC H3B 2M8 Telephone: 514-870-7839 m-christine.hudon@bell.ca |
| Wanda Marie Mali Manager - National Numbering Solutions Bell Canada 100 Borough Dr, Floor 5 Blue Scarborough, ON M1P4W2 Telephone: 416-296-6076 Fax: 416-296-0685 wanda_marie.mali@bell.ca | Daniel Morrison Specialist - Voice Network Services Bell Canada 100 Dundas St Flr 3 London, ON Canada N6A 5B6 Telephone: 519-850-6386 daniel.morrison@bell.ca |
| Leo Santoro Network Analyst Bell Mobility 5115 Creekbank Rd, Floor 3 Mississauga, ON Canada L4W 5R1 Telephone: 905-282-3021 Fax: 905-282-3106 leo.santoro@bell.ca | Pierre Guynot de Boismenu Manager of Core Network Engineering and Operations, Wireless Bragg Communications Inc 60800 Young St 6th Floor Halifax, NS Canada B3K 5L2 Telephone: 902-414-8020 Fax: 902-444-1019 pierre.guynotdeboismenu@corp.eastlink.ca |
| Marian Hearn Project Executive Canadian LNP Consortium Inc. 350 Palladium Drive, Suite 208 Kanata, ON Canada K2V 1A8 Telephone: 613-287-0225 Fax: 800-406-9250 marian.hearn@clnpc.ca | Rodger McNabb Manager Contracts and Receivables Canadian LNP Consortium Inc. 350 Palladium Drive. Suite 208 Kanata, ON Canada K2V 1A8 Telephone: 613-287-0226 rodger.mcnabb@clnpc.ca |
| Pavel Bigarov CNA System Administrator Canadian Numbering Administrator 150 Isabella Street - Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 pavel.bigarov@cnac.ca | Fiona Clegg Numbering Resource Administration Canadian Numbering Administrator 150 Isabella Street, Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext. 202 fiona.clegg@cnac.ca |
| David Comrie Numbering Resource Administration Canadian Numbering Administrator 150 Isabella Street, Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext. 204 david.comrie@cnac.ca | Suresh Khare CO Code Manager Canadian Numbering Administrator 150 Isabella Street, Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext. 201 suresh.khare@cnac.ca |
| Natalie Lessard Numbering Resource Administration Canadian Numbering Administrator 150 Isabella Street, Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext. 203 natalie.lessard@cnac.ca | Kelly T. Walsh CNA Program Manager Canadian Numbering Administrator 150 Isabella Street - Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext 205 kelly.walsh@cnac.ca |
| Bill Mason Manager, Numbering Administration Canadian Radio-television and Telecommunications Commission Central Building Les Terrasses de la Chaudière 1 Promenade du Portage Gatineau, QC Canada K1A 0N2 Telephone: 819-953-8882 Fax: 819-953-0795 bill.mason@crtc.gc.ca | Lynne Hewitson Membership Manager Canadian Security Association (CANASA) 610 Alden Road Markham, ON Canada L3R 9Z1 Telephone: 905-513-0622 ext 223 Fax: 905-513-0624 membership@canasa.org |
| Eric Smith Vice President, Regulatory Affairs Canadian Wireless Telecommunications Association (CWTA) 80 Elgin Street, Suite 30 Ottawa, ON Canada K1P 6R2 Telephone: 613-233-5884 Ext. 255 Fax: 613-233-2032 documentcontrol@cwta.ca | Ofir Smadja President COMsolve 3601 Highway 7 East, Suite 400 Markham, ON Canada L3R 0M3 Telephone: 416-915-5008 info@comsolveinc.com |
| Edward Antecol VP Professional Services COMsolve Inc. 70 East Beaver Creek Road, #202 Richmond Hill, ON Canada L4B 3B2 Telephone: 416-915-5008 x106 edward.antecol@comsolveinc.com | CLEC Admin Comwave Networks 61 Wildcat Road Toronto, ON Canada M3J 2P5 clecteam@comwave.net |
| Ron Barzakay CTO Comwave Networks 61 Wildcat Rd Toronto, ON M3J 2P5 Telephone: 416-663-9700 X 302 Fax: 416-736-3150 rbarzakay@comwave.net | Sundar Nagulan Team Lead - Voice Engineering Comwave Networks 61 Wildcat Rd Toronto, ON M3J 2P5 Telephone: 647-427-8363 snagulan@comwave.net |
| Numbering E-Mail Distributel Communications Limited 177 Nepean Street Ottawa, ON Canada K2P 0B4 numbering@distributel.ca | Geoff Batstone V.P., General Counsel Distributel Communications Limited 177 Nepean Street, Suite 300 Ottawa, ON Canada Telephone: 613-319-9964 geoff.batstone@distributel.ca |
| Don Cavanagh VP Distributel Communications Limited 177 Nepean Street, Suite 300 Ottawa, ON Canada K2P 0B4 Telephone: 613-237-7005 Fax: 613-237-7009 donald.cavanagh@distributel.ca | Kim Brown Carrier Services Manager Eastlink PO Box 8660, Station “A”: 6080 Young St, 7th Floor Halifax, NS Canada B3K 5M3 Telephone: 902-446-3794 Fax: 902-405-3426 kim.brown@corp.eastlink.ca |
| Kathleen Turnsek ExaTEL 222 McIntrye Street West, Suite 505 North Bay, ON Canada P1B 2Y9 Telephone: 705-474-3364 Fax: 705-472-9202 kturnsek@vianet.ca | Jesse Gasteiger ExaTEL Inc 128 Larch St., Suite 301 Sudbury, ON Canada P3E5J8 Telephone: 705-675-0400 Fax: 705-675-0404 jesse@vianet.ca |
| Larry Hishon Senior Network Engineer Fibernetics Corporation 605 Boxwood Drive Cambridge, ON Canada N3E 1A5 Telephone: 519-571-7433 Fax: 519-772-5014 lhishon@fibernetics.ca | Rick Schleihauf VP – Regulatory Affairs and Carrier Relations Fibernetics Corporation 605 Boxwood Drive Cambridge, ON Canada N3E 1A5 Telephone: 519-489-6700 ext 629 Fax: 519-653-7686 rschleihauf@corp.fibernetics.ca |
| Tim Calamari Director, Telecom and System Services Globalstar 300 Holiday Square Blvd Covington, LA USA 70433 Telephone: 985-335-1583 Tim.Calamari@globalstar.com | Angel Loyacano Telecom Analyst Globalstar 300 Holiday Square Blvd Covington, LA USA 70433 Telephone: 985-335-1663 Angel.Loyacano@globalstar.com |
| Mark Rowed Voice Engineer II Globalstar Suite 348 14-900 Village Lane Okotoks, AB Canada T1S1Z6 Telephone: 985-335-1607 Mark.Rowed@globalstar.com | James Mandala General Manager Globalstar Canada Satellite Co. 115 Matheson Blvd. West - Suite 100 Mississauga, ON Canada L5R 3L1 Telephone: 905-712-7715 jmandala@globalstar.ca |
| Praba Gunam President/CEO InnSysVoice Corp. 4500 Sheppard Ave E, Suite 111 Toronto, ON Canada M1S 3R6 Telephone: 416-800-0797 praba@innsys.ca | Deirdre Massiah-Gomes Interested Party Canada Telephone: 416-684-3070 Massiahgomesdeirdre@gmail.com |
| Iristel team.regulatory@iristel.com | Michelle Preda Regulatory Affairs Manager Iristel 675 Cochrane Dr Markham, ON L3R0B8 Telephone: 416-800-0032 mpreda@iristel.ro |
| Iristel Inc. 11 Bowan Court Toronto, ON Canada M2K 3A8 didorders@iristel.com | Andreea Badea Iristel Inc. 11 Bowan Court Toronto, ON Canada M2K 3A8 Telephone: 416-800-4747 abadea@iristel.ro |
| Samer Bishay CEO Iristel Inc. 11 Bowan Court Toronto, ON Canada M2K 3A8 Telephone: 416-800-9999 Fax: 416-628-0891 sbishay@iristel.com | Andrew Matoga VP President ISP Telecom 1155 Boul Rene-Levesque O Suite 2500 Montreal, QC Canada H3B 2K4 Telephone: 416-548-4626 Fax: 416-548-4847 andrew@isptelecom.net |
| Melanye Caisse Telecom Analyst ISP Telecom Inc 1155 Boul Rene-Levesque Ouest Suite 2500 Montreal, QC Canada H3B 2K4 Telephone: 416-548-4819 Fax: 416-548-4818 melanye@isptelecom.net | Robert Quance President ISP TELECOM Inc. 630 René-Lévesque blvd. West, Suite 2360 Montreal, QC Canada H3B 1S6 Telephone: 416-548-4636 Fax: 514-484-3662 robert@isptelecom.net |
| Jenoshan Balasingam IXICA Communications Inc. 174 Shropshire Drive Toronto, ON Canada M1P 1Z7 Telephone: 844-747-2729 ext: 1100 jenoshan@ixica.com | Phillip Koneswaran VP - Business IXICA Communications Inc. 174 Shropshire Drive Toronto, ON Canada M1P 1Z7 Telephone: 844-747-2729 ext: 2100 phillip@ixica.com |
| William Grier General Manager Lansdowne Rural Telephone Co. Ltd. 42 King St. West, PO BOX 9 Landsdowne, ON Canada K0E 1L0 Telephone: 613-659-2222 Fax: 613-659-2226 Wagrier@1000island.net | Rhonda Hunt Lansdowne Rural Telephone Company Lansdowne, ON Canada Telephone: 613-659-2222 Fax: 613-659-2226 rhunt@1000island.net |
| Clayton Zekelman Managed Network Systems Inc. 3363 Tecumseh Rd. E. Windsor, ON Canada N8W 1H4 Telephone: 519-985-8410 Fax: 519-985-8409 clayton@mnsi.net | Bruce Buchanan Manager, Network Operations Nexicom Telecommunications Inc. 5 King St. E. Millbrook, ON L0A1G0 Telephone: 705-932-4147 Fax: 705-775-4147 bbuchana@nexicomgroup.net |
| Deborah Hartwick Administration North Frontenac Telephone Company Limited 1019 Windwood Dr. Sharbot Lake, ON Canada K0H 2P0 Telephone: 613-279-2193 Fax: 613-279-2222 dhartwick@nftctelecom.com | Bill Young North Frontenac Telephone Corporation Limited 1019 Windwood Dr. Sharbot Lake, ON Canada K0H 2P0 Telephone: (613) 279-2193 Fax: (613) 561-6620 billyoung@nftctelecom.com |
| Grant G. Roughley North Frontenac Telephone Corporation Ltd. 545 Eglintoin Ave. west Suite 214 Toronto, ON Canada M9C 5K6 Telephone: 519-505-4347 groughley@frontenac.net | Austin He Network Planning Analyst, Network Planning Primus Management ULC. 2680 Skymark Avenue, Suite 100 Mississauga, ON Canada L4W 5L6 Telephone: 416-207-3361 AHe@primustel.ca |
| Irma Dulay Primus Telecommunications Canada Inc. 500- 5343 Dundas St West Toronto, ON Canada M9B 6K5 Telephone: 416-207-7151 Fax: 877-329-6875 idulay@primustel.ca | Rogers NumberAdmin@rci.rogers.com |
| Vivek Bhardwaj Traffic Specialist Rogers Communications 8200 Dixie Rd. Brampton, ON Canada L6T 0C1 Telephone: 647-747-3569 vivek.bhardwaj@rci.rogers.com | Jennifer Mack Traffic Specialist Rogers Communications 8200 Dixie Rd. Brampton, ON Canada L6T 0C1 Telephone: 647-747-2168 jennifer.mack@rci.rogers.ca |
| Brian Reyes Traffic Specialist Rogers Communications 8200 Dixie Rd Brampton, ON L6T0C1 Telephone: 647-747-4657 brian.reyes@rci.rogers.com | Stephanie Jackson Manager - Public Services Integration; Traffic Engineering Rogers Communications Canada Inc. 8200 Dixie Road Brampton, ON Canada L6T 0C1 Telephone: 647-747-4402 Fax: 647-747-4557 stephanie.jackson@rci.rogers.com |
| Gerry Thompson Manager, Intercarrier Relations Rogers Communications Canada Inc. 350 Bloor Street East, 6th Floor Toronto, ON Canada M4W 0A1 Telephone: 416-935-5239 Fax: 416-935-7719 Gerry.Thompson@rci.rogers.com | Tim Beach Vice President Operations Roxborough Telephone Company Limites (OCN 287H) P.O Box 190 Moose Creek, ON K0C1W0 Telephone: 613-538-7071 Fax: 613-538-8002 tjwbeach@ontarioeast.net |
| Nicholas Bayly Carrier Services Specialist Shaw Business 3636 23 ST NE Calgary, AB Canada T2E 6Y7 Telephone: 403-538-5223 nicholas.bayly@sjrb.ca | Lien Kaura Carrier Service Specialist Shaw Communications Inc. 2441 37th Ave NE Calgary, AB Canada T2E 6Y7 Telephone: 587-390-2982 Lien.Kaura@sjrb.ca |
| Ken Shackleton Manager, Consumer Voice Technology and Infrastructure Shaw Communications Inc. 2728 Hopewell Place NE Calgary, AB Canada T1Y 7J7 Telephone: 403-303-4024 Fax: 403-930-1850 ken.shackleton@sjrb.ca | Bruce Uy TN Administrator Shaw Telecom Inc 2728 Hopewell Pl NE Calgary, AB T1Y 7J7 Telephone: 403-234-6271 Fax: 403-750-4501 bruce.uy@sjrb.ca |
| Zahra Deliri Contractor Shaw Telecom Inc. Telephone: 587-390-2964 Zahra.Deliri@sjrb.ca | Sabrena McBride Product Manager T-Mobile USA 3625 132nd Ave SE Bellevue, WA USA 98006 Telephone: 877-413-5903 Sabrena.mcbride32@t-mobile.com |
| Diane Dolan Voice Service Manager TekSavvy Solutions Inc 227 rue Montcalm Gatineau, QC Canada J8Y 3B9 Telephone: 819-484-1234 ddolan@teksavvy.ca | Olena Bilozerska Network Planning Manager I, TS CC Planning & Management TELUS 200 Consilium Place, Floor 6 Scarborough, ON Canada M1H 3G2 Telephone: 647-837-1798 Olena.Bilozerska@telus.com |
| Nancy McIntyre Mgr - Planning & Engineering TELUS 3777 Kingsway Floor 07S Burnaby, BC V5H 3Z7 Telephone: 604-908-2029 nancy.mcintyre2@telus.com | Karen Robinson Network Planning Manager – Translations & Traffic Network Operation TELUS 200 Consilium Place Scarborough, ON Canada M1H 3J3 Telephone: 647-684-3053 Karen.Robinson3@telus.com |
| Johny Fernandez Technology Strategy TELUS Mobility 200 Consilium Place, 6th Flr Scarborough, ON Canada M1H 3J3 Telephone: 647-453-4442 Johny.fernandez@telus.com | Eric St-Yves Analyste Planification Videotron 2155 Pie IX Montreal, QC H1V 2E4 Telephone: 514-380-4751 eric.st-yves@videotron.com |
| Marc Berruyer Network Planner Videotron General Partnership 2155 Boul. Pie IX, 3e etage, bloc A Montreal, QC Canada H1V 2E4 Telephone: 514-380-4255 Fax: 514-899-8452 marc.berruyer@videotron.com |  |