Initial Planning Document (IPD)

- Version 1.0 – 18 May 2011

| Canadian Numbering Administrator (CNA) Suresh Khare 613-683-3296 60 Queen Street, Suite 1516 Ottawa, Ontario K1P 5Y7 khares@saiccanada.com |  |
| --- | --- |

- Table of Contents

1.	Introduction	1

2.	NPA RELIEF PLANNING PROCESS	3

3.	NPA Relief Methods	4

4.	NPA EXHAUST INFORMATION	5

5.	RELIEF options	6

5.1.	Geographic Split	6

5.1.1.	Split Option 1 & Option 2	7

5.1.2.	Split Options 3 and Option 4	7

5.2.	Distributed Overlay	8

5.2.1.	Distributed Overlay of New NPA Code on NPA 306 (Option 5):	8

6.	COMPARATIVE assessment of RELIEF OPTIONS	10

7.	Dialling impacts FOR LOCAL CALLS	12

8.	Implementation of Mandatory 10-Digit Local Dialling Prior to Overlays	14

9.	CO CODES for Initial Code Assignments AND CO CODES FOR INITIAL CODE ASSIGNMENTS FOR NEW ENTRANTS ONLY	15

10.	PROPOSED SCHEDULE	17

11.	Jeopardy Contingency Plan (JCP)	20

12.	SELECTION OF RELIEF NPA Code	28

13.	RECOMMENDATIONS	31

List Of ANNEXES

Annex A

Figure 1 –	Overview Map of NPA 306

Figure 2 –	NPA 306 Actual and Forecast CO Code Assignments

Figure 3 –	NPA 306 CO Code Exhaust, January 2011 G-NRUF

Figure 4 –	NPA 306 Miscellaneous and LEC+WSP Codes, January 2011 G-NRUF

Figure 5 –	NPA 306 CO Code Exhaust, April 2011 J–NRUF

Figure 6 –	NPA 306 CO Code Exhaust, April 2011 J–NRUF

Figure 7 –	Saskatchewan LIRs

Figure 8 –	Option 1 – Split – North Battleford, Prince Albert and Saskatoon LIRs retain NPA 306, and Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs change to new NPA

Figure 9 –	Option 2 – Split – North Battleford, Prince Albert and Saskatoon LIRs change to new NPA, and Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs retain NPA 306

Figure 10 –	Option 3 – Split – North Battleford, Prince Albert, Saskatoon and Yorkton LIRs retain NPA 306, and Moose Jaw, Regina, Swift Current and Weyburn LIRs change to new NPA

Figure 11 –	Option 4 – Split – North Battleford, Prince Albert, Saskatoon and Yorkton LIRs change to new NPA, and Moose Jaw, Regina, Swift Current and Weyburn LIRs retain NPA 306

Figure 12 –	Option 5 – Distributed Overlay of New NPA on NPA 306

ANNEX B

Table 1 –	Exchange Areas currently in NPA 306, and NPAs for these Exchange Areas after each Relief Option

Table 2 –	Exchange Areas in each LIR

Table 3 –	Suitability of Future Canadian Geographic NPAs for the relief of NPA 306

ANNEX C

Distribution List

Acronym List

| CATF | Consumer Awareness Task Force |
| --- | --- |
| CNA | Canadian Numbering Administrator |
| CISC | CRTC Interconnection Steering Committee |
| CLECs | Competitive Local Exchange Carriers |
| CO | Central Office |
| CRTC | Canadian Radio-television and Telecommunications Commission |
| G-NRUF | General Numbering Resource Utilization Forecast |
| ILECs | Incumbent Local Exchange Carriers |
| IPD | Initial Planning Document |
| JCP | Jeopardy Contingency Plan |
| J-NRUF | Jeopardy Numbering Resource Utilization Forecast |
| LIRs | Local Interconnection Regions |
| NANP | North American Numbering Plan |
| NITF | Network Implementation Task Force |
| NPA | Numbering Plan Area |
| NPA Codes | Area Codes |
| NRUF | Number Resource Utilization Forecasts |
| PD | Planning Document |
| PED | Projected Exhaust Date |
| POI | Point of Interconnection |
| RIP | Relief Implementation Plan |
| R-NRUF | Relief Planning Numbering Resource Utilization Forecast |
| RPC | Relief Planning Committee |
| TSPs | Telecommunications Service Providers |
| WNP | Wireless Number Portability |
| WSPs | Wireless Service Providers |

Initial Planning Document (IPD) Number Plan Area (NPA) 306 Relief

# Introduction

The 306 area code consists of 228 Exchange Areas serving the province of Saskatchewan which includes the major communities of Assiniboia, Esterhazy, Estevan, Humboldt, Kindersley, Maple Creek, Melfort, Melville, Moose Jaw, Moosomin, Nipawin, North Battleford, Outlook, Prince Albert, Regina, Rosetown, Saskatoon, Swift Current, Weyburn and Yorkton. A list of the Exchange Areas of NPA 306 is provided in Annex B.

Most of the growth for existing service providers in area code 306 is concentrated in less than eight (8) Exchange Areas, with the majority of this growth being in the Exchange Areas of Lloydminster, Moose Jaw, North Battleford, Prince Albert, Regina, Saskatoon, and Weyburn. However the growth due to new service providers introducing initial service in new areas is spread over a larger number of Exchange Areas throughout area code 306, with proportionally greater growth occurring outside the major communities. The total combined growth is therefore not concentrated in or limited to the Exchange Areas serving the major communities. See Annex B Table 1 for a list of Exchange Areas in NPA 306.

The introduction of Local Interconnection Regions (LIRs), the implementation of Wireless Number Portability (WNP), and initial Central Office (CO) Codes for new Competitive Local Exchange Carriers (CLECs) and Wireless Service Providers (WSPs) have accelerated demand for CO Codes throughout area code 306.

In December 2010 the Canadian Numbering Administrator (CNA) initiated its January 2011 General Numbering Resource Utilization Forecast (G-NRUF). The draft aggregate results of this G-NRUF, compiled on 29 March 2011, indicated that the Projected Exhaust Date (PED) for NPA 306 had moved in from April 2018 to August 2013. Because the PED was less than thirty-six (36) months in the future, it was necessary to start relief planning immediately. The CNA notified the CRTC staff of the Jeopardy situation in NPA 306, and asked the Canadian Radio-television and Telecommunications Commission (CRTC) to issue a Telecom Notice of Consultation for the establishment of a CISC ad hoc committee for area code relief planning in area code 306 for the province of Saskatchewan. On 29 March 2011, the CNA declared that NPA 306 was in a Jeopardy Condition. In order to gather detailed forecast data for relief planning purposes, the CNA conducted an initial Jeopardy Numbering Resource Utilization Forecast (J-NRUF) on 29 March 2011. The results of that J-NRUF, released on 10 May 2011, indicated NPA 306 would exhaust in July 2013.

On 19 April 2011, the CRTC issued Telecom Notice of Consultation CRTC 2011-260, in which it established a CISC ad hoc Relief Planning Committee (RPC) to examine options for providing relief to area code 306 in Saskatchewan. The Commission identified that the CNA had declared a Jeopardy Condition for area code 306 and that area code 306 was projected to exhaust within twenty-five (25) months.

The Notice of Consultation also stated:

The Commission considers that due to the jeopardy condition in area code 306, code conservation measures to extend the life of that area code must be implemented immediately. In particular, the jeopardy condition measures outlined in the Guidelines must be followed until i) the 306 RPC develops a jeopardy condition plan specific to area code 306 and ii) this plan is approved by the Commission.

The Commission notes that, in the event of any special circumstances in area code 306, the earliest relief implementation date determined by the 306 RPC may be after the projected exhaust date. If this occurs, the Commission directs the 306 RPC to make recommendations on the specific code conservation measures that should be taken to move the projected exhaust date so that it coincides with, or falls after, the scheduled relief implementation date. In addition, the Commission directs the 306 RPC to set aside three CO codes from area code 306 to be made available for new entrants only, and to ensure that those CO codes remain unassigned, other than to new entrants, for a period of two years after the introduction of the new area code in Saskatchewan.

This IPD is prepared by the CNA in accordance with the CRTC approved Canadian NPA Relief Planning Guideline (the Guideline) dated 2 June 2009. A copy of the Guideline is available from the CRTC CISC guidelines web page at: http://www.crtc.gc.ca/cisc/eng/cisf3fg.htm or via a link from the CNA website at http://www.cnac.ca/.

The objective of the NPA Relief Planning process is to ensure that CO Codes and telephone numbers are always available for use by Telecommunications Service Providers (TSPs) and their customers in the geographic area requiring relief.

Various options for providing NPA relief in the NPA 306 geographic area are identified in this IPD as part of the process for ensuring that an adequate quantity of CO Codes and telephone numbers is available for assignment in the geographic area covered by area code 306. Given the magnitude of this undertaking, inter-company commitment and co-operation are essential throughout the planning, provisioning and implementation stages of the introduction of a new NPA.

It is very important to closely monitor the CO Code requirements of all existing and prospective CO Code Holders so that relief can be timed to ensure that CO Codes and telephone numbers are always available for service providers and customers. It is also important that a Jeopardy Condition should be avoided wherever possible.

# NPA RELIEF PLANNING PROCESS

The NPA Relief Planning process, and the roles of the participants (e.g., CRTC, CNA, CISC, RPC participants, Interested Parties) for NPA Relief Planning are identified in the CRTC-approved Canadian NPA Relief Planning Guideline (the Guideline), dated 2 June 2009.

A copy of the Guideline is available from the CRTC CISC CSCN guidelines web page at http://www.crtc.gc.ca/cisc/eng/cisf3fg.htm or via a link from the CNA website at http://www.cnac.ca.

To increase public awareness and participation in the NPA Relief Planning process, the CRTC has determined that NPA RPCs will be established as ad hoc committees of the CISC. Generally, a separate ad hoc committee is created to deal with relief in each area code. The CNA, in its function as NPA Relief Planning Coordinator, acts as chair of these ad hoc committees. Meetings and conference calls of the ad hoc NPA RPCs are all open to public participation and are conducted in accordance with the CISC Administrative Guidelines.

A copy of the CISC Administrative Guidelines can be obtained from the CRTC website at http://www.crtc.gc.ca/public/cisc/c-docs/CISC2001-03-31.doc.

NPA Relief Planning is conducted under the regulatory oversight of the CRTC. Notwithstanding the process detailed in the Guideline, the CRTC may exercise its authority under the Telecommunications Act to alter this process at any time. The CRTC has the authority under the Telecommunications Act to review, modify and give final approval to the Planning Document (PD) and the Relief Implementation Plan (RIP) developed and submitted by the RPC to the CRTC via the CISC process.

Section 6.1.6 of the Canadian NPA Relief Planning Guideline requires the CNA to create and maintain a distribution list of parties who may be interested in participating in the RPC and to provide them with advance notice of the initial RPC meeting and the IPD.

Any person wishing to participate in the NPA Relief Planning process can contact the CNA and request to be added to the RPC distribution lists. In addition, individuals can also register with the CRTC as interested parties to any proceedings that result from the NPA Relief Planning process. More information on how to participate in CRTC public processes is available at: http://www.crtc.gc.ca/eng/info_sht/g4.htm.

A summary of Canadian geographic area code relief history is available at: www.cnac.ca/npa_codes/NPA_History.pdf.

# NPA Relief Methods

The three basic NPA Relief Methods (i.e., geographic split, overlay and boundary realignment) are described in detail in section 5.0 of the Canadian NPA Relief Planning Guideline. The purpose of this section is to identify and briefly describe those methods. For additional details refer to the Guideline at: http://www.crtc.gc.ca/cisc/eng/cisf3fg.htm.

The term Numbering Plan Area (NPA) refers to a discrete geographic area, within the area served by the North American Numbering Plan (NANP), to which one or more NPA Codes (also known as area codes) may be assigned (e.g., the city of Toronto is a Numbering Plan Area (NPA) to which NPA Codes 416/647 are assigned).

Split:

Under the geographic split method, the geographic area served by an existing NPA is generally divided or "split" into two or more unique geographic areas (i.e., two or more new NPAs. One of the areas retains the existing NPA Code, and the other area(s) changes to a new NPA Code(s).

Overlay:

Under the overlay method, a relief NPA Code is generally superimposed or "overlaid" on top of part or all of an existing NPA. With overlays, changes to existing customers' telephone numbers are not required. Four types of overlays are described in the Guideline as follows. Under the distributed overlay method, a new relief NPA Code is "overlaid" on top of all of an exhausting NPA. Under a concentrated overlay method, a new relief NPA Code is "overlaid" on top of part of an exhausting NPA (e.g., over a fast growing metropolitan area within an existing NPA). Under a boundary extension overlay method, the boundary of an existing NPA that has spare capacity is extended to overlay part or all of an exhausting NPA. Under a technology-specific overlay, a new NPA Code would be assigned to overlay an exhausting NPA and the numbering resources in the new NPA Code would be used only for a specific type of technology (e.g., wireline telephones, wireless telephones, facsimile).

Boundary Realignment:

Under the boundary realignment method, the boundary between the NPA that requires relief and an adjacent NPA are modified such that some of the customers in the exhausting NPA have their telephone numbers changed by being given telephone numbers in a different NPA Code in the adjacent NPA.

Once the necessity for NPA Code relief is established, all NPA Code Relief Methods are considered.

# NPA EXHAUST INFORMATION

As indicated in the following table, NRUFs for NPA 306 were used to determine Projected Exhaust Dates (PEDs), i.e. the dates when CO Codes in NPA 306 would be expected to exhaust.

| NRUF | Projected Exhaust Date |
| --- | --- |
| G-NRUF January 2010 | April 2018 |
| G-NRUF January 2011 | August 2013 |
| J-NRUF April 2011 | July 2013 |
| J-NRUF April 2011 (adjusted per CRTC TNC 2011-260 directive to set aside three (3) for initial code assignments for new entrants) | July 2013 |

When the initial J-NRUF results were adjusted per the Telecom Notice of Consultation CRTC 2011-260 directive to set aside three (3) CO Codes for initial code assignments for new entrants the PED remained at July 2013.

Refer to Annex A, Figures 2, 3, 4, 5, and 6 for graphs of forecasted CO Codes and charts of Miscellaneous and LEC + WSP CO Codes in area code 306.

# RELIEF options

Relief Options are alternative approaches for providing relief to an exhausting NPA. Each Relief Option generally utilizes one or more of the three (3) basic Relief Methods, specifically split, overlay or boundary realignment as described in the Canadian NPA Relief Planning Guideline (see Section 3 for a brief description of each method).

Based on the basic Relief Methods, the following Relief Options were identified and examined in detail:

- Geographic Split – Four (4) options (Options 1, 2, 3, 4)

- Distributed Overlay – One (1) option (Option 5)

Relief Options using a concentrated overlay were not examined in detail by the CNA since there is insufficient time to provide relief using such a Relief Option.

Relief Options using a boundary extension overlay and boundary realignment were not examined by the CNA because such options would create area codes that cross provincial boundaries, which is not allowed by the Canadian NPA Relief Planning Guideline and would create geographic confusion for customers and technical difficulties for TSPs.

See Annex A, Figures 8 through 12 for diagrams of the Relief Options identified by the CNA.

The Relief Options identified above were evaluated using the following assumption:

- The Relief Date for the geographic split and distributed overlay options will be 1st Q 2013 (four (4)  months prior to the NPA 306 PED of July 2013 identified using the April  2011 J-NRUF results).

## Geographic Split

Four (4) different Relief Options were evaluated to introduce a new area code in the NPA 306 area using the geographic split method of providing CO Code relief. With each of these options, number changes are required in the area that does not retain NPA 306. Selecting a split option for NPA Relief will impact from 42% to 58% of the customers with a number change.

A major attribute of a split is usually that the 7-digit local dialling plan does not have to be changed in either portion of the split area code.

It is assumed that after the split, local calls in NPA 306 and the new NPA will be dialled using 7-digits. Code Protection would not be required between NPA 306 and the new NPA because there is no Local Free Calling between the Exchange Areas of split regions.

All of the split options are based on LIRs. An LIR is a geographic area specified by Incumbent Local Exchange Carriers (ILECs) within which traffic is exchanged with CLECs on a Bill and Keep basis as specified in Telecom Decisions CRTC 2004-46 and 2006-35 Trunking arrangements for the interchange of traffic and the point of interconnection between local exchange carriers. LIRs are unique groupings of ILEC Exchange Areas which provide for more efficient interconnection between Local Exchange Carriers (LECs).

### Split Option 1 & Option 2

Split Options 1 and 2 – North Battleford, Prince Albert and Saskatoon LIRs in one NPA, and Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs in other NPA

Relief Option 1 – the North Battleford, Prince Albert and Saskatoon LIRs retain NPA 306, and Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs change to the new NPA:

- 112 Exchange Areas in the North Battleford, Prince Albert and Saskatoon LIRs retain NPA 306, and 116 Exchange Areas in the Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs change to the new NPA

Relief Option 2 – the North Battleford, Prince Albert and Saskatoon LIRs change to the new NPA and the Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs retain NPA 306:

- 112 Exchange Areas in the North Battleford, Prince Albert and Saskatoon LIRs change to the new NPA, and 116 Exchange Areas in the Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs retain NPA 306

With these options (Relief Options 1 and 2), CO Codes assigned in existing NPA 306 would split as follows, with number changes required in one of the two areas:

| Area | Assigned CO Codes in NPA 306 (as of 2011-04) |  | Projected Exhaust Date (as of 2011-04) |
| --- | --- | --- | --- |
|  | # | % of total |  |
| 112 Exchange Areas in North Battleford, Prince Albert and Saskatoon LIRs | 364 | 48% | 2048 |
| 116 Exchange Areas in Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs | 399 | 52% | 2053 |

If 7-digit local dialling is maintained between NPA 306 and the new NPA, Code Protection would not be required as there is no existing local calling between these regions.

### Split Options 3 and Option 4

Split Options 3 and 4 – North Battleford, Prince Albert , Saskatoon and Yorkton LIRs in one NPA, and Moose Jaw, Regina, Swift Current and Weyburn LIRs in other NPA

Relief Option 3 – the North Battleford, Prince Albert, Saskatoon and Yorkton LIRs retain NPA 306, and the Moose Jaw, Regina, Swift Current and Weyburn LIRs change to the new NPA:

- 136 Exchange Areas in the North Battleford, Prince Albert, Saskatoon and Yorkton LIRs retain NPA 306, and 92 Exchange Areas in the Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs change to the new NPA

Relief Option 4 – the North Battleford, Prince Albert, Saskatoon and Yorkton LIRs change to new NPA and the Moose Jaw, Regina, Swift Current and Weyburn LIRs retain NPA 306:

- 136 Exchange Areas in the North Battleford, Prince Albert, Saskatoon and Yorkton LIRs change to the new NPA and 92 Exchange Areas in the Moose Jaw, Regina, Swift Current and, Weyburn LIRs retain NPA 306

With these options (Relief Options 3 and 4), CO Codes assigned in existing NPA 306 would split as follows, with number changes required in one of the two areas:

| Area | Assigned CO Codes in NPA 306 (as of 2011-04) |  | Projected Exhaust Date (as of 2011-04) |
| --- | --- | --- | --- |
|  | # | % of total |  |
| 136 Exchange Areas in North Battleford, Prince Albert, Saskatoon and Yorkton LIRs | 443 | 58% | 2039 |
| 92 Exchange Areas in Moose Jaw, Regina, Swift Current and Weyburn LIRs | 320 | 42% | 2064 |

If 7-digit local dialling is maintained between NPA 306 and the new NPA, Code Protection would not be required as there are no existing local calling arrangements between these regions.

## Distributed Overlay

One (1) distributed overlay Relief Option was evaluated to provide CO Code relief in the NPA 306 geographical area.

### Distributed Overlay of New NPA Code on NPA 306 (Option 5):

This Relief Option would overlay the new NPA Code over the 228 Exchange Areas comprising the NPA 306 area.

With this overlay, NPA 306 and the new NPA Codes would be expected to exhaust in 3Q 2050.

This option retains the single NPA Relief Planning area in Saskatchewan. Currently, one new NPA Code would be required within the next 20-year period.

The following table summarizes the Relief Options, Projected Exhaust Dates, Relief Timing and Type, and Impacts:

| Relief Option |  | Projected Exhaust Dates |  | Relief - Timing & Type |  | CO Codes affected by No. changes (Qty/%of total) | Local Dial # of digits |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # | Description | NPA 306 | New NPA | Relief Date | Type |  |  |
| 1 | Split – North Battleford, Prince Albert and Saskatoon LIRs retain NPA 306, and Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs change to new NPA | 2013 2048 | 2053 | 2013 (306) 2047 (306) 2052 (New NPA) | S ? ? | 399 / 52% ? ? | 7 ? ? |
| 2 | Split – North Battleford, Prince Albert and Saskatoon LIRs change to new NPA, Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs retain NPA 306 | 2013 2051 | 2048 | 2013 (306) 2047 (New NPA) 2050 (306) | S ? ? | 364 / 48% ? ? | 7 ? ? |
| 3 | Split – North Battleford, Prince Albert, Saskatoon and Yorkton LIRs retain NPA 306, and Moose Jaw, Regina, Swift Current and Weyburn LIRs change to new NPA | 2013 2039 | 2064 | 2013 (306) 2038 (306) 2063 (new NPA) | S ? ? | 320 / 42% ? ? | 7 ? ? |
| 4 | Split – North Battleford, Prince Albert, Saskatoon and Yorkton LIRs change to new NPA, Moose Jaw, Regina, Swift Current and Weyburn LIRs retain NPA 306 | 2013 2064 | 2039 | 2013 (306) 2038 (new NPA) 2063 (306) | S ? ? | 443 / 58% ? ? | 7 ? ? |
| 5 | Distributed Overlay of New NPA on NPA 306 | 2013 | 2050 | 2013 (306) 2049 (new NPA) | O ? ? | Nil ? ? | 10 10 10 |
| Key | 7-D = 7-digit local dialling retained, 10-D = mandatory 10-digit local dialling, O = Overlay, S= Split, ? = Unknown (subsequent relief type, Qty of CO Codes affected by No. Changes, and dial plan) |  |  |  |  |  |  |

# COMPARATIVE assessment of RELIEF OPTIONS

The RPC identified five (5) Relief Options in section 5 of this document. A Pro, Neutral or Con (P, N or C) rating was established for each Relief Option for each of the following attributes. The results are listed in the table below the list of attributes.

- NPA Code Conservation – quantity of new NPAs required in Saskatchewan within the next 20 years after relief (2012-2032) (P = 0 new NPAs; N = 1 new NPA; C = 2 or more new NPAs)

- Number of separate Relief Planning areas in Saskatchewan in the long term (P = decrease; N = stays same; C = increase)

- Quantity of Potential Number Changes for existing customers' numbers either immediately or in the future (P = none; C = many)

- Level of Carrier Costs – e.g., including implementation, customer awareness, rate of return (P = Low; N = Medium; C = High)

- Time required to implement relief, i.e., time between the CRTC's Decision date and the date when CO Codes in the new/relief NPA can be activated (P = shortest; N = medium; C = longest)

- Longevity – the length of time between this relief and subsequent relief activity in NPA 306 (e.g., a new area code) (P = 15 or more years; N = 9 through 14 years; C = within 8 years)

- Established Geographic Identities – changes in boundaries of existing NPAs (P = none; C = 1 or more existing NPAs affected)

- New Geographic Identities – boundaries of new NPA align with boundaries of known areas (e.g., existing NPA areas, provinces) or identifiable geographical features (e.g., rivers, islands) (P = aligns with existing NPA boundaries; N = aligns with geographical features but not with existing NPA boundaries; C = aligns with neither existing NPA boundaries, nor identifiable geographical features)

- Creates areas with mix of 7- and 10-digit local dialling in Saskatchewan (P = none; N = minor amount; C = significant)

- Consistent with the transition towards universal 10-digit local dialling, the Uniform Dialling Plan and future NANP Expansion (P = Yes; C = No)

- Reprogram Mobile Phones – requirement to reprogram wireless devices to accommodate the number changes (P = Low; C = High)

- Potential maximum quantity of NPAs in an Exchange Area in the next 20 years after relief (2012-2032) (P = 1 NPA; N = 2 NPAs)

| Relief Option |  | Pro, Neutral or Con for Each Attribute |  |  |  |  |  |  |  |  |  |  |  |  | Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Description | A | B | C | D | E | F | G | H | I | J | K | L |  |  |
| 1 | Split – North Battleford, Prince Albert and Saskatoon LIRs retain NPA 306 and Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs change to new NPA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Split – North Battleford, Prince Albert and Saskatoon LIRs change to new NPA, Moose Jaw, Regina, Swift Current, Weyburn and Yorkton LIRs retain NPA 306 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Split – North Battleford, Prince Albert, Saskatoon and Yorkton LIRs retain NPA 306 and Moose Jaw, Regina, Swift Current and Weyburn LIRs change to new NPA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Split – North Battleford, Prince Albert, Saskatoon and Yorkton LIRs change to new NPA and Moose Jaw, Regina, Swift Current and Weyburn LIRs retain NPA 306 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Distributed Overlay of New NPA on NPA 306 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

* Note: In instances where two (2) values appear in a cell, the upper value is that provided by the ILEC. The lower value is that provided by other Carriers in Saskatchewan.

Note: None of the options require Exchange Area boundary changes.

If P, N and C are assigned a weighting of +1, 0 and -1, respectively, then analysis of the above table gives the highest rating of X points to Relief Option X, and the next highest rating of X points to Relief Option X and the subsequent ratings of X for Relief Options X, respectively.

Relief Option X is clearly superior when assessed using the above criteria.

# Dialling impacts FOR LOCAL CALLS

Currently the dialling for local calls within NPA 306 and across its boundaries is as follows:

    - 7-digit dialling for local calls within NPA 306

    - in addition to providing 7-digit dialling for local calls from NPA 306, some Telecommunications Service Providers permit 10-digit dialling, or 10- and 11-digit dialling,

    - 7-digit dialling for local calls from NPA 306 – Creighton SK to Flin Flon MB in adjacent NPA 204/431

    - 7-digit dialling for local calls from NPA 306 – Lloydminster SK to Lloydminster AB in adjacent NPA 780/587

    - no local calling between NPA 306 and adjacent Canadian NPAs 403/587 & 867, and US NPAs 406 and 701

After NPA relief, dialling for local calls will be as follows:

| Type of Relief | Local calls originating in NPA 306 and new NPA |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Within NPA 306 | Within new NPA | Between NPA 306 and new NPA | From NPA 306 &/or new NPA to adjacent NPA 204/431 (Creighton SK to Flin Flon MB) | From NPA 306 &/or new NPA to adjacent NPA 780/587 (Lloydminster SK to Lloydminster AB) |
| Split | 7-digit dialling retained | 7-digit dialling provided | 7-digit dialling eliminated, and mandatory 10-digit dialling introduced (see below for potential major exception) | 7-digit dialling eliminated, and mandatory 10-digit dialling introduced (see below for potential minor exception) | 7-digit dialling eliminated, and mandatory 10-digit dialling introduced (see below for potential minor exception) |
| Overlay | 7-digit dialling eliminated, and mandatory 10-digit dialling introduced |  |  |  |  |

The Canadian NPA Relief Planning Guideline section 4.10 specifies that Code Protection be eliminated on relief, which means mandatory 10-digit dialling must be introduced for all local calls across NPA boundaries, unless the CRTC approves otherwise. An exception would not normally be justified if it would affect the life of the relief. In addition, if the amount of Code Protection is sufficient to affect the life of the relief it would create a significant administrative burden for managing it.

For all of the geographical split options, existing CO Code Protection practices must remain in place for Creighton SK to Flin Flon MB and Lloydminster SK to Lloydminster AB in order to retain 7-digit local dialling.

Any future additional CO Code assigned in NPA 204/431 in the Flin Flon MB Exchange Area would need to be protected in NPA 306 or the new NPA in the Creighton MB Exchange Area to maintain 7-digit local dialling as the standard in Creighton SK.

Any future additional CO Code assigned in NPA 780/587 in the Lloydminster AB Exchange Area would need to be protected in NPA 306 or the new NPA in the Lloydminster SK Exchange Area to maintain 7-digit local dialling as the standard in Lloydminster SK.

Given the small amount of Code Protection that would be required to maintain 7-digit local dialling as the standard for all local calls in Creighton and Lloydminster and the fact that the protected CO Codes in NPA 204/431 and 780/587 could be assigned in parts of Manitoba and Alberta distant from NPA 306, thus making effective use of the CO Codes, the RPC recommends that an exception be made to allow 7-digit dialling to continue on local calls from Creighton and Lloydminster SK.

Note regarding long-distance calling: Regardless of the Relief Option approved, NPA relief will not affect the dialling plan for long-distance calls originating in NPA 306 and other NPAs. No local calling will become long-distance, and no long-distance calling will become local as a result of NPA relief.

# Implementation of Mandatory 10-Digit Local Dialling Prior to Overlays

In Telecom Regulatory Policy CRTC 2009-156, section 13, regarding dialling plan changes, the Commission retained the general obligation for all relevant TSPs to inform all customers about dialling plan changes but that TSPs may determine the appropriate methods to inform their customers. Accordingly, TSPs may determine the appropriate methods for informing their customers of dialling plan changes that will occur as part of NPA relief projects (e.g., network announcements on 7-digit dialled calls, bill messages and inserts, customer letters, e-mail messages, media advertising, web sites, etc.).

Equipment used by Local Exchange Carriers to provide service in some Exchange Areas may not be able to connect a call following an announcement (i.e., cut-through), as is usually expected during transition to an overlay. Investments that would be required to upgrade or replace network elements to provide transition announcements in some communities could be significant relative to their size, and such investments would provide a capability that would only be used for a short time, i.e. during the dialling transition period.

In Telecom Decision CRTC 2006-26, the CRTC addressed the above situation and established a process and requirements for Carriers to follow. The RPC recommends the same approach be adopted for NPA 306.

In the Decision, the Commission directed TSPs to:

    - send monthly bill inserts in each of the four (4) months immediately prior to the month when mandatory 10-digit local dialling is scheduled to be implemented;

    - place two (2) notices in local newspapers (if available), one during the month prior to the month when mandatory 10-digit local dialling is scheduled to be implemented, and one during the month when mandatory 10-digit local dialling is scheduled to be implemented;

    - send a personal letter to each affected customer, to be received ten (10) days prior to the implementation date of mandatory 10-digit local dialling; and

    - place information on the TSPs' websites in a prominent, highly visible location for the minimum period of about five (5) months ending at the end of the month when mandatory 10-digit local dialling is scheduled to be implemented.

# CO CODES for Initial Code Assignments AND CO CODES FOR INITIAL CODE ASSIGNMENTS FOR NEW ENTRANTS ONLY

When area code relief planning becomes necessary, the CRTC usually directs that quantities of CO Codes in an exhausting NPA be set aside prior to relief as unavailable for assignment in order to ensure that some CO Codes in the exhausting NPA will be available after relief via an overlay for initial code assignments for new entrants only and for initial code assignments for applicants in general or those already providing service in the NPA. In the absence of a Jeopardy Condition, exhaust of the NPA, or a split, the set-aside CO Codes would only be available after relief via an overlay, and any set-aside CO Codes remaining two (2) years after the overlay would be returned to the general pool.

A New Entrant is an entity who, at the time of their first request for assignment of CO Code(s) in an NPA, does not provide any telecommunications services and does not hold any CO Codes within the boundaries of the NPA.

Direction regarding set-aside CO Codes is provided by subparagraphs a), b) and c) of the fifth paragraph of section 9.1 of the Canadian NPA Relief Planning Guideline, which requires that the RPC establish the following as part of the JCP:

- If the CRTC has directed, or the RPC has recommended (e.g., per section 5.2 of this guideline), that CO Codes in the exhausting NPA be set aside for initial code assignments for New Entrants only for assignment following relief, then, if all other available CO Codes in the exhausting NPA have been assigned, or if the CRTC has approved a split, these set-aside codes should be made available during the Jeopardy Condition for assignment as initial codes for New Entrants only, i.e. for assignment prior to relief.

- If the CRTC has directed, or the RPC has recommended (e.g., per section 5.2 of this guideline), that CO Codes in the exhausting NPA be set aside for initial code assignments for applicants in general for assignment following relief, then the JCP should specify that these set-aside CO Codes will become available for general assignment when a Jeopardy Condition is in effect.

- If a Jeopardy Condition is in effect and, if all other available CO Codes in the exhausting NPA have been assigned, CRTC staff may make some or all of the CO Codes in the two pools identified in a) and b), above, available for assignment to any entity for any purpose.

Telecom Notice of Consultation CRTC 2011-260, Establishment of a CISC ad hoc committee for area code relief planning for area code 306 in Saskatchewan, issued by the Commission on 19 April 2011, the CRTC noted the CNA had declared a Jeopardy Condition for area code 306 and that area code 306 was projected to exhaust within twenty-five (25) months.

In paragraph ten of the Notice of Consultation, the Commission directed the NPA 306 RPC to set aside three (3) CO Codes from area code 306 to be made available for New Entrants only, and to ensure that those CO Codes remain unassigned, other than to New Entrants, for a period of two (2) years after the introduction of the new area code in Saskatchewan. Accordingly, the CNA has set aside three (3) CO Codes, as directed.

If the CRTC-approved Relief Method is an overlay, then these quantities of set aside CO Codes would become available for assignment as specified above during the two (2) year time period after implementation of the overlay. Any set-aside CO Codes remaining unassigned at the end of the two (2) year time period would be returned to the general pool of assignable CO Codes.

# PROPOSED SCHEDULE

The RPC submits the following schedule for NPA 306 relief based on the recommendations contained in this Initial Planning Document and the current PED of July 2013. The RPC will monitor the PED, and if it changes significantly in the future (e.g., is advanced or delayed by greater than six (6) months), the RPC will assess the situation and, if necessary, submit recommendations including a revised schedule to the CRTC for consideration and approval.

RELIEF IMPLEMENTATION SCHEDULE

For a Distributed Overlay of new NPA over NPAs 306

To be completed by RPC.

| Item | Task or Event | PRIME | START | END |
| --- | --- | --- | --- | --- |
| 1 | CNA identifies NPA exhaust and notifies by e-mail CRTC staff, CSCN, NANPA & CISC that the NPA will exhaust within 25 months and NPA is in Jeopardy Condition. | CNA | 29-Mar-11 | 29-Mar-11 |
| 2 | CNA conducts first J-NRUF (April 2011 J-NRUF) | CNA | 29-Mar-11 | 3-Jun-11 |
| 3 | CRTC issues Telecom Notice of Consultation regarding RPC Ad Hoc CISC and Interested Parties list | CRTC |  | 19 Apr-11 |
| 4 | CNA develops and distributes IPD to RPC | CNA | 19 Apr-11 | 18-May-11 |
| 5 | RPC participants review IPD & submit contributions to RPC | RPC | 18-May-11 | 31-May-11 |
| 6 | CNA chairs initial RPC meeting to start development of PD, RIP & PL, & schedules future meetings/conference calls including creation & consultation with CATF and NITF | CNA RPC | 31-May-11 | 1-Jun-11 |
| 7 | CNA chairs subsequent RPC meetings/conference calls to finalize PD, RIP | CNA RPC | 1-Jun-11 |  |
| 8 | Special Types of Telecommunications Service Users (9-1-1 PSAPs, alarm companies, ISPs, paging companies, etc.) to identify any concerns to RPC & CRTC | Special Users |  |  |
| 9 | CNA forwards Planning Document (PD) and, possibly, RIP to the CISC and CRTC for approval | CNA |  |  |
| 10 | CRTC issues Telecom Decision approving the Relief Method, Relief Date, New NPA & Relief Implementation Plan (RIP) | CRTC |  |  |
| 11 | Task Forces, TSPs and users implement relief (starts when CRTC approves RIP and ends on Relief Date) | TSPs |  |  |
| 12 | All Telecom Service Providers (TSPs) to develop and file individual consumer awareness programs with the CRTC (may be done collectively by Telecommunications Alliance) (starts when CRTC approves RIP and should be completed about 24 months prior to the Relief Date) | TSPs |  |  |
| 13 | CNA issues media release (in coordination with Telecommunications Alliance) (may start when CRTC approves RIP and should be issued at least 18 months prior to the Relief Date) | CNA |  |  |
| 14 | CNA submits PL and RIP to NANPA (should be submitted at least 18 months prior to the Relief Date) | CNA |  |  |
| 15 | NANPA receives and posts Planning Letter to NANPA website (should be posted at least 12 months prior to Relief Date and within 2 weeks of receipt from the CNA) | NANPA |  |  |
| 16 | Task Forces, TSPs and users implement relief (starts upon CRTC approval of RIP and ends on the Relief Date) | Task Forces, TSPs & Users |  |  |
| 17 | All TSPs implement consumer awareness activities (starts when Consumer Awareness Programs are filed with the CRTC and is completed on the Relief Date) | TSPs |  |  |
| 18 | All TSPs to notify all customers (including residence, business & special customers) of the new overlay NPA (may start when Consumer Awareness Programs are filed with the CRTC and all customers should be notified by at least 18 months prior to the Relief Date) | TSPs |  |  |
| 19 | TSPs to submit Progress Report #1 to NITF and CATF (starts after completion date for all TSPs to notify their customers and requires 2 weeks) | TSPs |  |  |
| 20 | NITF and CATF develop & submit Progress Report #1 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF |  |  |
| 21 | RPC submits Progress Report #1 to CISC/CRTC (linked to NITF and CATF reports) | RPC |  |  |
| 22 | Telcordia TRA database updates to add Exchanges to new overlay NPA (starts on the date that the PL is posted to the NANPA web site and must be completed by 6 months prior to the Relief Date) | Telcordia TRA |  |  |
| 23 | All Telecommunications Service Users (including Special Users 9-1-1 PSAPs, alarm companies, ISPs, paging companies, etc.) to implement changes to their telecom equipment & systems to accommodate the new NPA (starts when CRTC approves RIP and ends on the Relief Date) | Telecom Service Users |  |  |
| 24 | Payphone Providers Reprogram Payphones (starts when CRTC approves RIP and ends on the Relief Date) | Payphone Providers |  |  |
| 25 | TSPs and database owners/operators to modify systems and industry databases (starts when CRTC approves RIP and ends on the Relief Date) | TSPs & Database Owners |  |  |
| 26 | Operator Services & Directory Assistance Readiness (starts when CRTC approves RIP and ends on the Relief Date) | TSPs |  |  |
| 27 | Directory Publisher Readiness for overlays (ability to identify the NPA in telephone numbers in the directory published after the Overlay NPA is activated) (starts when CRTC approves RIP and ends on the Relief Date) | Directory Publishers |  |  |
| 28 | 9-1-1 PSAP Systems and Databases Readiness (starts when CRTC approves RIP and ends on the Relief Date) | PSAPS & TSPs |  |  |
| 29 | 9-1-1 TSP Readiness (starts when CRTC approves RIP and ends on the Relief Date) | TSPs |  |  |
| 30 | ISCP & Service Order Systems Readiness (starts when CRTC approves RIP and ends on the Relief Date) | TSPs |  |  |
| 31 | International Gateway Switch Translations Readiness for new NPA (starts when CRTC approves RIP and ends on the Relief Date) | Int’l TSPs |  |  |
| 32 | Canadian Local Number Portability Consortium (CLNPC) Database Readiness for new NPA (starts when CRTC approves RIP and ends on the Relief Date) | CLNPC & NPAC |  |  |
| 33 | Toll Free SMS Database Readiness for new NPA (starts when CRTC approves RIP and ends on the Relief Date) | Toll TSPs |  |  |
| 34 | ISCP & Service Order Systems Readiness (starts when CRTC approves RIP and ends on the Relief Date) | TSPs |  |  |
| 35 | TSPs apply for Test CO Codes in new NPA (applications may be submitted no more than 6 months and no less than 66 days prior to the start date for the Inter-Carrier Testing Period) (Section 7.16.4 Canadian RP GL) | TSPs |  |  |
| 36 | Develop Inter-Carrier Network Test Plans and prepare for testing (individual TSPs to make arrangements in accordance with interconnection agreements) (may start when CRTC approves RIP and must be completed by start date for the Inter-Carrier Testing Period) | NITF & TSPs |  |  |
| 37 | All international and domestic Telecommunications Service Providers (TSPs) must activate the new NPA in their networks by the start date for the Inter-Carrier Testing Period | TSPs |  |  |
| 38 | Activation date for Overlay NPA Test CO Codes and Test Numbers in network (should be completed by the start date for the Inter-Carrier Testing Period) | TSPs |  |  |
| 39 | Inter-Carrier Testing Period (subject to Inter-Carrier Network Test Plans) (starts about 3 months prior to the Relief Date, and ends about 1 month after the Relief Date) | NITF & TSPs |  |  |
| 40 | TSPs to submit Progress Report #2 to NITF and CATF (starts on commencement of Inter-Carrier Testing Period) | TSPs |  |  |
| 41 | NITF and CATF develop & submit Progress Report #2 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF |  |  |
| 42 | RPC submits Progress Report #2 to CISC/CRTC (linked to NITF and CATF reports) | RPC |  |  |
| 43 | Relief Date (earliest date when CO Codes in new NPA may be activated) |  |  |  |
| 44 | TSPs submit Final Report to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs |  |  |
| 45 | NITF and CATF develop & submit Final Progress Report to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF |  |  |
| 46 | RPC submits Final Progress Report to CISC/CRTC (linked to NITF and CATF reports) | RPC |  |  |
| 47 | TSPs disconnect Test Codes & Numbers, and submit Part 1 form to return Test Codes (starts 1 month after Relief Date and allows 1 month for completion) | TSPs |  |  |

# Jeopardy Contingency Plan (JCP)

The RPC has developed the following JCP for inclusion in the PD for NPA 306. This JCP is based on the example contained in Appendix F to the Canadian NPA Relief Planning Guideline.

This JCP shall remain in effect until either the Jeopardy Condition is suspended or sixty-six (66) days before the Relief Date.

During a Jeopardy Condition, CO Code Applicants shall submit all CO Code applications and related correspondence for the Jeopardy NPA to CRTC staff in addition to the CNA.

In Telecom Notice of Consultation CRTC 2011-260 the Commission directed that any CO Code application to the CNA be accompanied by a letter, on company letterhead and signed by a company officer, justifying the request and certifying that the requested CO Code will be in service within four (4) months of the date of that application.

During a Jeopardy Condition, the CNA shall only assign CO Codes from the exhausting NPA to a CO Code Applicant upon approval of CRTC staff.

The following measures shall be implemented by all CO Code Holders in NPA 306 when this JCP is approved by the CRTC and while a Jeopardy Condition is in effect.

- Carriers and/or Telecommunications Service Providers (TSPs):

  - shall age disconnected residential and wireless telephone numbers for a maximum of two (2) months;

  - shall age disconnected business telephone numbers for a maximum of six (6) months. Under special circumstances, the six (6) month aging limit for business telephone numbers may be extended to twelve (12) months if required to accommodate local directory publishing dates for high volume call-in applications (e.g., heavily advertised local business numbers such as radio talk shows, food ordering services, ticket sales, chat lines), or for numbers associated with public service emergency applications or for numbers advertised in directories for which customers have requested reference of calls;

  - shall return all CO Codes that are not being used nor intended to be used to directly serve customers to the assignment pool within two (2) months (e.g., plant test codes);

  - should work towards, and encourage existing customers, to either activate or return the reserved numbers in order to bring the reserved quantity down to a maximum of ten percent (10%) of the quantity of numbers In-service for that customer;

  - shall not allow the quantity of reserved numbers to be increased by new reservation requests by existing customers to more than ten percent (10%) of the quantity of numbers in service for that customer. In the case of new customers, number reservations shall be limited to ten percent (10%) of the total quantity of telephone numbers being placed into service for that customer;

  - shall, within forty-five (45) days from the date that the CNA declares a Jeopardy Condition submit a Part 1 Form for each remaining reserved CO Code either returning the reserved CO Code to the CNA or requesting assignment of the reserved CO Code. Once the forty-five (45) day period has elapsed, the CNA shall make available for general assignment all CO Codes that are still reserved and have not been applied for as assignments on a Part 1 Form received by the CNA. Within sixty (60) days from the date that the CNA declares a Jeopardy Condition, the CNA shall report to CRTC staff and the RPC as to how many of these codes have been assigned or made available for general assignment;

  - shall not be permitted to obtain a new CO Code reservation;

  - shall place all CO Codes assigned prior to the Jeopardy Condition being declared In-Service within three (3) months of the effective date for CO Code activation in the network, or within three (3) months of the date that the Jeopardy Condition was declared. If the CO Code is an Initial Code and the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-service date has been delayed beyond the applicable timeframe, then the CNA may grant an extension of up to two (2) months to the In-service date. The CNA shall initiate reclamation procedures for all CO Codes that have not been placed In-service within these timeframes unless CRTC staff approves a further extension.

- For new applications for Initial Codes, each CO Code Holder shall certify that the CO Code will be activated in the network and placed In-service within four (4) months of the date of application for the code. If the CNA does not receive a Part 4 Form within this timeframe, confirming that the CO Code has been placed In-service, the CNA will initiate reclamation measures. If the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-service date has been delayed not more than six (6) months from the original application date, and then the CNA may grant an extension to the In-service date, so long as the In-service date is not more than six (6) months beyond the original application date. If the In-service date has been delayed more than six (6) months from the original application date, then the CNA shall reclaim the CO Code unless CRTC staff approves a further extension.

- When applying for an Additional Code for Growth, a CO Code Holder who is submitting a Part 1 Form and Appendix B worksheet shall also submit a completed Supplementary Form for a Growth CO Code Application (attached) which certifies and/or provides the following information for the specific switching entity/POI and Exchange Area when the growth CO Code is being requested in a Jeopardy Condition:

  - certification that all held telephone numbers have been released;

  - certification that reserved numbers do not exceed ten percent (10%) of the total quantity of numbers as defined in Appendix G of the Canadian CO Code (NXX) Assignment Guideline;

  - certification that each reseller/dealer had been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two (2) times the highest quantity of customer numbers assigned in any month during the previous twelve (12) months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three (3) months' inventory;

  - confirmation that the Part 1 Form submitted with the application has the Jeopardy Condition box in section 1.6 checked to certify that the existing CO Codes are projected to exhaust within four (4) months of the date of application or within the period specified within an approved JCP, and that the months-to-exhaust is documented on an Appendix B submitted to the CNA;

  - a completed Telephone Number Utilization Report;

  - confirmation that the requested Growth CO Code was forecasted in the most recent NRUF or an explanation as to why it was not is attached; and

  - confirmation that the requested Growth CO Code will be placed In-service within four (4) months of the date of assignment.

In Telecom Notice of Consultation 2011-260 it was specified that the Telephone Number Utilization Report Form (see item 3e) above) is to be signed by both a company officer and the company's Authorized Representative.

- Any CO Codes for growth assigned after the implementation of this JCP must be activated in the network and placed In-service within four (4) months of assignment. In the event that a CO Code Holder is unable to place the CO Code In-service within four (4) months of the date of assignment, the CO Code Holder must submit a written request for extension to the CNA. Such written requests must include documentation explaining the reason(s) for the missed date and proposing the new In-Service date. If the explanation includes reasons beyond the control of the CO Code Holder, the CNA may extend the In-service date a maximum of one (1) month. If the CO Code Holder does not place the CO Code In-service within the one (1) month extension, the CNA shall reclaim the CO Code immediately at the end of the one (1) month extension unless CRTC staff approves a further extension.

- A Carrier that has multiple switching entities within an Exchange Area shall examine the possibility of, and implement where feasible, number sharing between those switches as a potential method to delay requirements for additional CO Codes.

- The CNA will compare the initial J-NRUF input to the recent NRUF inputs, in order to assess forecasting trends. The CNA shall monitor all inputs and shall test them for reasonableness in consultation with the Carrier. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the deviations, then the matter will be referred to the Commission.

- The CNA will request subsequent J-NRUF input from all current and prospective CO Code Holders quarterly until three (3) months before relief is provided. If one or more R-NRUFs have already been conducted, and depending on the severity of the Jeopardy Condition, the CNA may defer a J-NRUF by up to two (2) months if such a deferral brings the timing of that J-NRUF and subsequent J-NRUFs into alignment with other NRUFs that are conducted at twelve (12), six (6) or three (3) month intervals. Subsequent J-NRUF input will be compared with the initial J-NRUF input to evaluate the effectiveness of the JCP. The CNA shall monitor all J-NRUF inputs and shall test them for reasonableness in consultation with the Telecommunications Service Providers. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the changed forecasts, then the matter will be referred to the Commission.

- A CO Code Applicant must have submitted a completed J-NRUF to the CNA before the CNA may assign a CO Code to that CO Code Applicant.

- When a CO Code Applicant requests more CO Codes than it identified in its most recent J-NRUF forecast, the CNA will discuss the matter with the CO Code Applicant and if the CO Code Applicant wishes to proceed with the request, the CNA will forward the request to CRTC staff for consideration.

- The CO Codes identified in the NPA CO Code Inventory Chart as “Assignable CO Codes in a Jeopardy Condition” will be assigned in the order determined by the RPC after all CO Codes which are “Available for Assignment as of dd/mm/yyyy” have been assigned.

- After each J-NRUF, the CNA shall provide the Commission and the RPC participants with a report providing an updated NPA CO Code Inventory Chart for the NPA in jeopardy as well as the aggregate results of the most recent J-NRUF.

- Exceptional issues or concerns may be referred by the CNA, or by individual entities (with a courtesy copy to the CNA), to the Commission for resolution.

- In a situation where the Relief Date is on or after the PED, the quantity of CO Codes that may be assigned to a CO Code Applicant prior to the end of the Jeopardy Condition (i.e., sixty-six (66) days prior to the Relief Date) shall be limited to the quantity forecasted by the CO Code Applicant in its most recent NRUF forecast submitted prior to the Jeopardy Condition being declared by the CNA (if no previous NRUF was submitted, then the previous forecast will be deemed to be zero (0) codes). When making requests to obtain CO Codes prior to the end of the Jeopardy Condition (i.e., sixty-six (66) days prior to the Relief Date), the CO Code Applicant may change the Exchange Area or the month when the CO Code assignment is required, provided a new J-NRUF and explanation accompanies the application. The control imposed by this option may be relaxed if subsequent J-NRUFs defer the PED to after the Relief Date. CO Codes that become available for assignment due to future reduced demand from other current and prospective CO Code Holders may be assigned at the discretion of CRTC staff.

- If the CNA determines that the implementation of the JCP has not extended the Projected Exhaust Date of the NPA beyond the Relief Date, the CNA will consult with Commission staff and further CO Code conservation and assignment procedures may be ordered by the Commission (e.g., rationing, lottery, etc.).

- In Telecom Notice of Consultation CRTC 2011-260 the CRTC directed the 306 RPC to set aside, three (3) CO Codes for initial code assignments exclusively for new entrants. A New Entrant is an entity who, at the time of their first request for assignment of CO Code(s) in an NPA, does not provide any telecommunications services and does not hold any CO Codes within the boundaries of the NPA.

When a Jeopardy Condition is in effect, the three (3) CO Codes for initial code assignments exclusively for new entrants shall be made available for initial code assignment for new entrants prior to the relief if all other available CO Codes in the exhausting NPA have been assigned. Any CO Codes from this previously set-aside pool that remain when the Jeopardy Condition ends shall be returned to the pool for initial code assignments for New Entrants for assignment following relief.

When a Jeopardy Condition is in effect and, if all other available CO Codes in the exhausting NPA have been assigned, CRTC staff may make some or all of the CO Codes in the set-aside pool described above, available for assignment.

Supplementary form for a Growth CO Code Application – Page 1 of 2 – Telephone Number Utilization Report

This form is required with each request for an Additional Code for Growth in an NPA where a Jeopardy Condition is in effect. It should be submitted to the CNA together with the Part 1 and Appendix B forms that are required for an application for an Additional Code for Growth. See the Part 1 form for information on how and where to submit the form.

I hereby certify that the following information is true and accurate to the best of my knowledge and has been prepared in accordance with Special Conservation Procedures for a Jeopardy Condition contained in the Canadian NPA Relief Planning Guideline or the applicable approved Jeopardy Contingency Plan.

Name & Signature of Authorized Representative of Code Holder	Title	Date

Name & Signature of Company Officer (see item 3 of this JCP)	Title	Date

Contact information:	Entity Name: 	__________________	Contact Name:	_____________

Address: 	__________________	City, Province, Postal Code:	_____________

Telephone: 	__________________	Facsimile:	_____________

E-mail: 	__________________

Switch Identification (Switching Entity/POI) CLLI: _______________ 	Exchange Area: ________________

For the above Switch Identification and Exchange Area for which a Growth CO Code is requested:

I certify that all held telephone numbers have been released

I certify the total quantity of reserved numbers does not exceed ten percent (10%) of the total quantity of telephone numbers as defined in Appendix G of the Canadian CO Code (NXX) Assignment Guideline

I certify that each reseller/dealer has been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two (2) times the highest quantity of customer numbers assigned in any month during the previous twelve (12) months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three months' inventory.

The Part 1 form submitted with the application has the Jeopardy Condition box in section 6 checked (this certifies that the existing CO Codes are projected to exhaust within four (4) months of the date of the application or within the period specified in an approved Jeopardy Contingency Plan, and that the months-to-exhaust is documented on an Appendix B submitted to the CNA).

The Telephone Number Utilization Report on page 2 of this form has been completed.

The requested Growth CO Code was forecasted in the most recent NRUF, or an explanation as to why it was not is attached.

The requested Growth CO Code will be placed In-Service within four (4) months of the date of assignment.

Supplementary form for a Growth CO Code Application - Page 2 of 2 - Telephone Number Utilization Report

(Note: if the spreadsheet below does not show on your display, please change the Word view to “Print Layout” or “Reading Layout”

Remarks: 	_______________________________________________________________________________________

_______________________________________________________________________________________

_______________________________________________________________________________________

NPA 306 CO Code Inventory Chart

The following chart and the instructions it contains will apply in NPA 306 in a Jeopardy Condition.

The chart shown below lists quantities of CO Codes unassignable prior to a Jeopardy Condition, CO Codes that become assignable in a Jeopardy Condition, and CO Codes in NPA 306 assigned and In-service as of 18 May 2011. For an Overlay option it identifies thirty three (33) CO Codes that are unassignable prior to a Jeopardy Condition, sixteen (16) of which become assignable in a Jeopardy Condition. The CO Codes that become assignable in a Jeopardy Condition shall only be made available for assignment when all other available CO Codes have been assigned. The types of CO Codes that become assignable in a Jeopardy Condition should be made available in the same order as listed in the chart.

|  |  | Quantity |
| --- | --- | --- |
| A | Total CO Codes in NPAs 306 (NXX format) | 800 |
| B | CO Codes unassignable prior to a Jeopardy Condition |  |
|  | N11 Service Codes (211, 311, 411, 511, 611, 711, 811, 911) | 8 |
|  | Special Use Codes (555, 950 & 976) | 3 |
|  | Home NPA Code(s) (306) | 1 |
|  | Current Neighbouring NPA Codes (204,403,431) | 3 |
|  | Future Geographic NPA Codes (437,474,568,639,851,871,879,942) | 8 |
|  | Plant Test Codes (958 & 959) | 2 |
|  | Special 7-digit Dialling Codes (310, 610 & 810) | 2 |
|  | CO Codes set aside for Initial Codes for New Entrants only (for assignment after relief via an overlay [or before if a split]) | 3 |
|  | 9-1-1 Misdial Codes (912, 914 & 915) | 3 |
|  | Total B | 33 |
| C | CO Codes assignable prior to a Jeopardy Condition (C=A-B) | 767 |
| D | CO Codes unassignable prior to a Jeopardy Condition that become assignable in a Jeopardy Condition: |  |
|  | Future Canadian Geographic NPA Codes (437,568,639,851,871,879, 942) | 7 |
|  | Current Neighbouring NPA Codes (assign CO Code 403, in the Eastern portion of NPA 306 and assign CO Codes 204 and 431 in the western portion of NPA 306) | 3 |
|  | CO Codes set aside for Initial Codes for New Entrants only (for assignment after relief via an overlay [or before if a split]) | 3 |
|  | 911 Misdial Codes (912, 914 & 915) | 3 |
|  | Total D | 16 |
| E | Assignable CO Codes in a Jeopardy Condition (E=C+D) | 783 |
| F | Assigned CO Codes as of 18 May 2011 | 701 |
| G | Net CO Codes available for assignment as of 18 May 2011 without a Jeopardy Condition (G=C-F) | 66 |
| H | Net CO Codes available for assignment as of 18 May 2011 in a Jeopardy Condition (H=E-F) | 82 |

Notes:

1.	21 of the 29 CO Codes corresponding to Future Canadian Geographic NPA Codes are already assigned, in-service, or available for assignment in NPA 306 leaving 8 CO Codes as currently unavailable for assignment.

2.	 CO Codes 437, 474, 568, 639, 851, 871, 879 and 942 are unavailable for assignment in NPA 306. One of these cannot become assignable even in a Jeopardy Condition as it would correspond to the new NPA, therefore must remain unassignable as a CO Code.

# SELECTION OF RELIEF NPA Code

When an immediate or subsequent NPA relief requires a new NPA Code, some of the criteria for selecting the new NPA Code from the list of available Future Canadian Geographic NPA Codes are described in section 4.9 of the Canadian NPA Relief Planning Guideline as follows.

In the event that the recommended relief option requires a new NPA Code, the criteria for selection of an appropriate area code for relief is addressed in section 4.6 of the Canadian NPA Relief Planning Guideline. The criteria that should be taken into account when Future Canadian Geographic NPAs are being considered as candidates for relief of a specific current Canadian Geographic NPA include the following:

- The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in the area that is being relieved (Home NPA(s)).

- The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in another NPA within the same province where there is a possibility that a single new NPA Code could be overlaid on more than one NPA within the province, or where boundary realignment could occur that affects another NPA.

- The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in an Exchange Area in a neighbouring NPA, if the neighbouring NPA has 7-digit local calling within the NPA, and i) the Exchange Area in the neighbouring NPA where the CO Code is assigned has local calling to the NPA being relieved, or ii) the Exchange Area in the neighbouring NPA where the CO Code is assigned does not have local calling to the NPA being relieved, but other Exchange Areas within that neighbouring NPA have 7-digit local calling to the Exchange Area where the CO Code is assigned as well as local calling to the new NPA.

On the CNA web site at http://www.cnac.ca/npa_codes/relief/overview.htm there is an NPA Selection Tool that can assist in determining which of the NPA Codes that are currently available for assignment in Canada are most suitable for relief of an exhausting NPA.

For information extracted from the NPA Selection Tool that shows the suitability of Future Canadian Geographic NPA Codes for the relief of NPA 306, see Annex B, Table 3.

CO Codes corresponding to Future Canadian Geographic NPA Codes which are not assigned in NPA 306 and therefore meet criterion a) above are 437, 474, 568, 639, 851, 871, 879 and 942.

Criterion b) is not applicable since Saskatchewan has a single Numbering Plan Area.

Criterion c) is met by seven (7) of the eight (8) codes because none of them are assigned as CO Codes in Flin Flon MB or Lloydminster AB. All of the NPA Codes except 871 (437, 474, 568, 639, 851, 879 and 942) are therefore equally suitable as a new NPA Code for the relief of NPA 306, unless analysis of potential future code reservations for NPA reliefs in other areas of Canada, or TSP cost considerations indicate a preference for one code over another for the relief of NPA 306.

The NPA Code Selection Tool located on the CNA web site at http://www.cnac.ca/npa_codes/relief/overview.htm can assist in selecting a relief NPA Code from the pool of NPA Codes reserved for relief of geographic Canadian NPAs. The following table, extracted from the NPA Code Selection Tool, shows all codes corresponding to Future Canadian Geographic NPA Codes that are designated as unassignable CO Codes in the Home NPA, therefore are preferred candidates when selecting a relief NPA Code for NPA 306.

| NXX corresponding to Future NPA  | 437 | 474 | 568 | 639 | 851 | 871 | 879 | 942 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Split - Option 1 |  |  |  |  |  |  |  |  |
| Split - Option 2 |  |  |  |  |  |  |  |  |
| Split - Option 3 |  |  |  |  |  |  |  |  |
| Split - Option 4 |  |  |  |  |  |  |  |  |
| Distributed Overlay of New NPA Code on NPA 306 |  |  |  |  |  |  |  |  |

 	Indicates that corresponding CO Code is designated as unassignable in Home NPA(s)

	Indicates that corresponding CO Code is designated as an unsuitable NPA in split Option 2 and Option 4 due to criterion c) above. The NPA Code Selection Tool indicates that 871 is in-service CO Code in Lloydminster AB, which has 7-digit local dialling from Lloydminster SK.

Based on the above table, all of the Future Canadian Geographic NPA Codes which are not assigned in NPA 306, except 871, meet all the criteria for relief of NPA 306 and for the retention of 7-digit local dialling after relief if a split option is chosen as the Relief Method.

In CSCN TIF Report 87, dated 10 April 2010, re: Reservation of Future Canadian Geographic NPA Codes for relief of existing Canadian NPAs forecast to exhaust in the next 25 year timeframe, the CSCN submitted recommendations to the Commission for reserving NPA Codes for future relief of existing Canadian NPAs.

On 22 October 2010, the CRTC issued Telecom Decision CRTC 2010-784 CRTC Interconnection Steering Committee consensus item – Reservation of area codes for future area code relief. In this Decision, the CRTC directed the CNA to "set aside" the area codes proposed by the CSCN for future relief of existing in-service area codes that are forecast to exhaust during the next twenty (20) years. The CRTC noted in the Decision that if these area codes are required for other purposes before they are used as the CSCN has proposed, the CNA may request that the Commission approve their use for alternative assignments. See http://www.crtc.gc.ca/eng/archive/2010/2010-784.htm.

The CRTC included the following table in the Decision:

| Existing NPA | Description of NPA | Proposed area code reservation |
| --- | --- | --- |
| 226/519 | Southern Ontario | 548 |
| 289/365/905 | Toronto fringe, southern Ontario | 742 |
| 306 | Province of Saskatchewan | 474 |
| 416/647 | Toronto, Ontario | 437 |
| 506 | Province of New Brunswick | 428 |
| 709 | Province of Newfoundland and Labrador | 879 |
| 902 | Provinces of Nova Scotia and Prince Edward Island | 942 |

Given the above considerations, the NPA 306 RPC recommends that NPA Code 474 be the new relief NPA Code for the area code 306 region.

An additional factor requiring consideration when recommending a specific NPA Code for NPA 306 relief is that the NPA Code Selection Tool indicates CO Code 871 is In-service in Lloydminster AB, which has 7-digit local dialling from Lloydminster SK.

# RECOMMENDATIONS

Based on its analysis of the Relief Options, the Relief Planning Committee recommends that:

To be completed by RPC.

NPA 306

INITIAL PLANNING DOCUMENT

ANNEXES