

NPA 343/613 Proposal for Relief of an Overlay NPA Complex (PROC)

Version 1.0 – 30 September 2020

|  |  |
| --- | --- |
| Canadian Numbering Administrator (CNA)  Suresh Khare  613-702-0016 ext. 201  150 Isabella Street, Suite 605 Ottawa ON K1S 5H3  suresh.khare@cnac.ca |  |

**TABLE OF CONTENTS**

[1. INTRODUCTION 1](#_Toc52358124)

[2. NPA RELIEF PLANNING PROCESS 2](#_Toc52358125)

[3. NPA RELIEF METHODS 3](#_Toc52358126)

[4. NPA EXHAUST INFORMATION 3](#_Toc52358127)

[5. RELIEF OPTIONS 4](#_Toc52358128)

[5.1. Distributed Overlay 4](#_Toc52358129)

[6. SUMMARY OF RELIEF OPTIONS 5](#_Toc52358130)

[7. DIALLING CHANGES FOR LOCAL CALLS 5](#_Toc52358131)

[8. PROPOSED SCHEDULE 5](#_Toc52358132)

[9. JEOPARDY CONTINGENCY PLAN (JCP) 7](#_Toc52358133)

[10. SELECTION OF RELIEF NPA CODE 14](#_Toc52358134)

[11. RECOMMENDATIONS 15](#_Toc52358135)

[ANNEXES 16](#_Toc52358136)

**LIST OF ANNEXES**

**ANNEX A**

[Figure 1 – Overview Map of NPA 343/613 A-1](#_Toc52358137)

[Figure 2 – NPA 343/613 Actual and Forecast CO Code Assignments A-2](#_Toc52358138)

[Figure 3 – NPA 343/613 CO Code Exhaust: January 2020 R‑NRUF A-3](#_Toc52358139)

[Figure 4 – NPA 343/613 CO Code Exhaust: July 2020 R‑NRUF A-3](#_Toc52358140)

[Figure 5 – Distributed Overlay A-4](#_Toc52358141)

**ANNEX B**

[Table 1 – NPA 343/613/753 Exchange Areas After Distributed Overlay B-1](#_Toc52358142)

**ANNEX C**

Distribution List

**ACRONYM LIST**

|  |  |
| --- | --- |
| CATF | Consumer Awareness Task Force |
| CNA | Canadian Numbering Administrator |
| CISC | CRTC Interconnection Steering Committee |
| CLEC | Competitive Local Exchange Carrier |
| CLNPC | Canadian Local Number Portability Consortium |
| CO | Central Office |
| CRTC | Canadian Radio-television and Telecommunications Commission |
| CSCN | Canadian Steering Committee on Numbering |
| EAS | Extended Area Service |
| G-NRUF | General Numbering Resource Utilization Forecast |
| ILEC | Incumbent Local Exchange Carrier |
| IPD | Initial Planning Document |
| ISP | Internet Service Provider |
| JCP | Jeopardy Contingency Plan |
| J‑NRUF | Jeopardy Numbering Resource Utilization Forecast |
| LEC | Local Exchange Carrier |
| LIR | Local Interconnection Region |
| LNP | Local Number Portability |
| NANP | North American Numbering Plan |
| NANPA | North American Numbering Plan Administrator |
| NITF | Network Implementation Task Force |
| NoC | Notice of Consultation |
| NPA | Numbering Plan Area (Area Code) |
| NRUF | Numbering Resource Utilization Forecast |
| PD | Planning Document |
| PED | Projected Exhaust Date |
| PL | Planning Letter |
| POI | Point of Interconnection |
| PROC | Proposal for Relief of an Overlay NPA Complex |
| PSAP | Public Safety Answering Point |
| RIP | Relief Implementation Plan |
| R-NRUF | Relief Planning Numbering Resource Utilization Forecast |
| RPC | Relief Planning Committee |
| TSP | Telecommunications Service Provider |
| WNP | Wireless Number Portability |
| WSP | Wireless Service Provider |

**Proposal for Relief of an Overlay NPA Complex (PROC)**

**Numbering Plan Area (NPA) 343/613**

**Yellow highlight implies that these sections should be reviewed and updated in any planning document contribution(s).**

# INTRODUCTION

Numbering Plan Areas (NPAs) 416 and 613, commonly referred to as area codes, were originally assigned to Ontario by AT&T in 1947 as two of the 86 area codes to be used in Canada and the continental United States. In 1953 NPA 519 was split from NPA 416 and NPA 613 and in 1957 NPA 705 was split from NPA 519 and NPA 613.

In 2006, 10-digit local dialling was mandated by the Canadian Radio-television and Telecommunications Commission (CRTC) to provide relief for NPA 613 and in 2010 NPA 343 was introduced.

The following table provides a high-level summary of the history of area code usage in the area currently served by NPA 343/613 since 1947.

|  |  |
| --- | --- |
| **Year** | **Activity** |
| 1947 | Area Codes 416 and 613 are assigned to Ontario by AT&T |
| 1953 | Area Code 519 is split from 416 and 613 |
| 1957 | Area Code 705 is split from 519 and 613 |
| 2006 | 10-digit local dialling mandated to provide relief for NPA 613 |
| 2010 | New Area Code 343 overlays 613 |

NPA 343/613 consists of 132 Exchange Areas serving mainly Ottawa, Kingston, Belleville, Brockville, Cornwall and surrounding communities in the eastern part of Ontario, Canada. A list of the Exchange Areas in NPA 343/613 is provided in Annex B, Table 1.

| **Date** | **Activity** |
| --- | --- |
| 3 February 2017 | In Telecom Decision CRTC 2017-38, the Commission determined that area code 753 should be set aside as a potential future relief area code for area codes 343 and 613.  **For the purposes of this document the new NPA will be 753.** |
| 8 March 2018 | The Canadian Numbering Administrator (CNA) published the January 2018 G-NRUF results which indicated that the Projected Exhaust Date (PED) had advanced to February 2024. |
| 27 August 2018 | The CNA published the July 2018 R-NRUF results which indicated that the PED had advanced to August 2022. |
| 31 October 2018 | The CRTC released Telecom Notice of Consultation CRTC 2018‑409 - The Commission announces the establishment of a CRTC Interconnection Steering Committee ad hoc relief planning committee (RPC) to examine options and make recommendations for providing numbering relief to area codes 343 and 613 in Eastern Ontario. |
| 26 March 2019 | The CNA published the January 2019 R-NRUF results which indicated that the PED had deferred to December 2023. |
| 20 September 2019 | The CNA published the July 2019 R-NRUF results which indicated that the PED had moved out to September 2025. |
| 24 March 2020 | The CNA published the January 2020 R-NRUF results which indicated that the PED had advanced to June 2025. |
| 18 August 2020 | The CNA published the July2020 R-NRUF results which indicated that the PED had advanced to February 2024. |

This PROC is prepared by the CNA in accordance with Telecom Notice of Consultation CRTC 2018‑409 and the *Canadian NPA Relief Planning Guideline*, Version 7.0 dated 29 January 2019 (the Guideline). A copy of the Guideline is available from the Canadian Radio-Television and Telecommunications Commission (CRTC), CRTC Interconnection Steering Committee (CISC), Canadian Steering Committee on Numbering (CSCN) guidelines web page at: <https://crtc.gc.ca/cisc/eng/cisf3fg.htm>.

The objective of the NPA Relief Planning process is to ensure that CO Codes and telephone numbers are always available for use by TSPs and their customers in the geographic area requiring relief.

It is very important to closely monitor the CO Code requirements of all existing and prospective CO Code Holders so that relief can be timed to ensure that CO Codes and telephone numbers are always available for service providers and customers.

In this PROC, a single option is identified for providing NPA relief in the NPA 343/613 geographic area. Given the magnitude of this undertaking, intercompany commitment and co‑operation are essential throughout the planning, provisioning and implementation stages of the introduction of a new NPA.

# NPA RELIEF PLANNING PROCESS

The NPA Relief Planning process and the roles of the participants (i.e., CRTC, CNA, CISC, Relief Planning Committee (RPC) participants and Interested Parties) for NPA Relief Planning are identified in the Guideline.

To increase public awareness and participation in the NPA Relief Planning process, the CRTC has determined that NPA RPCs will be established as ad hoc committees of the CISC. Generally, a separate ad hoc committee is created to deal with relief in each area code. The CNA, in its function as NPA Relief Planning Coordinator, acts as chair of these ad hoc committees. Meetings and conference calls of the ad hoc NPA RPCs are all open to public participation and are conducted in accordance with the *CISC Administrative Guidelines* which are available from the CRTC website at: [<http://www.crtc.gc.ca/cisc/eng/cag.htm>](http://www.crtc.gc.ca/cisc/eng/cag.htm.).

NPA Relief Planning is conducted under the regulatory oversight of the CRTC. Notwithstanding the process detailed in the Guideline, the CRTC may exercise its authority under the *Telecommunications Act* to alter this process at any time. The CRTC has the authority under the *Telecommunications Act* to review, modify and give final approval to the Planning Document (PD) and the Relief Implementation Plan (RIP) developed and submitted by the RPC to the CRTC via the CISC process.

Section 7.1.6 of the *Canadian NPA Relief Planning Guideline* requires the CNA to create and maintain a distribution list of parties who may be interested in participating in the RPC and to provide them with advance notice of the initial RPC meeting and the release of a PROC.

Any person wishing to participate in the NPA Relief Planning process can contact the CNA and request to be added to the RPC distribution list. More information about how to participate in CRTC public processes is available at: <http://www.crtc.gc.ca/eng/info_sht/g4.htm>.

A summary of Canadian geographic area code relief history is available at: <http://www.cnac.ca/npa_codes/NPA_History.pdf>.

# NPA RELIEF METHODS

The purpose of this section is to identify and briefly describe NPA Relief Methods.

The Guideline states that: “The only NPA Relief Method considered in Canada is the Distributed Overlay Method which superimposes or “overlays” a Relief NPA on top of an entire existing NPA or NPAs.” There are three types of Distributed Overlay:

1. a Distributed Overlay over an existing geographic area served by a single existing NPA (A new NPA is overlaid over a single existing NPA (i.e., the geographic area) that is served by a single NPA.);
2. a Distributed Overlay over an existing geographic area served by multiple existing overlay NPAs (A new NPA is overlaid over a single existing NPA (i.e., the geographic area) that is served by multiple existing overlay NPAs); and,
3. a Distributed Overlay over multiple existing geographic areas, each served by one or more existing NPAs (A new NPA is overlaid over multiple existing NPAs (i.e., different geographic areas served by multiple NPAs. This type of overlay may be considered for NPA relief for two or more adjacent NPAs (i.e., geographic areas) within a province.).

# NPA EXHAUST INFORMATION

As indicated in the following table, NRUFs for NPA 343/613 were used to determine PEDs, i.e. the dates when CO Codes in NPA 343/613 would be expected to exhaust.

|  |  |
| --- | --- |
| **NRUF** | **Projected Exhaust Date (PED)** |
| G-NRUF January 2017 | April 2025 |
| G‑NRUF January 2018 | February 2024 |
| R-NRUF July 2018 | August 2022 |
| R-NRUF January 2019 | December 2023 |
| R-NRUF July 2019 | September 2025 |
| G&R-NRUF January 2020 | June 2025 |
| R-NRUF July 2020 | February 2024 |

Refer to, Figures 2 through 4 for graphs of forecast CO Code demand from current and prospective CO Code Holders and charts of Administrative Codes set aside in area code 343/613 for the two most recent NRUFs (January 2020 and July 2020).

# RELIEF OPTIONS

The Relief Option as identified and examined in this PROC is a Distributed Overlay over an existing geographic area served by multiple existing overlay NPAs.

Using this method, a new NPA is overlaid over an existing NPA (i.e., the geographic area). In this case the new NPA 753 will be overlaid over the geographic area currently served by NPA 343/613.

The Relief Option identified above was evaluated using the following assumptions:

1. The Five-Year Average growth values of 61 CO Codes was used to identify the subsequent PED for this Relief Option by comparing the 2020 July R-NRUF data in the table below:

|  |  |  |  |
| --- | --- | --- | --- |
| **Statistical Method** | **Data** | **Period** | **Quantity of CO Codes** |
| median | forecast growth | next six years | 83 |
| average | forecast growth | five-year period (January 2021 until January 2026) | 78 |
| average | forecast growth | next six years | 87 |
| average | forecast growth | next six years | 80 |
| average | historical growth | past five years | 73 |
| median | historical growth | past five years | 76 |

1. The Relief Date for the Distributed Overlay will be Q2 2023 (approximately 8 months prior to the NPA 343/613 PED of February 2024 identified using the July 2020 R‑NRUF results).

See Annex A, Figure 5 for diagram of the Distributed Overlay Relief Option identified by the CNA.

## Distributed Overlay

One Distributed Overlay Relief Option was evaluated which would overlay the NPA 753 over the 132 Exchange Areas comprising the NPA 343/613 area. See Annex A, Figure 5.

The introduction of a Distributed Overlay would keep the same number of NPA Relief Planning areas in Ontario.

After this Distributed Overlay, CO Codes in NPA 343/613/753 would be expected to exhaust in Q2 2034.

# SUMMARY OF RELIEF OPTIONS

|  |  |  |  |
| --- | --- | --- | --- |
| **Relief Option** | **Projected Exhaust Dates** | | **Subsequent Relief Dates** |
| **NPA 343/613** | **NPA 343/613/753** |
| Distributed Overlay | February 2024 | May 2034 | May 2033 |

**Note: For a Distributed Overlay NPA 753 would be in service in Q2 2023.**

# DIALLING CHANGES FOR LOCAL CALLS

Currently 10-digit dialling is mandatory for local calls originating within area code NPA 343/613 and all neighbouring NPAs (i.e., NPA 249/705, NPA 289/365/905, NPA 450/579 and NPA 819/873). Local dialling plans will not change with this relief.

# PROPOSED SCHEDULE

The CNA submits the following schedule for NPA 343/613 relief based on the recommendations contained in this PROC and the current PED of February 2024. The RPC will monitor the PED, and if it changes significantly in the future, the RPC will assess the situation and, if necessary, submit recommendations including a revised schedule to the CRTC for consideration and approval.

**RELIEF IMPLEMENTATION SCHEDULE**

**For a Distributed Overlay of NPA 753 over NPA 343/613**

[Insert proposed schedule from Excel worksheet]

# JEOPARDY CONTINGENCY PLAN (JCP)

The CNA has provided the template below to assist the RPC with the development of the Jeopardy Contingency Plan (JCP).

The RPC has developed the following JCP for inclusion in the PD for NPA 343/613. This JCP is based on the example contained in Appendix F to the *Canadian NPA Relief Planning Guideline*.

This JCP shall remain in effect until superseded by a CRTC-approved JCP, the Jeopardy Condition is suspended or 66 days prior to the Relief Date.

The following measures shall be implemented in NPA 343/613 while a Jeopardy Condition is in effect.

During a Jeopardy Condition, CO Code Applicants shall submit all CO Code applications and related correspondence for the Jeopardy NPA to CRTC staff in addition to the CNA. The CNA shall only assign CO Codes from the exhausting NPA to a CO Code Applicant when instructed by CRTC staff.

1. Carriers and/or Telecommunications Service Providers (TSPs):
   1. shall age disconnected residential wireline telephone numbers for a maximum of two months;
   2. shall age disconnected wireless telephone numbers for a maximum of three months;
   3. shall age disconnected business wireline telephone numbers for a maximum of six months. Under special circumstances, the six month aging limit for business telephone numbers may be extended to twelve months, if required, to accommodate local directory publishing dates for high volume call-in applications (e.g., heavily advertised local business numbers such as radio talk shows, food ordering services, ticket sales, chat lines), or for numbers associated with public service emergency applications or for numbers advertised in directories for which customers have requested reference of calls;
   4. shall return all CO Codes that are not being used, nor intended to be used to directly serve customers to the assignment pool within two months (e.g., plant test codes);
   5. should work towards, and encourage existing customers, to either activate or return the reserved numbers to bring the reserved quantity down to a maximum of 10% of the quantity of numbers In-Service for that customer;
   6. shall not allow the quantity of reserved numbers to be increased by new reservation requests by existing customers to more than 10% of the quantity of numbers in service for that customer. In the case of new customers, number reservations shall be limited to 10% of the total quantity of telephone numbers being placed into service for that customer;
   7. shall, within 45 days from the date that the CNA declares a Jeopardy Condition submit a Part 1 Form for each remaining reserved CO Code either returning the reserved CO Code to the CNA or requesting assignment of the reserved CO Code. Once the 45-day period has elapsed, the CNA shall make available for general assignment all CO Codes that are still reserved and have not been applied for as assignments on a Part 1 Form received by the CNA. Within 60 days from the date that the CNA declares a Jeopardy Condition, the CNA shall report to CRTC staff and the RPC as to how many of these codes have been assigned or made available for general assignment;
   8. shall not be permitted to obtain a new CO Code reservation;
   9. shall place all CO Codes assigned prior to the Jeopardy Condition being declared In-Service within three months of the effective date for CO Code activation in the network, or within three months of the date that the Jeopardy Condition was declared. If the CO Code is an Initial Code and the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-Service date has been delayed beyond the applicable timeframe, then the CNA may grant an extension of up to two months to the In-Service date. The CNA shall initiate reclamation procedures for all CO Codes that have not been placed In-Service within these timeframes unless CRTC staff provides a further extension.
2. For new applications for Initial Codes, each CO Code Holder shall certify that the CO Code will be activated in the network and placed In-Service within four months of the date of application for the Code. If the CNA does not receive a Part 4 Form within this timeframe, confirming that the CO Code has been placed In-Service, the CNA will initiate reclamation measures. If the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-Service date has been delayed not more than six months from the original application date, then the CNA may grant an extension to the In-Service date, so long as the In-Service date is not more than six months beyond the original application date. If the In-Service date has been delayed more than six months from the original application date, then the CNA shall reclaim the Code unless CRTC staff provides a further extension.
3. When applying for an Additional Code for Growth, a CO Code Holder who is submitting a Part 1 Form and Appendix B worksheet shall also submit a completed Supplementary Form for a Growth CO Code Application (attached) which certifies and/or provides the following information for the specific switching entity/POI and Exchange Area when the Growth CO Code is being requested in a Jeopardy Condition:
   1. certification that all held telephone numbers have been released;
   2. certification that reserved numbers do not exceed ten percent of the total quantity of numbers as defined in Appendix G of the Canadian CO Code (NXX) Assignment Guideline;
   3. certification that each reseller/dealer had been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two times the highest quantity of customer numbers assigned in any month during the previous 12 months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three months' inventory;
   4. confirmation that the Part 1 form submitted with the application has the Jeopardy Condition box in section 1.6 checked to certify that the existing CO Codes are projected to exhaust within 4 months of the date of application and that the months-to-exhaust is documented on an Appendix B submitted to the CNA;
   5. a completed Telephone Number Utilization Report for the applicable switching entity signed by both a company officer and the company’s authorized representative;
   6. confirmation that the requested Growth CO Code was forecasted in the most recent NRUF or an explanation as to why it was not is attached; and,
   7. confirmation that the requested Growth CO Code will be placed In-Service within four months of the date of assignment.
4. Any CO Codes for growth assigned after the implementation of this JCP must be activated in the network and placed In-Service within four months of assignment. In the event that a CO Code Holder is unable to place the CO Code In-Service within four months of the date of assignment, the CO Code Holder must return the assigned CO Codes or submit a written request for extension to the CNA. Such written requests must include documentation explaining the reason(s) for the missed date and proposing the new In-Service date. If the explanation includes reasons beyond the control of the CO Code Holder, the CNA may extend the In-Service date a maximum of one month. If the CO Code Holder does not place the CO Code In-Service within the one-month extension, the CNA shall initiate the reclamation process at the end of the one-month extension unless CRTC staff provides a further extension.
5. A Carrier that has multiple switching entities within an Exchange Area shall examine the possibility of, and implement where feasible, number sharing between those switches as a potential method to delay requirements for additional CO Codes.
6. The CNA will request two versions (two separate worksheets (Form 1 and Form 2)) of the J-NRUF input from all current and prospective CO Code Holders quarterly until three (3) months before relief is provided.
   1. The forecast quantities in Form 1 should be the same as or lower than the last R‑NRUF input submitted, prior to declaration of a Jeopardy Condition. CO Code Holder forecasts may reflect an increase in demand in the period subsequent to the Relief Date.
   2. Form 2 will reflect the actual demand required by the CO Code Holder's current business plan and will be provided for information purposes only.
7. The CNA will compare the initial J-NRUF input to the recent NRUF inputs, to assess forecasting trends. The CNA shall monitor all inputs and shall test them for reasonableness in consultation with the Carrier. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the deviations, then the matter will be referred to the CRTC staff.
8. The CNA will request subsequent J-NRUF input from all current and prospective CO Code Holders quarterly until 3 months before relief is provided. If one or more R-NRUFs have already been conducted, and depending on the severity of the Jeopardy Condition, the CNA may defer a J-NRUF by up to two months if such a deferral brings the timing of that J‑NRUF and subsequent J-NRUFs into alignment with other NRUFs that are conducted at 12, 6 or 3 month intervals. Subsequent J-NRUF input will be compared with the initial J‑NRUF input to evaluate the effectiveness of the JCP. The CNA shall monitor all J-NRUF inputs and shall test them for reasonableness in consultation with the Telecommunications Service Providers. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the changed forecasts, then the matter will be referred to CRTC staff.
9. A CO Code Applicant must have submitted a completed J-NRUF to the CNA before the CNA may assign a CO Code to that CO Code Applicant.
10. If a CO Code applicant wishes to request more CO Codes than it identified in its most recent J NRUF, the CO Code Applicant should discuss the matter with the CNA. If the CO Code Applicant wishes to proceed with the request, the CO Code Applicant will forward the request and revised forecast to CRTC staff and the CNA for consideration.
11. The CO Codes identified in the NPA CO Code Inventory Chart as “Assignable CO Codes in a Jeopardy Condition” will be assigned in the order determined by the RPC after all CO Codes which are “Available for Assignment as of [day month year] have been assigned.
12. After each J-NRUF, the CNA shall provide CRTC staff, the RPC and CSCN participants with a report providing an updated NPA CO Code Inventory Chart for the NPA in jeopardy as well as the aggregate results of the most recent J-NRUF.
13. Exceptional issues or concerns may be referred by the CNA, or by individual entities (with a courtesy copy to the CNA), to the CRTC staff for resolution.
14. In a situation where the Relief Date is on or after the PED, the quantity of CO Codes that may be assigned to a CO Code Applicant prior to the end of the Jeopardy Condition (i.e. 66 days prior to the Relief Date) shall be limited to the quantity forecasted by the CO Code Applicant in its most recent NRUF forecast submitted prior to the Jeopardy Condition being declared by the CNA (if no previous NRUF was submitted, then the previous forecast will be deemed to be zero codes). When making requests to obtain CO Codes prior to the end of the Jeopardy Condition (i.e. 66 days prior to the Relief Date), the CO Code Applicant may change the Exchange Area or the month when the CO Code assignment is required, provided a new J-NRUF and explanation accompanies the application. The control imposed by this option may be relaxed if subsequent J-NRUFs defer the PED to after the Relief Date. CO Codes that become available for assignment due to future reduced demand from other current and prospective CO Code Holders may be assigned at the discretion of CRTC staff.
15. If the CNA determines that the implementation of the JCP has not extended the Projected Exhaust Date of the NPA beyond the Relief Date, the CNA will consult with CRTC staff and further CO Code conservation and assignment procedures may be ordered by the Commission (e.g., rationing, lottery, etc.).

.

Supplementary form for a Growth CO Code Application – Page 1 of 2 – Telephone Number Utilization Report

This form is required with each request for an Additional Code for Growth in an NPA where a Jeopardy Condition is in effect. It should be submitted to the CNA together with the Part 1 and Appendix B forms that are required for an application for an Additional Code for Growth. See the Part 1 form for information on how and where to submit the form.

I hereby certify that the following information is true and accurate to the best of my knowledge and has been prepared in accordance with Special Conservation Procedures for a Jeopardy Condition contained in the *Canadian NPA Relief Planning Guideline* or the applicable approved Jeopardy Contingency Plan.



Name & Signature of Authorized Representative of Code Holder Title Date



Name & Signature of Company Officer (see item 3 of this JCP) Title Date

Contact information: Entity Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Contact Name: \_\_\_\_\_\_\_\_\_\_\_\_\_

Address: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ City, Province, Postal Code: \_\_\_\_\_\_\_\_\_\_\_\_\_

Telephone: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Facsimile: \_\_\_\_\_\_\_\_\_\_\_\_\_

E-mail: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Switch Identification (Switching Entity/POI) CLLI: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Exchange Area: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

For the above Switch Identification and Exchange Area for which a Growth CO Code is requested:

I certify that all held telephone numbers have been released

I certify the total quantity of reserved numbers does not exceed ten percent (10%) of the total quantity of telephone numbers as defined in Appendix G of the *Canadian CO Code (NXX) Assignment Guideline*

I certify that each reseller/dealer has been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two (2) times the highest quantity of customer numbers assigned in any month during the previous twelve (12) months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three months' inventory.

The Part 1 form submitted with the application has the Jeopardy Condition box in section 6 checked (this certifies that the existing CO Codes are projected to exhaust within four (4) months of the date of the application or within the period specified in an approved Jeopardy Contingency Plan, and that the months-to-exhaust is documented on an Appendix B submitted to the CNA).

The Telephone Number Utilization Report on page 2 of this form has been completed.

The requested Growth CO Code was forecasted in the most recent NRUF, or an explanation as to why it was not is attached.

The requested Growth CO Code will be placed In-Service within four (4) months of the date of assignment.

**Supplementary Form for a Growth CO Code Application – Page 2 of 2 – Telephone Number Utilization Report**

Use Arial 9 to complete this form. (Note: If the spreadsheet below does not show on your display, please change the Work view to "Print Layout" or "Reading Layout")



Remarks: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**NPA 343/613 CO Code Inventory Chart**

The following chart and the instructions it contains will apply in NPA 343/613 in a Jeopardy Condition.

The chart below lists quantities of CO Codes unassignable prior to a Jeopardy Condition, CO Codes that become assignable in a Jeopardy Condition and CO Codes in NPA 343/613 assigned and In‑service as of 30 September 2020. The CO Codes that become assignable in a Jeopardy Condition shall only be made available for assignment when all other available CO Codes have been assigned in the order listed below.

|  |  |  |
| --- | --- | --- |
|  |  | **Quantity** |
| **A** | **Total CO Codes in NPAs 343/613** **(NXX format)** | **1,600** |
|  | | |
| **B** | **CO Codes unassignable prior to a Jeopardy Condition** |  |
|  | N11 Service Codes (211, 311, 411, 511, 611, 711, 811, 911) | 16 |
|  | Special Use Codes (555, 950 & 976) | 5 |
|  | Home NPA Codes (343, 613) | 4 |
|  | Current Neighbouring NPA Codes (289, 365, 450, 579, 819, 873, 905) | 14 |
|  | Future Geographic NPA Codes (460, 468, 568 ,753, 871, 942)  (Note 1) | 12 |
|  | Plant Test Codes (958 & 959) | 4 |
|  | Special 7-digit Dialling Codes (310, 610 & 810) | 5 |
|  | **Total B** | 60 |
|  | | |
| **C** | **CO Codes assignable prior to a Jeopardy Condition (C=A-B)** | **1,540** |
|  | | |
| **D** | CO Codes unassignable prior to a Jeopardy Condition that become assignable in a Jeopardy Condition: |  |
| Future Canadian Geographic NPA Codes (Notes 1 & 2) | 10 |
| Current Neighbouring NPA Codes (289, 365, 450, 579, 819, 873, 905) (Note 3) | 14 |
| **Total D** | 24 |
|  | | |
| **E** | **Assignable CO Codes in a Jeopardy Condition (E=C+D)** | **1,564** |
| **F** | **Assigned CO Codes as of 30 September 2020** | **1,207** |
| **G** | **Net CO Codes available for assignment as of 30 September 2020 without a Jeopardy Condition (G=C-F)** | 333 |
| **H** | **Net CO Codes available for assignment as of 30 September 2020 in a Jeopardy Condition (H=E-F)** | 357 |

**Notes:**

1. In Telecom Decision CRTC 2017-38, the Commission determined that area code 753 should be set aside as a potential future relief area code for area codes 343 and 613.
2. CO Codes 460, 468, 568, 871 and 942 should become assignable in a Jeopardy Condition.
3. In an extreme Jeopardy Condition (i.e., when the Projected Exhaust Date is earlier than the Relief Date), the current Neighbouring NPA Codes 289, 365, 450, 579, 819, 873, and 905 could be assignable with CRTC staff approval.

# SELECTION OF RELIEF NPA CODE

In the event that the recommended relief option requires a new NPA Code, the criteria for selection of an appropriate area code for relief is addressed in section 4.10 of the *Canadian NPA Relief Planning Guideline*. The criteria that should be taken into account when Future Canadian Geographic NPAs are being considered as candidates for relief of a specific current Canadian Geographic NPA include the following:

1. The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in the area that is being relieved (Home NPA(s)).
2. The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in another NPA within the same province where there is a possibility that a single new NPA Code could be overlaid on more than one NPA within the province, or where boundary realignment could occur that affects another NPA.
3. The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in an Exchange Area in a neighbouring NPA, if the neighbouring NPA has 7-digit local calling within the NPA and i) the Exchange Area in the neighbouring NPA where the CO Code is assigned has local calling to the NPA being relieved or ii) the Exchange Area in the neighbouring NPA where the CO Code is assigned does not have local calling to the NPA being relieved, but other Exchange Areas within that neighbouring NPA have 7-digit local calling to the Exchange Area where the CO Code is assigned as well as local calling to the new NPA.

CO Codes corresponding to Future Canadian Geographic NPA Codes which are not assigned in NPA 343/613 and therefore meet criterion a) above are 460, 468, 568 ,753, 871, and 942.

CO Codes 460, 468, 568, 753, 871, and 942 are all assigned in at least one neighbouring NPA so none of these resources meet criterion b).

Criterion c) is not applicable since NPA 343/613 and all neighbouring NPAs have 10-digit local calling.

The NPA Code Selection Tool located on the CNA web site at <http://www.cnac.ca/npa_codes/relief/NPA_Selection_Tool.xlsx> can assist in selecting a relief NPA Code from the pool of NPA Codes reserved for relief of geographic Canadian NPAs. The following table, extracted from the NPA Code Selection Tool, shows all CO Codes corresponding to Future Canadian Geographic NPA Codes that are designated as unassignable CO Codes in the Home NPA, and therefore are preferred candidates when selecting a relief NPA Code for NPA 343/613.

| **NXX corresponding to Future NPA** | **460** | **468** | **568** | **753** | **871** | **942** |
| --- | --- | --- | --- | --- | --- | --- |
| Distributed Overlay | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |

✓ Indicates that corresponding CO Code is designated as unassignable in Home NPA(s)

All of the NPA Codes (460, 468, 568, 753, 871, and 942) are therefore equally suitable as a new NPA Code for the relief of NPA 343/613, unless analysis of potential future code reservations for NPA reliefs in other areas of Canada, or TSP cost considerations indicate a preference for one code over another for the relief of NPA 343/613.

In Telecom Decision CRTC 2017-38, the Commission determined that area code 753 should be set aside as a potential future relief of Eastern NPA complex 343/613 but could be used elsewhere if required.

# RECOMMENDATIONS

The CNA recommends:

1. The Relief Method should be a distributed overlay of a new NPA Code on Eastern Ontario NPA 343/613;
2. The Relief NPA Code for NPA 343/613 should be NPA 753 as per Telecom Decision CRTC 2017-38; and
3. The Relief Date should be 10 June 2023 to provide Carriers and customers with advanced notification and sufficient lead-time to implement relief in NPA 343/613.

ANNEXES

**Proposal for Relief of an Overlay NPA Complex (PROC)**

**Numbering Plan Area (NPA) 343/613**

Maps and Figures

1. Maps and Figures




Figure 1 – Overview Map of NPA 343/613



Figure 2 – NPA 343/613 Actual and Forecast CO Code Assignments



Figure 3 – NPA 343/613 CO Code Exhaust: January 2020 R‑NRUF



Figure 4 – NPA 343/613 CO Code Exhaust: July 2020 R‑NRUF




Figure 5 – Distributed Overlay

1. NPA 343/613/753 Exchange Areas

Table 1 – NPA 343/613/753 Exchange Areas After Distributed Overlay

| **NPA 343/613/753**  **Exchange Areas** |
| --- |
|
|
| Adolphustown |
| Alexandria |
| Alfred |
| Almonte |
| Arden |
| Arnprior |
| Athens |
| Avonmore |
| Bancroft |
| Barry's Bay |
| Bath |
| Beachburg |
| Belleville |
| Bloomfield |
| Bourget |
| Brighton |
| Brockville |
| Calabogie |
| Cardiff |
| Cardinal |
| Carleton Place |
| Carp |
| Casselman |
| Chalk River |
| Chesterville |
| Clarence Creek |
| Cobden |
| Coe Hill |
| Constance Bay |
| Cornwall |
| Crysler |
| Cumberland |
| Deep River |
| Delta |
| Denbigh |
| Deseronto |
| Douglas |
| Eganville |
| Elgin |
| Embrun |
| Enterprise |
| Finch |
| Foymount |
| Frankford |
| Gananoque |
| Gilmour |
| Glen Robertson |
| Gloucester |
| Golden Lake |
| Harrowsmith |
| Hawkesbury |
| Ingleside |
| Inverary |
| Iroquois |
| Jockvale |
| Kanata-Stittsville |
| Kemptville |
| Killaloe |
| Kingston |
| L'Orignal |
| Lanark |
| Lancaster |
| Lansdowne |
| Long Sault |
| Maberly |
| Madoc |
| Maitland |
| Mallorytown |
| Manotick |
| Marmora |
| Martintown |
| Maxville |
| Maynooth |
| McDonalds Corners |
| Merrickville |
| Metcalfe |
| Moose Creek |
| Morrisburg |
| Napanee |
| Navan |
| Newburgh |
| North Augusta |
| North Gower |
| Northbrook |
| Odessa |
| Orleans |
| Osgoode |
| Ottawa-Hull |
| Pakenham |
| Palmer Rapids |
| Parham |
| Pembroke |
| Pembroke Independent |
| Perth |
| Petawawa |
| Picton |
| Plantagenet |
| Plevna |
| Portland |
| Prescott |
| Renfrew |
| Richmond |
| Rockland |
| Rolphton |
| Russell |
| Seeleys Bay |
| Selby |
| Sharbot Lake |
| Smiths Falls |
| South Mountain |
| Spencerville |
| St-Regis |
| St. Eugene |
| St. Isidore |
| Stirling |
| Sydenham |
| Tamworth |
| Thurlow |
| Toledo |
| Trenton |
| Tweed |
| Vankleek Hill |
| Verona |
| Wellington |
| Westmeath |
| Westport |
| Whitney |
| Williamsburg |
| Winchester |
| Wolfe Island |
| Wooler |
| Yarker |

1. Distribution List

|  |  |
| --- | --- |
| Iristel  team.regulatory@iristel.com | Iristel Inc.  11 Bowan Court  Toronto, ON  Canada  M2K 3A8  didorders@iristel.com |
| Rogers  NumberAdmin@rci.rogers.com | CLEC Admin  Comwave Networks  61 Wildcat Road  Toronto, ON  Canada  M3J 2P5  clecteam@comwave.net |
| Numbering E-Mail  Distributel Communications Limited  177 Nepean Street  Ottawa, ON  Canada  K2P 0B4  numbering@distributel.ca | NXX Admin  Bell Canada  nxx.admin@bell.ca |
| Edward Antecol  VP Professional Services  COMsolve Inc.  70 East Beaver Creek Road, #202  Richmond Hill, ON  Canada  L4B 3B2  Telephone: 613-702-0016 ext. 106  Edward.Antecol@cnac.ca | Andreea Badea  Iristel Inc.  11 Bowan Court  Toronto, ON  Canada  M2K 3A8  Telephone: 416-800-4747  abadea@iristel.ro |
| Jenoshan Balasingam  IXICA Communications Inc.  174 Shropshire Drive  Toronto, ON  Canada  M1P 1Z7  Telephone: 844-747-2729 ext: 1100  jenoshan@ixica.com | Ron Barzakay  CTO  Comwave Networks  61 Wildcat Rd  Toronto, ON  M3J 2P5  Telephone: 416-663-9700 X 302  Fax: 416-736-3150  rbarzakay@comwave.net |
| Geoff Batstone  V.P., General Counsel  Distributel Communications Limited  177 Nepean Street, Suite 300  Ottawa, ON  Canada  Telephone: 613-319-9964  geoff.batstone@distributel.ca | Nicholas Bayly  Carrier Services Specialist  Shaw Business  3636 23 ST NE  Calgary, AB  Canada  T2E 6Y7  Telephone: 403-538-5223  nicholas.bayly@sjrb.ca |
| Tim Beach  Vice President Operations  Roxborough Telephone Company Limites (OCN 287H)  P.O Box 190  Moose Creek, ON  K0C1W0  Telephone: 613-538-7071  Fax: 613-538-8002  tjwbeach@ontarioeast.net | Marc Berruyer  Network Planner  Videotron General Partnership  2155 Boul. Pie IX, 3e etage, bloc A  Montreal, QC  Canada  H1V 2E4  Telephone: 514-380-4255  Fax: 514-899-8452  marc.berruyer@videotron.com |
| Vivek Bhardwaj  Traffic Specialist  Rogers Communications  8200 Dixie Rd.  Brampton, ON  Canada  L6T 0C1  Telephone: 647-747-3569  vivek.bhardwaj@rci.rogers.com | Pavel Bigarov  CNA System Administrator  Canadian Numbering Administrator  150 Isabella Street - Suite 605  Ottawa, ON  Canada  K1S 5H3  Telephone: 613-702-0016  pavel.bigarov@cnac.ca |
| Olena Bilozerska  Network Planning Manager I, TS CC Planning & Management  TELUS  200 Consilium Place, Floor 6  Scarborough, ON  Canada  M1H 3G2  Telephone: 647-837-1798  Olena.Bilozerska@telus.com | Doug Birdwise  Interested Party  109 Westpark Drive  Ottawa, ON  Canada  K1B 3G4  Telephone: 613-830-0081  douglas.birdwise@sympatico.ca |
| Samer Bishay  CEO  Iristel Inc.  11 Bowan Court  Toronto, ON  Canada  M2K 3A8  Telephone: 416-800-9999  Fax: 416-628-0891  sbishay@iristel.com | Laurie Bowie  Network Planning  Bell Canada  100 Dundas Street, Floor 3  London, ON  Canada  N6A 5B6  Telephone: 519-850-5818  laurie.bowie@bell.ca |
| Kim Brown  Carrier Services Manager  Eastlink  PO Box 8660, Station “A”: 6080 Young St, 7th Floor  Halifax, NS  Canada  B3K 5M3  Telephone: 902-446-3794  Fax: 902-405-3426  kim.brown@corp.eastlink.ca | Bruce Buchanan  Manager, Network Operations  Nexicom Telecommunications Inc.  5 King St. E.  Millbrook, ON  L0A1G0  Telephone: 705-932-4147  Fax: 705-775-4147  bbuchana@nexicomgroup.net |
| Melanye Caisse  Telecom Analyst  ISP Telecom Inc  1155 Boul Rene-Levesque Ouest Suite 2500  Montreal, QC  Canada  H3B 2K4  Telephone: 416-548-4819  Fax: 416-548-4818  melanye@isptelecom.net | Tim Calamari  Director, Telecom and System Services  Globalstar  300 Holiday Square Blvd  Covington, LA  USA  70433  Telephone: 985-335-1583  Tim.Calamari@globalstar.com |
| Don Cavanagh  VP  Distributel Communications Limited  177 Nepean Street, Suite 300  Ottawa, ON  Canada  K2P 0B4  Telephone: 613-237-7005  Fax: 613-237-7009  donald.cavanagh@distributel.ca | Fiona Clegg  Numbering Resource Administration  Canadian Numbering Administrator  150 Isabella Street, Suite 605  Ottawa, ON  Canada  K1S 5H3  Telephone: 613-702-0016 ext. 202  fiona.clegg@cnac.ca |
| David Comrie  Numbering Resource Administration  Canadian Numbering Administrator  150 Isabella Street, Suite 605  Ottawa, ON  Canada  K1S 5H3  Telephone: 613-702-0016 ext. 204  david.comrie@cnac.ca | Doug Cooper  Director Network Planning and Profitability  Distributel  801-3300 Bloor St. West  Toronto, ON  M8X2X2  Telephone: 647-317-2924  doug.cooper@distributel.ca |
| James Deane  CEO & Corporate Officers  Access Communications  2250 Park St  Regina, SK  S4N7K7  Telephone: 306-565-5340  Fax: 306-565-5395  jim.deane@myaccess.coop | Zahra Deliri  Contractor  Shaw Telecom Inc.  Telephone: 587-390-2964  Zahra.Deliri@sjrb.ca |
| Jeffrey DeSarno  Chief Tehnology Officer  Access Communications Co-operative Limited  2250 Park St  Regina, SK  S4N 7K7  Telephone: 306-565-5364  Fax: 306-565-5395  jeffrey.desarno@myaccess.coop | Diane Dolan  Voice Service Manager  TekSavvy Solutions Inc  227 rue Montcalm  Gatineau, QC  Canada  J8Y 3B9  Telephone: 819-484-1234  ddolan@teksavvy.ca |
| Irma Dulay  Primus Telecommunications Canada Inc.  500- 5343 Dundas St West  Toronto, ON  Canada  M9B 6K5  Telephone: 416-207-7151  Fax: 877-329-6875  idulay@primustel.ca | Jean-François Dumoulin  VP, Regulatory and Government Affairs  Iristel  Canada  Telephone: 514-800-1577  jdumoulin@iristel.com |
| Diane Faillant  Associate - Network Management/NSS (National Numbering Solution)  Bell Canada  671 LAGAUCHETIERE Ouest. 11  Montreal, QC  Canada  H3B 2M8  Telephone: 514-870-6044  Fax: 514-786-9062  diane.faillant@bell.ca | Johny Fernandez  Technology Strategy  TELUS Mobility  200 Consilium Place, 6th Flr  Scarborough, ON  Canada  M1H 3J3  Telephone: 647-453-4442  Johny.fernandez@telus.com |
| Jesse Gasteiger  ExaTEL Inc  128 Larch St., Suite 301  Sudbury, ON  Canada  P3E5J8  Telephone: 705-675-0400  Fax: 705-675-0404  jesse@vianet.ca | Marlo Gelito  Engineer II - TRANSLATIONS & TRAFFIC NETWORK OPERATION  TELUS  3777 Kingsway, Floor 07  Burnaby, BC  V5H 3Z7  Telephone: 604-695-3189  marlo.gelito@telus.com |
| Iann Gorrill  Manager, Network Services  Access Communications  2250 Park St  Regina, AB  S4N7K7  Telephone: 306-565-5396  Fax: 306-565-5395  iann.gorrill@myaccess.coop | William Grier  General Manager  Lansdowne Rural Telephone Co. Ltd.  42 King St. West, PO BOX 9  Landsdowne, ON  Canada  K0E 1L0  Telephone: 613-659-2222  Fax: 613-659-2226  Wagrier@1000island.net |
| Praba Gunam  President/CEO  InnSysVoice Corp.  4500 Sheppard Ave E, Suite 111  Toronto, ON  Canada  M1S 3R6  Telephone: 416-800-0797  praba@innsys.ca | Pierre Guynot de Boismenu  Manager of Core Network Engineering and Operations, Wireless  Bragg Communications Inc  60800 Young St 6th Floor  Halifax, NS  Canada  B3K 5L2  Telephone: 902-414-8020  Fax: 902-444-1019  pierre.guynotdeboismenu@corp.eastlink.ca |
| Carmela Haines  Chief Operating Officer  Access Communications  2250 Park St  Regina, SK  S4N7K7  Telephone: 306-565-5351  Fax: 306-565-5395  carmela.haines@myaccess.coop | Deborah Hartwick  Administration  North Frontenac Telephone Company Limited  1019 Windwood Dr.  Sharbot Lake, ON  Canada  K0H 2P0  Telephone: 613-279-2193  Fax: 613-279-2222  dhartwick@nftctelecom.com |
| Isaac Hayford  Network Analyst  Access Communications  2250 Park St  Regina, SK  S4N7K7  Telephone: 306-565-5339  Isaac.Hayford@myaccess.coop | Austin He  Network Planning Analyst, Network Planning  Primus Management ULC.  2680 Skymark Avenue, Suite 100  Mississauga, ON  Canada  L4W 5L6  Telephone: 416-207-3361  AHe@primustel.ca |
| Marian Hearn  Project Executive  Canadian LNP Consortium Inc.  350 Palladium Drive, Suite 208  Kanata, ON  Canada  K2V 1A8  Telephone: 613-287-0225  Fax: 800-406-9250  marian.hearn@clnpc.ca | Pierre-Luc Hebert  Assistant General Counsel  Bell Canada  160 Elgin St.  Ottawa, ON  Canada  K1G 3J4  Telephone: 613-785-6363  p.l.hebert@bell.ca |
| Lynne Hewitson  Membership Manager  Canadian Security Association (CANASA)  610 Alden Road  Markham, ON  Canada  L3R 9Z1  Telephone: 905-513-0622 ext 223  Fax: 905-513-0624  membership@canasa.org | Larry Hishon  Senior Network Engineer  Fibernetics Corporation  605 Boxwood Drive  Cambridge, ON  Canada  N3E 1A5  Telephone: 519-571-7433  Fax: 519-772-5014  lhishon@fibernetics.ca |
| Rhonda Hunt  Lansdowne Rural Telephone Company  Lansdowne, ON  Canada  Telephone: 613-659-2222  Fax: 613-659-2226  rhunt@1000island.net | Stephanie Jackson  Manager - Public Services Integration; Traffic Engineering  Rogers Communications Canada Inc.  8200 Dixie Road  Brampton, ON  Canada  L6T 0C1  Telephone: 647-747-4402  Fax: 647-747-4557  stephanie.jackson@rci.rogers.com |
| Lien Kaura  Carrier Service Specialist  Shaw Communications Inc.  2441 37th Ave NE  Calgary, AB  Canada  T2E 6Y7  Telephone: 587-390-2982  Lien.Kaura@sjrb.ca | Suresh Khare  CO Code Manager  Canadian Numbering Administrator  150 Isabella Street, Suite 605  Ottawa, ON  Canada  K1S 5H3  Telephone: 613-702-0016 ext. 201  suresh.khare@cnac.ca |
| Phillip Koneswaran  VP - Business  IXICA Communications Inc.  174 Shropshire Drive  Toronto, ON  Canada  M1P 1Z7  Telephone: 844-747-2729 ext: 2100  phillip@ixica.com | Natalie Lessard  Numbering Resource Administration  Canadian Numbering Administrator  150 Isabella Street, Suite 605  Ottawa, ON  Canada  K1S 5H3  Telephone: 613-702-0016 ext. 203  natalie.lessard@cnac.ca |
| Angel Loyacano  Telecom Analyst  Globalstar  300 Holiday Square Blvd  Covington, LA  USA  70433  Telephone: 985-335-1663  Angel.Loyacano@globalstar.com | Steve Lynn  General Manager  Westport Telephone Company Limited  28 Main Street, P.O. Box 580  Westport, ON  Canada  K0G 1X0  Telephone: 613-273-0104  Fax: 613-273-2323  steve@wtccommunications.ca |
| Jennifer Mack  Traffic Specialist  Rogers Communications  8200 Dixie Rd.  Brampton, ON  Canada  L6T 0C1  Telephone: 647-747-2168  jennifer.mack@rci.rogers.ca | Wanda Marie Mali  Manager - National Numbering Solutions  Bell Canada  100 Borough Dr, Floor 5 Blue  Scarborough, ON  M1P4W2  Telephone: 416-296-6076  Fax: 416-296-0685  wanda\_marie.mali@bell.ca |
| James Mandala  General Manager  Globalstar Canada Satellite Co.  115 Matheson Blvd. West - Suite 100  Mississauga, ON  Canada  L5R 3L1  Telephone: 905-712-7715  jmandala@globalstar.ca | Bill Mason  Manager, Numbering Administration  Canadian Radio-television and Telecommunications Commission  Central Building Les Terrasses de la Chaudière 1 Promenade du Portage  Gatineau, QC  Canada  K1A 0N2  Telephone: 819-953-8882  Fax: 819-953-0795  bill.mason@crtc.gc.ca |
| Deirdre Massiah-Gomes  Interested Party  Canada  Telephone: 416-684-3070  Massiahgomesdeirdre@gmail.com | Andrew Matoga  VP President  ISP Telecom  1155 Boul Rene-Levesque O Suite 2500  Montreal, QC  Canada  H3B 2K4  Telephone: 416-548-4626  Fax: 416-548-4847  andrew@isptelecom.net |
| Sabrena McBride  Product Manager  T-Mobile USA  3625 132nd Ave SE  Bellevue, WA  USA  98006  Telephone: 877-413-5903  Sabrena.mcbride32@t-mobile.com | Nancy McIntyre  Mgr - Planning & Engineering  TELUS  3777 Kingsway Floor 07S  Burnaby, BC  V5H 3Z7  Telephone: 604-908-2029  nancy.mcintyre2@telus.com |
| Nicola McLaughlin  Team Lead  Allstream  200 Wellington St W. F12  Toronto, ON  Canada  M5V 3G2  Telephone: 416-640-5271  Nicola.mclaughlin@allstream.com | Rodger McNabb  Manager Contracts and Receivables  Canadian LNP Consortium Inc.  350 Palladium Drive. Suite 208  Kanata, ON  Canada  K2V 1A8  Telephone: 613-287-0226  rodger.mcnabb@clnpc.ca |
| Priyesh Modi  Project Manager  Comwave Networks  61 Wildcat Rd  Toronto, ON  M3J 2P5  Telephone: 416-663-9700 X 320  Fax: 416-736-3165  pmodi@comwave.net | Daniel Morrison  Specialist - Voice Network Services  Bell Canada  100 Dundas St Flr 3  London, ON  Canada  N6A 5B6  Telephone: 519-850-6386  daniel.morrison@bell.ca |
| Sundar Nagulan  Team Lead - Voice Engineering  Comwave Networks  61 Wildcat Rd  Toronto, ON  M3J 2P5  Telephone: 647-427-8363  snagulan@comwave.net | Anh-Thu Nguyen  Ingenieur Planifi. & Gestion Du Trafic  Vidéotron ltée  2155 boul. Pie IX  Montréal, QC  Canada  H1V 2E4  Telephone: 514-380-1764  Anh-Thu.Nguyen@videotron.com |
| Catherine O’Grady  Senior Manager, Provisioning  Allstream  200 Wellington St W. F12  Toronto, ON  Canada  M5V 3G2  Telephone: 416-644-9703  catherine.ogrady@allstream.com | Sonali Pandey  E911 Administrator  Freedom Mobile Inc.  207 Queens Quay, Suite 710  Toronto, ON  Canada  M5J 1A7  Telephone: 647-551-8552  Fax: N/A  spandey@freedommobile.ca |
| Drew Penner  Manager – Network Planning and Carrier Relations  Navigata Communications Limited  177 Nepean Street, Suite 400  Ottawa, ON  K2P 0B4  Telephone: 613-317-3614  drew.penner@distributel.ca | Michelle Preda  Regulatory Affairs Manager  Iristel  675 Cochrane Dr  Markham, ON  L3R0B8  Telephone: 416-800-0032  mpreda@iristel.ro |
| Marc Pressault  Manager, Customer Champion  Distributel Communications Limited  177 Nepean Street, Suite 400  Ottawa, ON  Canada  K2P 0B4  Telephone: 613-317-3357  Marc.Presseault@distributel.ca | Robert Quance  President  ISP TELECOM Inc.  630 René-Lévesque blvd. West, Suite 2360  Montreal, QC  Canada  H3B 1S6  Telephone: 416-548-4636  Fax: 514-484-3662  robert@isptelecom.net |
| Brian Reyes  Traffic Specialist  Rogers Communications  8200 Dixie Rd  Brampton, ON  L6T0C1  Telephone: 647-747-4657  brian.reyes@rci.rogers.com | Quamrul Hasan Robin  E911 Consultant  Freedom Mobile  207 Queens Quay West Suite 710  Toronto, ON  M5J 1A7  Telephone: 647-225-9523  qrobin@freedommobile.ca |
| Karen Robinson  Network Planning Manager – Translations & Traffic Network Operation  TELUS  200 Consilium Place  Scarborough, ON  Canada  M1H 3J3  Telephone: 647-684-3053  Karen.Robinson3@telus.com | Grant G. Roughley  North Frontenac Telephone Corporation Ltd.  545 Eglintoin Ave. west Suite 214  Toronto, ON  Canada  M9C 5K6  Telephone: 519-505-4347  groughley@frontenac.net |
| Mark Rowed  Voice Engineer II  Globalstar  Suite 348 14-900 Village Lane  Okotoks, AB  Canada  T1S1Z6  Telephone: 985-335-1607  Mark.Rowed@globalstar.com | Leo Santoro  Network Analyst  Bell Mobility  5115 Creekbank Rd, Floor 3  Mississauga, ON  Canada  L4W 5R1  Telephone: 905-282-3021  Fax: 905-282-3106  leo.santoro@bell.ca |
| Rick Schleihauf  VP – Regulatory Affairs and Carrier Relations  Fibernetics Corporation  605 Boxwood Drive  Cambridge, ON  Canada  N3E 1A5  Telephone: 519-489-6700 ext 629  Fax: 519-653-7686  rschleihauf@corp.fibernetics.ca | Ofir Smadja  President  COMsolve  3601 Highway 7 East, Suite 400  Markham, ON  Canada  L3R 0M3  Telephone: 416-915-5008  info@comsolveinc.com |
| Eric Smith  Vice President, Regulatory Affairs  Canadian Wireless Telecommunications Association (CWTA)  80 Elgin Street, Suite 30  Ottawa, ON  Canada  K1P 6R2  Telephone: 613-233-5884 Ext. 255  Fax: 613-233-2032  [documentcontrol@cwta.ca](mailto:documentcontrol@cwta.ca) | Eric St-Yves  Analyste Planification  Videotron  2155 Pie IX  Montreal, QC  H1V 2E4  Telephone: 514-380-4751  eric.st-yves@videotron.com |
| Gerry Thompson  Manager, Intercarrier Relations  Rogers Communications Canada Inc.  350 Bloor Street East, 6th Floor  Toronto, ON  Canada  M4W 0A1  Telephone: 416-935-5239  Fax: 416-935-7719  Gerry.Thompson@rci.rogers.com | Kathleen Turnsek  ExaTEL  222 McIntrye Street West, Suite 505  North Bay, ON  Canada  P1B 2Y9  Telephone: 705-474-3364  Fax: 705-472-9202  kturnsek@vianet.ca |
| Bruce Uy  TN Administrator  Shaw Telecom Inc  2728 Hopewell Pl NE  Calgary, AB  T1Y 7J7  Telephone: 403-234-6271  Fax: 403-750-4501  bruce.uy@sjrb.ca | Craig Van Ham  Manager, Network Planning  Access Communications  2250 Park St  Regina, SK  S4N7K7  Telephone: 306-565-5365  Fax: 306-565-5395  Craig.vanham@myaccess.coop |
| Kelly T. Walsh  CNA Program Manager  Canadian Numbering Administrator  150 Isabella Street - Suite 605  Ottawa, ON  Canada  K1S 5H3  Telephone: 613-702-0016 ext 205  kelly.walsh@cnac.ca | Albert Yin  Comwave Networks Inc.  Telephone: 416-663-9700 Ext 330  Fax: 416-736-3165  ayin@comwave.net |
| Bill Young  North Frontenac Telephone Corporation Limited  1019 Windwood Dr.  Sharbot Lake, ON  Canada  K0H 2P0  Telephone: (613) 279-2193  Fax: (613) 561-6620  billyoung@nftctelecom.com | Clayton Zekelman  Managed Network Systems Inc.  3363 Tecumseh Rd. E.  Windsor, ON  Canada  N8W 1H4  Telephone: 519-985-8410  Fax: 519-985-8409  clayton@mnsi.net |
| Clayton Zekelman  Nexicom Telecommunications Inc  5 King St. E.  Millbrook, ON  L0A1G0  Telephone: 705-932-4344  czekelman@nexicomgroup.net |  |