## Schedule
| Highlight means that the date is in either Jan or Dec |  |  | CRTC Decision
| Highlight is a field that needs to be filled in (yyyy-mm-dd) |  |  | Relief Date | 2022-10-22
Highlight means you should have a look at the overall period
Item | Task or Event | PRIME | START | END | Notes | Date Check
1 | NPA 263 is set aside for future relief of QC NPAs 438-514 per CRTC decision 2017-38 but could be used elsewhere if required. For the purpose of this document the new NPA will be 263 | CRTC |  | 2017-02-03
2 | CNA identifies NPA exhaust of October 2023 and notifies CRTC staff, CSCN, NANPA & CISC, via email, that the NPA will exhaust within the future six year time period | CNA |  | 2019-03-26
3 | CNA published the Initial R-NRUF (July 2019) results which indicated that PED has moved out to June 2024 | CNA | 2019-06-15 | 2019-09-20
4 | CRTC issues Telecom Notice of Consultation regarding establishment of an ad hoc Relief Planning Committee | CRTC |  | 2020-01-30
5 | RPC Chair starts preparing and submitting RPC Chair Reports to the CISC, on an as required basis | RPC Chair | 2020-01-30 | 2023-02-17
6 | CNA conducts January 2020 R-NRUF results indicating the PED has moved out to March 2026 | CNA |  | 2020-03-24
7 | CNA issues July 2020 R-NRUF results indicating the PED has advanced to December 2024 | CNA |  | 2020-08-18
8 | CNA issues January 2021 R-NRUF results showing the PED has advanced to July 2024 | CNA |  | 2021-02-23
9 | CNA issues revised January 2021 R-NRUF results showing the PED has advanced to February 2024 | CNA |  | 2021-06-09
10 | CNA identifies NPA exhaust of February 2024 and notifies CRTC staff, CSCN, NANPA & CISC, via email, that the NPA will exhaust within the future three year time period | CNA |  | 2021-06-09 | Enter date
11 | CNA shares Revised January 2021 R-NRUF results with the CSCN and RPC indicating that the PED has advanced to February 2024 | CNA | 2021-06-09 | 2021-06-11
12 | CNA releases the PROC and announces the date for the initial RPC conference call | CNA | 2021-06-09 | 2021-06-17 | Enter date PROC is released
13 | RPC participants review PROC & submit contributions base on revised January 2021 R-NRUF results to RPC |  | 2021-06-17 | 2021-07-02
14 | CNA chairs initial RPC conference call to start development of PD, RIP, and Planning Letter and schedules future meetings/conference calls including creation & consultation with CATF and NITF | CNA, RPC | 2021-07-02 | 2021-07-16
15 | CNA chairs subsequent RPC conference calls to finalize PD & RIP | CNA, RPC | 2021-07-19 | 2021-08-02 | Enter target end date for finalized PD&RIP Enter real dates.
16 | CNA forwards the PD and RIP to the CISC and CRTC for approval | CNA | 2021-08-02 | 2021-08-09 | Enter real finalization dates
17 | Special Types of Telecommunications Service Users (911 PSAPs, alarm companies, ISPs, paging companies, etc.) to identify any concerns to RPC & CRTC | Special Users | 2021-07-16 | 2021-08-09 | Enter real finalization dates
18 | CRTC issues Telecom Decision approving the Relief Method, Relief Date, New NPA & Relief Implementation Plan (RIP) | CRTC | 2021-08-09 | 2021-12-09 | Enter best guess on when the CRTC issues a Decision
19 | CNA obtains relief NPA from NANPA | CNA | 2021-12-09 | 2021-12-16
20 | Task Forces, TSPs and users implement relief (starts on CRTC approval of RIP and ends on Relief Date) | TSPs | 2021-12-09 | 2022-10-22
21 | All Telecom Service Providers (TSPs) to develop and file individual consumer awareness programs with the CRTC (may be done collectively by Telecommunications Alliance) (starts on CRTC approval of RIP) | TSPs | 2021-12-09 | 2022-01-22
22 | CNA submits PL to NANPA | CNA | 2021-12-09 | 2021-12-16
23 | NANPA receives and posts Planning Letter to NANPA website (within 2 weeks of receipt from the CNA) | NANPA | 2021-12-16 | 2021-12-30
24 | All TSPs implement consumer awareness activities (starts on filing of Consumer Awareness Programs with the CRTC and is completed on the Relief Date) | TSPs | 2022-01-22 | 2022-10-22
25 | CNA issues media release (in coordination with TSPs and/or Telecommunication Alliance) (may start upon CRTC approval of RIP) | CNA | 2021-12-09 | 2022-03-22 | adjusted this date - 3 months
26 | All TSPs to notify all customers (including residence, business & special customers) of the new overlay NPA (may start upon the filing of Consumer Awareness Programs with the CRTC) | TSPs | 2022-01-22 | 2022-03-22 | Enter date (initial date is 9 months before relief) Adjusted this date -3 months
27 | TSPs to submit Progress Report #1 to NITF and CATF (starts after completion date for all TSPs to notify their customers and requires 2 weeks) | TSPs | 2022-03-22 | 2022-04-05
28 | NITF and CATF develop & submit Progress Report #1 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2022-04-05 | 2022-04-21
29 | RPC submits Progress Report #1 to CISC/CRTC (linked to NITF and CATF reports) | RPC | 2022-04-21 | 2022-05-05
30 | iconectiv TRA database updates to add Exchange Areas to new overlay NPA (starts on the date that the PL is posted to the NANPA web site and must be completed by 6 months prior to the Relief Date) | iconectiv TRA | 2021-12-09 | 2021-12-21
31 | All Telecommunications Service Users (including Special Users 911 PSAPs, alarm companies, ISPs, paging companies, etc.) to implement changes to their telecom equipment & systems to accommodate the new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Telecom Service Users | 2021-12-09 | 2022-10-22
32 | Payphone Providers Reprogram Payphones (starts on CRTC approval of RIP and ends on the Relief Date) | Payphone Providers | 2021-12-09 | 2022-10-22
33 | TSPs and database owners/operators to modify systems and industry databases (starts on CRTC approval of RIP and ends on the Relief Date) | TSPs & Database Owners | 2021-12-09 | 2022-10-22
34 | Operator Services & Directory Assistance Readiness (starts on CRTC approval of RIP and ends on the Relief Date) | TSPs | 2021-12-09 | 2022-10-22
35 | Directory Publisher Readiness for overlays (ability to identify the NPA in telephone numbers in the directory published after the Overlay NPA is activated) (starts on CRTC approval of RIP and ends on the Relief Date) | Directory Publishers | 2021-12-09 | 2022-10-22
36 | 9-1-1 Systems and Databases Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | PSAPS, 9-1-1 Service Providers & TSPs | 2021-12-09 | 2022-10-22
37 | Network Systems & Equipment Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2021-12-09 | 2022-10-22
38 | Service Order & Business System Readiness (starts on CRTC approval of RIP and ends on the Relief Date) | TSPs | 2021-12-09 | 2022-10-22
39 | International Gateway Switch Translations Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Int’l TSPs | 2021-12-09 | 2022-10-22
40 | Canadian Local Number Portability Consortium (CLNPC) Database Readiness for new NPA (starts on CRTC approval of RIP and ends on the Relief Date) | CLNPC & NPAC | 2021-12-09 | 2022-10-22
41 | Toll Free SMS Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Toll TSPs | 2021-12-09 | 2022-10-22
42 | TSPs apply for Test CO Codes in new NPA (applications may be submitted no more than 6 months and no less than 66 days prior to the start date for the Inter-Carrier Testing Period) (Section 7.16.4 Canadian RP GL) | TSPs | 2021-12-22 | 2022-04-17
43 | Develop Inter-Carrier Network Test Plans and prepare for testing (individual TSPs to make arrangements in accordance with interconnection agreements) (may start on CRTC approval of RIP and must be completed by start date for the Inter-Carrier Testing Period) | NITF & TSPs | 2021-12-09 | 2022-06-22
44 | All international and domestic Telecommunications Service Providers (TSPs) must activate the new NPA in their networks by the start date for the Inter-Carrier Testing Period | TSPs | 2021-12-09 | 2022-06-22
45 | Activation date for Overlay NPA Test CO Codes and Test Numbers in network (should be completed by the start date for the Inter-Carrier Testing Period) | TSPs |  | 2022-06-22 | Adjusted this date to avoid July timeframe
46 | Inter-Carrier Testing Period (subject to Inter-Carrier Network Test Plans) (starts about 3 months prior to the Relief Date, and ends about 1 month after the Relief Date) | NITF & TSPs | 2022-06-22 | 2022-11-21 | Look at overall period
47 | TSPs to submit Progress Report #2 to NITF (starts on commencement of Inter-Carrier Testing Period) | TSPs | 2022-06-22 | 2022-07-08
48 | NITF develops & submits Progress Report #2 to RPC (linked to TSP reports to NITF) | NITF | 2022-07-08 | 2022-07-22
49 | RPC submits Progress Report #2 to CRTC staff (linked to NITF report) | RPC | 2022-07-22 | 2022-08-08
50 | Relief Date (earliest date when CO Codes in new NPA may be activated) |  |  | 2022-10-22 | Enter relief date
51 | TSPs submit Final Report to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs | 2022-10-24 | 2022-11-07
52 | NITF and CATF develop & submit Final Progress Report to RPC (linked to TSP reports to NITF and CATF) | NITF | 2022-11-08 | 2022-11-22
53 | The RPC submits Final Progress Report to CRTC staff (linked to NITF and CATF reports) | RPC | 2022-11-22 | 2022-12-06 | Look at overall period
54 | TSPs disconnect Test Codes & Numbers, and submit Part 1 form to return Test Codes (starts 1 month after Relief Date and allows 1 month for completion) | TSPs | 2022-11-21 | 2023-01-13 | Adjust this date to January 2023
55 | RPC Chair submits, to the CISC, the final RPC Chair report indicating that the NPA 263/438/514 ad hoc RPC is no longer required | RPC Chair | 2023-01-13 | 2023-02-17 | Update NPA as required
Formulas:
END = [START]+14
END = EDATE([START],4)
START = [END, row above]
START = WORKDAY([END, row above],1,Holidays!$B2:B210)

## Holidays
2016
2016-01-01 | 2016-01-01 | New Years's Day
2016-02-15 | 2016-02-15 | Family Day
2016-03-25 | 2016-03-25 | Good Friday
2016-03-28 | 2016-03-28 | Easter Monday
2016-05-23 | 2016-05-23 | Victoria Day
2016-06-24 | 2016-06-24 | St Jean Baptiste Day
2016-01-01 | 2016-01-01 | Canada Day
2016-08-01 | 2016-08-01 | Civic Holiday
2016-09-05 | 2016-09-05 | Labour Day
2016-10-10 | 2016-10-10 | Thanksgiving
2016-11-11 | 2016-11-11 | Remember Day
2016-12-26 | 2016-12-26 | Christmas Day
2016-12-27 | 2016-12-27 | Boxing Day
2017
2017-01-02 | 2017-01-02 | New Years's Day
2017-02-20 | 2017-02-20 | Family Day
2017-04-14 | 2017-04-14 | Good Friday
2017-04-17 | 2017-04-17 | Easter Monday
2017-05-22 | 2017-05-22 | Victoria Day
2017-06-23 | 2017-06-23 | St Jean Baptiste Day
2017-07-03 | 2017-07-03 | Canada Day
2017-08-07 | 2017-08-07 | Civic Holiday
2017-09-04 | 2017-09-04 | Labour Day
2017-10-09 | 2017-10-09 | Thanksgiving
2017-11-13 | 2017-11-13 | Remember Day
2017-12-25 | 2017-12-25 | Christmas Day
2017-12-26 | 2017-12-26 | Boxing Day
2018
2018-01-01 | 2018-01-01 | New Years's Day
2018-02-19 | 2018-02-19 | Family Day
2018-03-30 | 2018-03-30 | Good Friday
2018-04-02 | 2018-04-02 | Easter Monday
2018-05-21 | 2018-05-21 | Victoria Day
2018-06-22 | 2018-06-22 | St Jean Baptiste Day
2018-07-02 | 2018-07-02 | Canada Day
2018-08-06 | 2018-08-06 | Civic Holiday
2018-09-03 | 2018-09-03 | Labour Day
2018-10-08 | 2018-10-08 | Thanksgiving
2018-11-12 | 2018-11-12 | Remember Day
2018-12-25 | 2018-12-25 | Christmas Day
2018-12-26 | 2018-12-26 | Boxing Day
2019
2019-01-01 | 2019-01-01 | New Years's Day
2019-02-18 | 2019-02-18 | Family Day
2019-04-19 | 2019-04-19 | Good Friday
2019-04-22 | 2019-04-22 | Easter Monday
2019-05-20 | 2019-05-20 | Victoria Day
2019-06-24 | 2019-06-24 | St Jean Baptiste Day
2019-07-01 | 2019-07-01 | Canada Day
2019-08-05 | 2019-08-05 | Civic Holiday
2019-09-02 | 2019-09-02 | Labour Day
2019-10-14 | 2019-10-14 | Thanksgiving
2019-11-11 | 2019-11-11 | Remember Day
2019-12-25 | 2019-12-25 | Christmas Day
2019-12-26 | 2019-12-26 | Boxing Day
2020
2020-01-01 | 2020-01-01 | New Years's Day
2020-02-17 | 2020-02-17 | Family Day
2020-04-10 | 2020-04-10 | Good Friday
2020-04-13 | 2020-04-13 | Easter Monday
2020-05-18 | 2020-05-18 | Victoria Day
2020-05-18 | 2020-05-18 | St Jean Baptiste Day
2020-07-01 | 2020-07-01 | Canada Day
2020-08-03 | 2020-08-03 | Civic Holiday
2020-09-07 | 2020-09-07 | Labour Day
2020-10-12 | 2020-10-12 | Thanksgiving
2020-11-11 | 2020-11-11 | Remember Day
2020-12-25 | 2020-12-25 | Christmas Day
2020-12-28 | 2020-12-28 | Boxing Day
2021
2021-01-01 | 2021-01-01 | New Years's Day
2021-02-15 | 2021-02-15 | Family Day
2021-04-02 | 2021-04-02 | Good Friday
2021-04-05 | 2021-04-05 | Easter Monday
2021-05-24 | 2021-05-24 | Victoria Day
2021-06-24 | 2021-06-24 | St Jean Baptiste Day
2021-07-01 | 2021-07-01 | Canada Day
2021-08-02 | 2021-08-02 | Civic Holiday
2021-09-06 | 2021-09-06 | Labour Day
2021-10-11 | 2021-10-11 | Thanksgiving
2021-11-11 | 2021-11-11 | Remember Day
2021-12-25 | 2021-12-25 | Christmas Day
2021-12-26 | 2021-12-26 | Boxing Day
2022
2022-01-01 | 2022-01-01 | New Years's Day
2022-02-22 | 2022-02-22 | Family Day
2022-04-15 | 2022-04-15 | Good Friday
2022-04-18 | 2022-04-18 | Easter Monday
2022-05-23 | 2022-05-23 | Victoria Day
2022-06-24 | 2022-06-24 | St Jean Baptiste Day
2022-07-01 | 2022-07-01 | Canada Day
2022-08-01 | 2022-08-01 | Civic Holiday
2022-09-05 | 2022-09-05 | Labour Day
2022-10-10 | 2022-10-10 | Thanksgiving
2022-11-11 | 2022-11-11 | Remember Day
2022-12-25 | 2022-12-25 | Christmas Day
2022-12-26 | 2022-12-26 | Boxing Day
2023
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2024
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2025
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2026
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2027
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2028
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2029
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
0 |  | Boxing Day
2030
0 |  | New Years's Day
0 |  | Family Day
0 |  | Good Friday
0 |  | Easter Monday
0 |  | Victoria Day
0 |  | St Jean Baptiste Day
0 |  | Canada Day
0 |  | Civic Holiday
0 |  | Labour Day
0 |  | Thanksgiving
0 |  | Remember Day
0 |  | Christmas Day
2030-12-26 | 2030-12-26 | Boxing Day